## 16.2 SM Priority List
Rqmts Status | PD Team | Rqmts Doc | Priority | Rank | JAZZ # | Description | Status | PD Status | SM Critical item from Carnetta's list 3/11
N/A |  | N/A | 1 | 1 | Get Jazz # from Tom. May be multiple tickets. | Patients can no longer use SM. | This may be related to a VistA patch that broke something. |  | Patients can no longer use SM: There is still massive amounts of SM patients users who all of a sudden can’t find their team to send a SM message to. Suggest this be a high priority with the Sustainment team to find out why.
N/A |  | N/A | 1 | 2 | Get Jazz # from Tom. May be multiple tickets. | PCMM team and other associations dropped at several sites 4/1: fix that went out only addresses specific clinic numbers. Carnetta is putting together a Tiger team to review/discuss. | This may be related to a VistA patch that broke something. | Need specific instances from prod where this is happening. "Need specific instances from prod where this is happening in ""massive"" quantities. The following are the items that sustainment is investigating: CA I7700027FY16 “SM - User with SM and premium MHV accounts does not appear in SM” Most of the JAZZ/CA items for PCMM-R are related to issues with triage groups, veteran’s providers are dropped from their lists and issues with their account settings. I7519396FY16 SM - User linked to two providers and coordinator cannot remove the incorrect one"" I7768480FY16 SM - Users of the triage group 'Home TeleHealth L2 - GLA_TH' can't send messages to the group I7772410FY16 SM - Provider sent 2 uncompleted messages, which recipient received, but cannot open I7772480FY16 SM - User who was able in January to access and use SM, is now not able to access the feature I6915810FY16 Trying to see her escalated secure messages and she can see the first page but when she clicks to the second page it is giving error ""This page can't be displayed."" I6893720FY16 unable to create new message to triage group, I6911223FY16 THE VETERANS SECURE MESSAGE DROP DOWN LIST HAS NOT UPDATED IN THREE YEARS. I6915810FY16 ISSUE: Trying to see her escalated secure messages and she can see the first page but when she clicks to the second page it is giving error ""This page can't be displayed. Please make sure the website is correct."" " | Providers can’t use SM: PCMM-R: There is some reason providers are not able to be associated to use SM. This problem is occurring at sites switching over to use PCMM-R. Suggest this be a high priority with the Sustainment team to find out why.
N/A |  | N/A | 1 | 3 | Defect 271648 | "Error saving" message displayed when updating Triage Groups. |  | The root cause for this defect needs to be analyzed. The defect needs a higher priority if it needs to be fixed. 4/19 Need cases from Prod ( JAZZ or remedy tickets or emails ) of the latest site(s) that are having this issue . VFE will do root cause analysis. Can start work as soon as the info is received. | SM Admin Edit a Triage Group: Users are getting the same error that could be because of different issues. This error occurs often at some sites. 4/14: North FL South GA was getting this error every few seconds causing the employee to work the night shift just to perform job duties.
In Progress |  | SM Clinician BUC | 1 | 4 | Defect 280669 (4/2 defect) | Address approx 20K messages where sender=receiver only (no other recipient) when: 1) replying from the Sent folder. 2) CC recipient: was added to message reply. This is the follow on to Defect 280669 *May need to add auto draft saved messages that were sent which did not include the attachments. | 4/14: Clinicin BUC to include requirements for a system folder that requires Clinical Review. Clinical Review folder to include copies of messages for: 1) Sender=Receiver 2) Draft Messages Saved as Progress Notes 3) Messages that were sent but removed attachments | 2/23: Defect Fixed in Production (sender=receiver when messages replied to from Sent folder). 4/2: Defect Fixed in Production (sender=receiver when CC recipient: was added to message reply). 4/14: PD needs this prioritized and requirements for how to handle the messages impacted before defect resolved. 4/19 Need updated BUC with the requirements | 4/14: Patient Safety Issue 3090
In Progress |  | SM Clinician BUC | 1 | 5 |  | Identify, review, and adress draft messages that have been saved as CPRS Progress notes (patient safety issue) Including messages that Clinicians are unable to delete or send (Message included as part of CPRS Progress Notes prior to OCT 10th) *Make sure to include the system removing from the system folder and draft folder. *Potential alert after 30 days if no action taken by the clinician. | 4/14: Clinicin BUC to include requirements for a system folder that requires Clinical Review. Clinical Review folder to include copies of messages for: 1) Sender=Receiver 2) Draft Messages Saved as Progress Notes 3) Messages that were sent but removed attachments | Late 2015: Defect Fixed in Production. 4/14: PD needs this prioritized and requirements for how to handle the messages impacted before defect resolved. 4/19 Need updated BUC with the requirements | Patient Safety issue 2999: Provide requirements and implement reviews of draft messages saved as progress notes. Most of the requirements should be captured. This needs to be priority work per HIMS to clean-up patient records.
Not Started |  | SM Clinician BUC | 1 | 6 |  | Handle messages that were sent without the attachment. Follow on to defects: Defect 290411 Defect 220151 SM Reply to messages with attachments not working with Auto-save function | 3/17: This is happening to both Clinicians and Patients. This has been happening since Sept 2015. Clinical Review folder to include copies of messages for: 1) Sender=Receiver 2) Draft Messages Saved as Progress Notes 3) Messages that were sent but removed attachments | 4/14: PD is working on this and development testing will be ready next week. 4/19: VFE team is working on this. ( Defect 290411 Defect 220151 ) what is the follow on work on this? | 4/14: Patient Safety Issue 3145
In Progress |  | SM Admin Portal BUC | 1 | 7 | Story 220342 | Allow Triage Group to be deleted when there are incomplete messages older than 12 months | May not need this if the code is implemented to have the MHV system automatically mark incomplete messages older than 12 months as: 1) unescalated (remove escalation flag if applicable) 2) mark as completed | Awaiting updated BUC from business. 4/19 Need updated BUC with the requirements
Not Started |  | SM Clinician BUC | 1 | 8 |  | If a message is forwarded or CCd to a clinician that has set a preference to only show messages assigned to me, then that clinician does not receive that message. | Discuss if this is a Redesign enhancement or to be addressed as a critical enhancement.
In Progress |  | Delegation BUC | 2 | H | Story 234879 | Story: Analysis of Delegation and Surrogacy BUC |  | Need finalized requirements. PD provided comments on BUC on 3/11. Need confirmation if this is priority #1 for 16.3 release. 4/19: No SM changes for surrogacy and delegation (phase 1)
In Progress |  | SM Patient BUC | 2 | H | NO CR submitted | SM Allow Veterans to remove recipients from their "To" list. Patient to self select the recipient. Add requirements for SM Administrator as well. Difine what this group does. | This will include preventing disassociations by the MHV system. Need to coordinate after PCMM-R release. *Starting in November Release, Veterans may see multiple PC TG and have no way of removing TG they are no longer associated with. | Awaiting updated BUC from business. 4/19 Need updated BUC with the requirements
N/A |  | N/A | 2 | H | Story 155384 | Story: SM handling non-treatment facilities in Secure Messaging (Performance Improvement) 11/13 VFE team update: No requirements needed. Depending on workload for 16.1, this can be addressed | Functional and Technical analysis completed | Do not need requirements from business. Will be worked on based on priority
In Progress |  | SM Admin Portal BUC | 3 | M | NO CR submitted | SM user is not deactivated when a user account is deactivated in MHV admin portal | issue identified in Prod. When a user's account in MHV is deactivated, it should deactivate the account duplicate of "SM user table and MHV Admin Portal sync for VA staff and VA patients"? | Awaiting updated BUC from business. 4/19 Need updated BUC with the requirements. Migration to SRE will resolve this issue
In Progress |  | SM Admin Portal BUC | 3 | M | NO CR submitted | SM user table and MHV Admin Portal synchronization for VA staff and VA Patients. | The SM User Account information should match and be updated when the MHV Admin Portal user account is updated. Updates made to the MHV Administrative user table should be automatically be made to the SM user table to include: identity updates, deactivations, and Treatment Facility changes. May need to utilize APIs. | Awaiting updated BUC from business. 4/19 Need updated BUC with the requirements. Migration to SRE will resolve this issue
In Progress |  | SM Admin Portal BUC | 3 | M | NO CR submitted | Deactivating VA Staff in SM | SM requires the network ID to be unique and those network IDs can be assigned to new employees. SM is not set up to allow network IDs to be reused. 11/13 VFE team update:Need requirements from business | Awaiting updated BUC from business. 4/19 Need updated BUC with the requirements.
In Progress |  | SM Admin Portal BUC | 3 | M | NO CR submitted | “Add Patient to Facility” menu, include phone and email fields for VA staff member requesting Patient to be added to facility. |  | Requirements complete in BUC . Will be worked on based on Priority
In Progress |  | SM Admin Portal BUC SM Clinician BU | 3 | M |  | MHV System will automatically mark incomplete messages older than 12 months as: 1) unescalated (remove escalation flag if applicable) 2) mark as completed. | Need requirements from business. This will allow TG to be deleted that have old messages that are older than 12 months and prevent SM admins from assigning messages that are older than 12 months. One-time script (stored procedure) to flag all previously archived messages are completed and not escalated. This includes non-archived incomplete messages that are greater than one year. 11/13 VFE team update: Requirements not received from business | Awaiting updated BUC from business. 4/19 Need updated BUC with the requirements.
In Progress |  | SM Clinician BUC | 3 | M | Story 29247 | Story: Include/Exclude the Messages in the message thread and capture the Workload/Historical Note - ANALYSIS | Need requirements from business. | Awaiting updated BUC from business. 4/19 Need updated BUC with the requirements.
In Progress |  | SM Patient BUC | 3 | M | NO CR submitted | Reduce message reply expiration date for patients from 120 days to 30 days |  | 4/19 Requirements complete in BUC. Will be worked on based on Priority
In Progress |  | SM Clinician BUC | 3 | M | Story 17788 | SM DG based on PCMM/OERR | Distribution group size needs to be increased. Allow DG messages to be sent to all patients in TG based on PCMM or OERR teams. | Awaiting updated BUC from business. 4/19 Need updated BUC with the requirements.
New |  | Clinician BUC potentially | 3 | M | Being investigated | A Surrogate, that is not assigned to the Triage Group, goest to Finish Message Option, the message defaults assignment to another user. | 3/17: this was briefed on 2/16 noon call. Ro to pull the minutes. This may be considered an enhancement if specific requirements were never provided. | There is no JAZZ item for this. Need details from business on the specific issue. Does it happen for all surrogate or is it a specific user? This maybe an enhancement for changing the surrogate functionality. 4/19 Need updated BUC with the requirements.VFE team is able recreate this scenario. Need requiremetns for the enhancement change
New |  |  | 3 | M |  | For Business Consideration: Remove FWD feature. When messages are forwarded, the forwarded recipient is not listed on the message. When CCd message comes through as a BCC. | Will be considered with redesign. May need to look at quick fixes to implement before | 4/19 Need updated BUC with the requirements.
In Progress |  | Timeout Messaging BUC | 4 | L | Story 193205 | SM Clinician - 5 minute warning message prior to timeout | Need finalized requirements; Analysis work is in progress on the Liferay. | Dependency on Liferay migration
In Progress |  | Timeout Messaging BUC | 4 | L | Story 193364 | Story: SM Patient received warning message 5 min prior to timeout along with the ability to count user keystrokes | Need finalized requirements | Dependency on Liferay migration
In Progress |  | Timeout Messaging BUC | 4 | L | Story 193366 | Story: SM Admin receives warning message 5 min before timeout | Need finalized requirements | Dependency on Liferay migration
In Progress |  | Email Sync BUC | 4 | L | Story 190680 | Turing on/off SM notifications from MHV registration and profile Email Synchronization and SM Notification Preference Updates | Awaiting updated BUC from business. | Awaiting updated BUC from business.
In Progress |  | SM Clinician BUC | 4 | L | Story 225688 | Secure Messaging Staff-Side Escalated Messages Enhancement | Add an exclamation point (!) before the From: Field (in front of the Sender’s name) along with bolding the font in the entire line when messages go beyond two working days. | Awaiting updated BUC from business.
In Progress |  | SM Clinician BUC | 4 | L | Story 17787 | Spell check functionality | Evaluated TRM approved tools to implement this – all of them are browser based solutions, where the user has to enable in their respective browsers. | PD provided options from TRM but not approved by business since they are browser based solutions
In Progress |  | SM Clinician BUC | 4 | L | NO CR submitted | Add “Search by Assigned” in all folders |  | Awaiting updated BUC from business.
N/A |  | SM Admin Portal Redesign | 4 | L | Story 182460 | SM Report for Facility admin to view list of all patients blocked from facility | Requirements received from business with CR. 11/13 VFE team update: No requirements needed. | Requirements complete. Will be worked on based on Priority
|  |  | TBD |  | Story 223834 | Story: Turn off deprecated SM Ensemble web service methods |  | Ongoing
|  |  | TBD |  | Story 249962 | Story: Analysis - Adding Save option in reminder folder |  | Awaiting updated BUC from business.
|  |  | TBD |  | Story 250743 | Story: SM need to retrieve all Clinician associations outside of team role code 43 |  | VFE team is doing analysis of the issue. 4/19 Is this a priority for VFE ( 16.3)
|  |  | TBD |  | Story 264355 | Story: SM BLOCKED users issue analysis from production |  | Awaiting updated BUC from business.
|  |  | Defect | Defect | Need Jazz # | Notifications with missing Message IDs
|  |  | Defect | Defect | Defect 190758 | Defect: PROD - Admin user reported of a search issue in MHV Admin portal
|  |  | Defect | Defect | Several Jazz items | Fortify defect fixes | This is unplanned work for prod/critical issues. Several defect fixes for fortify issues in order to get ATO.
|  |  | Defect | Defect | Defect 118657 | Defect (Production): System Reports page on the SM Admin Portal gets distorted | Open - need PD to retest
|  |  | Defect | Defect | Defect 163914 | Defect: SM Provider’s not able to Save Progress notes due to Ensemble receiving errors for TIU ACK from SM Servers
|  |  | Defect | Defect | Defect 198647 | Defect: PROD - SM opt in issues | 8/19: Provided feedback to Lisa and others during the week of 8/12. 6 specific cases were identified and email from Lisa contained screenshots as well. PD provided input on each. 1/25/16 Need update from business to see if the defect is still valid
|  |  | Defect |  | Defect 220691 | Defect: PROD - Multiple messages are sent to the recipient | this is auto save issue - sept 2015 maybe resolved. PD to retest
|  |  | Defect |  | Defect 221164 | Defect: PROD - IE11 web browser compatibility issue with Secure Messaging File Attachment
|  |  | Defect |  | Defect 225847 | Defect: Not able to Delete and Send few messages from Draft folder.
|  |  | Defect |  | Defect 267476 | Defect: SM WLC Service Connected Condition issue filing WLC - Boston VAMC
|  |  | Defect |  | Defect 267484 | Defect: SM WLC Patient Problem List not showing Items mapped to ICD-10 Diagnosis issue filing WLC - Boston VAMC
|  |  | Defect |  | Defect 268778 | Defect: SM (Production) - Message is not copied to Reminder folder after setting up a reminder from Draft folder
In Progress |  | SM Patient BUC | N/A | N/A |  | Stop hiding SM messages older than 365 days of original date from SM users. Let Veteran self select what they want on their dropdown list and dropdown order/default | 4/14: This should be part of Redesign. Carnetta discussing with PHR Policy Group. Need input from HIMS, General Council and Privacy. Need to come up with a better way to hide/show messages. Impact - all SM users will see all messages ever sent or ever received. HIMS/Privacy recommended user driven archive. | PD has not received any requirements for this.  We would like to see the draft requirements for discussion. As mentioned earlier, if we can have a separate flow (new Archive folder in the left navigation), where we can have user select how far back would they want to filter their messages and not interrupt the flow with existing system folders. | PHR Policy recommendation: Stop hiding SM messages older than 365 days of original date from SM users. SM users are not told in SM T&C that messages older than a certain origination date will not be accessible. PHR Policy group recommends that this feature be stopped as it could be considered a Patient Safety issue if the message is hidden without regard to the last activity date. SM users should have a preference or something that will determine when messages should be hidden.
In Progress |  | SM Admin Portal BUC | N/A | N/A | Story 202051/249932 | VISN Realignment 1) Facilty moves, 2) CBOC moves, and 3) VISN moves. Story: Admin Portal - Impact of moving a facility from one VISN to another in Admin portal and Secure Messaging - Analysis | 4/14: Will be addressed with Admin Portal Redesign. | awaiting updated BUC from business.
In Progress |  | SM Patient BUC | N/A | N/A | NO CR submitted | Visual indicator of messages that were reassigned from one HCT member to another TG/HCT member. Include sent audit trail to whom the messages were sent/reassigned (PHR Policy Group - Patient Safety) | V/CHIO needs input from Redesign Team (PTP) on how to address. Veteran should see that a message that they sent to person A was reassigned to person B by someone else and on what date. 4/14: Will be addressed by SM Redesign | awaiting updated BUC from business.
N/A |  | N/A | N/A | N/A |  | Legacy-SRE code migration to support Feb and May 2016 production release (MHV and SM). | Ongoing | Ongoing
N/A |  | N/A | N/A | N/A | Story 200316 | SM WLC – National Release Support | Ongoing | After Patch 24 is installed at all the sites ( 3/31) we will need to coordinate when the national roll out.
|  |  | N/A | SM Performance items | 179470 | Story: Improve user experience in IE and Chrome by setting the right meta tag value
|  |  | N/A | SM Performance items | 179773 | Defect: PROD only - JMX error in prod from ms7a MHV managed node
|  |  | N/A | SM Performance items | 188007 | Defect: FORTIFY PROD - Weak XML Schema: Unbounded Occurrences (Environment, Configuration) - AdminQueries.wsdl
|  |  | N/A | SM Performance items | 188052 | Defect: FORTIFY PROD - Weak XML Schema: Unbounded Occurrences (Environment, Configuration) - MHVSM_MHVAuthentication.wsdl
|  |  | N/A | SM Performance items | 188058 | Defect: FORTIFY PROD - Weak XML Schema: Unbounded Occurrences (Environment, Configuration) - MHVSM_TIUNote.wsdl
|  |  | N/A | SM Performance items | 188063 | Defect: FORTIFY PROD - Weak XML Schema: Unbounded Occurrences (Environment, Configuration) - MHVSMQueryCallback.wsdl
|  |  | N/A | SM Performance items | 217649 | Defect: PROD - JTA transaction timeout expiration in MHV
|  |  | N/A | SM Performance items | 226323 | Defect: commons collections 3.2 is not being used by Jenkins inconsistently with SM builds