## Completed (hidden)
Former Sprints Plan Rows are hidden - unhide to view more info
| Sprint 34: "Warm Up" | Focal | Dev | Design | Product | Notes
15643 | Google Analytics Set Up with Analytics Team |  |  |  |  | closed
14474 | BUG: Basic auth page showing up in search and going to 401 error page |  |  |  |  | closed
14452 | Type Ahead POC: Implement Feature Flag |  |  |  |  | moved to sprint 35
15674 | Data Analytics Review |  |  |  |  | moved to sprint 35
15668 | Team Observations + Exploration Notes |  |  |  |  | moved to sprint 35
15674 | Search.gov Audit |  |  |  |  | moved to sprint 35
12543 | Analytics Reporting Request | Analytics
| Sprint 35: "1st Sprint" (Nov 18 - Dec 1) | Focal | Dev | Design | Product | Notes
Theme: Onboarding & Analytics & Type Ahead
14452 | Type Ahead POC: Implement Feature Flag | Sam | 3
13494 | Analytics Implementation Search Type-Ahead POC | Sam | 5 |  |  | dev work completed but will roll over to sprint 36: dependent on analytics team to complete their review
15674 | Search.gov Analytics Audit | Denise |  |  | 3
15668 | Team Observations + Exploration Notes- Part 1 | ALL | 2 | 2 | 2
16360 | Identify KPIs for search (onsite + offsite) | Denise |  |  | 5
14897 | New Team VSP Orientation- Denise | Denise |  |  | 3
15853 | New Team VSP Orientation #15853 -Sam | Sam | 3
15858 | New Team VSP Orientation - Megan | Megan |  | 3
16189 | Social Media User Research | Megan |  | 3
16820 | Social Media User Research - scam awareness | Megan |  | 1
14955 | VA.gov Search Click Tracking API - Validation Testing (Front End) #14955 | Sam | 3 |  |  | Type Ahead POC implementation was prioritized and therefore this will not be completed in Sprint 35
12331 | [Discovery] - Create research plan for VA.gov sitewide search usability study #12331 | Megan |  | 5
16186 | Explore + Establish Medallia Survey Implementation #16186 | Megan |  | 2 |  | Was unplanned
| Totals | 45 | 16 | 16 | 13
GH # | Sprint 36: (Dec 2-15) |  | Focal | Dev | Design | Product | Notes
Theme: Click Tracking/ Type Ahead POC/ Discovery/ XML Sitemap/ Product Definition
16367 | [Click Tracking] VA.gov Search Click Tracking API Back End Development |  | Sam | 5 |  |  | Sam is anticipating this will be considerable and may cause others to bump (rolling over into sprint 37)
14955 | [Click Tracking] VA.gov Search Click Tracking API Front End Development |  | Sam | 5 |  |  | Back end needs to be done first ( rolling over into sprint 37
16658 | [Type Ahead POC] Creating a set of canned query suggestions to populate type ahead suggestions |  | Denise |  |  | 3 | Rollover to sprint 37
16730 | [Type Ahead POC] Solidify OKRs for Type Ahead |  | Denise |  |  | 2 | Will be Completed - Denise to complete remaining tasks
16743 | [Type Ahead POC] POC QA Check |  | Sam | 3 |  |  | complete
16652 | [XML Sitemap] Collecting a baseline understanding of XML Sitemap |  | Sam | 3 |  |  | Rollover to sprint 37
16287 | [XML Sitemap] Add R&S to sitemap for indexing |  | Sam | 5 |  |  | Rollover to sprint 37
16822 | [Discovery] Research plan approvals |  | Megan |  | 2 |  | complete
16823 | [Discovery] Analytics research plan |  | Megan |  | 5 |  | complete
12333 | [Discovery] Create DRAFT conversation guide for VA.gov sitewide search usability study |  | Megan |  | 5 |  | complete
16650 | [Onboarding] Review Content + IA Onboarding Materials |  | ALL | 1 | 1 | 1 | complete
16360 | [Product Dfn] Identify KPIs for search (onsite + offsite) |  | Denise |  |  | 5 | onsite is complete - extracted offsite in new ticket for future focus
16188 | [Product Dfn] Define Metrics for DOMO Dashboard |  | Denise |  |  | TBD | complete
17704 | [Type Ahead POC] Address Accessibility Issues related to 508 Defect Level 1 |  | Sam | 13 |  |  | UNPLANNED complete
Support Tickets - Just FYI
16625 | [Discovery] User Survey Request for Public Websites - Medallia Pilot |  | Analytics | 0 | 0 | 0 | Dependency Ticket
16914 | [Type Ahead POC] VSA dev intent or spot check review for Search Typeahead |  | Accesibility | 0 | 0 | 0 | Dependency Ticket
16944 | [Typeahead POC] Accessibility feedback for the Spot Check Review |  | Accesibility | 0 | 0 | 0 | Dependency Ticket
16943 | Accessibility feedback for the Spot Check Review |  | Accesibility | 0 | 0 | 0 | Dependency Ticket
17002 | [Type Ahead] Staging Review | UP | Collab Cycle | 0 | 0 | 0 | Dependency Ticket
17005 | [Click Tracking] Project Kickoff |  | Collab Cycle | 0 | 0 | 0 | Dependency Ticket
17009 | Search & Discovery - Search.gov fwd proxy endpoint |  | Operations | 0 | 0 | 0 | Dependency Ticket
| Totals |  | 59 | 35 | 13 | 11
| Sprint 37: (Dec 16-29) |  | Focal | Dev | Design | Product | Notes
Info: | [Code Freeze: Dec 25-Jan 4] [PTO: Dec 24+25 All Dec 28-29 John + Denise]
14955 | [Click Tracking] VA.gov Search Click Tracking API Front End Development |  | Sam | 3 |  |  | Back end needs to be done first (changed the estimate from a 5 to a 3)
16367 | [Click Tracking] VA.gov Search Click Tracking API Back End Development |  | Sam | 1 |  |  | Platform team is working on this is a tracking ticket for Sam
16652 | [XML Sitemap] Collecting a baseline understanding of XML Sitemap |  | Sam | 3 |  |  | Rollover from sprint 36
16287 | [XML Sitemap] Add R&S to sitemap for indexing |  | Sam | 5 |  |  | Rollover from sprint 36
16738 | [XML Sitemap] Remove url from sitemap XML |  | Sam | 3 |  |  | will roll over to 38 b/c it requires code changes that will wait until post freeze
17539 | [Discovery] Finalize conversation guide and research plan (based on input from VAPO review) |  | Megan |  | 3 |  | blocked by 16902 - will roll over to sprint 38
16886 | [Discovery] Approval for Conversation Guide |  | Megan |  | 3 |  | dependent on17539
16936 | [Discovery] Comparative Analysis Research (Part 1) |  | Megan |  | 8 |  | complete - megan to make notes in GH issue and close
16902 | [Discovery] Research Plan reviews with POs |  | John |  | 5 | 5 | Ongoing - final session planned on Jan 5 - rolling over to Sprint 38
17532 | [Product Dfn] Establish List of top 50 Search Terms |  | Denise |  |  | 3 | Rollover to sprint 38
16658 | [Type Ahead 1.0] Creating a set of canned query suggestions to populate type ahead suggestions |  | Denise |  |  | 3 | (Rollover from sprint 36)
| Totals |  | 45 | 15 | 19 | 11
Dependencies for Reference
17009 | search.gov fwd proxy endpoint |  | Platform
16446 | [XML Sitemap] Remove REAP page from the sitemap and best bets |  | CMS | 3 |  |  | CMS to do the work to make this disappear (will have to follow up in sprint 38)
| Sprint 38: (Dec 30-Jan12) |  | Focal | Dev | Design | Product | Notes
Info: | [Code Freeze: Dec 25-Jan 4] [PTO: Jan 1:All + Dec 30-31: John + Denise]
17797 | [Type Ahead 1.0] Spell Check API Exploration |  | Sam | 2 |  |  | we have been told that Search.gov does not offer an API Sam will review information we have and determine if there are any action items we can move forward with to improve the experience. Had thought it may roll over into Sprint 39 but with Click tracking Sam was able to idenfity some information about spell check and feels confident he has a baseline understanding which was the goal of this issue.
14955 | [Click Tracking] VA.gov Search Click Tracking API Front End Development |  | Sam | 5 |  |  | Will roll over into Sprint 38 (blocked by platform team)
16367 | [Click Tracking] VA.gov Search Click Tracking API Back End Development |  | Sam | 5 |  |  | Will roll over into Sprint 38 (blocked by platform team)
16738 | [XML Sitemap] Remove url from sitemap XML |  | Sam | 3 |  |  | Rolled over from 37 b/c it required code changes that will wait until post freeze
17697 | [Onsite Search] Create E2E tests for the site-wide search experience |  | Sam | 5
17532 | [Product Dfn] Establish List of top 50 Search Terms |  | Denise |  |  | 3 | Rollover from sprint 37
16658 | [Type Ahead 1.0] Creating a set of canned query suggestions to populate type ahead suggestions |  | Denise |  |  | 3 | Rollover from sprint 37
17560 | [Type Ahead 1.0] Review Design Specs for Type Ahead |  | Megan |  | 2 |  | Megan will review this discussion and look for actionable insights that need to be captured going forward
18036 | [Discovery] Comparative Analysis Research (Part 2) |  | Megan |  | 8 |  | megan to create a ticket
17539 | [Discovery] Finalize conversation guide and research plan (based on input from VAPO review) |  | Megan |  | 3 |  | blocked by 16902 - will roll over to sprint 38
17534 | [Discovery] Search Relevancy analysis/scoring ticket |  | John/Denise |  |  | 5
16902 | [Discovery] Research Plan reviews with POs |  | John |  |  | 5 | Final VAPO Review sessions will happen in January as a result this will roll over into sprint 38
17534 | Audit/Score VA.gov Search Results Relevance |  | John/Denise |  | 8
| Totals |  | 57 | 20 | 21 | 16
| Not Completed |  |  | 10
Support Issues for Reference
16778 | [Analytics] KPI Dashboard Request |  | Analytics | 0 | 0 | 0 | Denise would like to initiate with OKR + KPI info to iniate dashboard request
| Sprint 39 (Jan 13 -26) | Groomed | Focal | Dev | Design | Product | Notes | End of Sprint Status
Sprint Goals | Wrap up click tracking data implementation and resolve outstanding bugs for XML Sitemap and Type Ahead Analytics. Prep for upcoming user research sessions including recruiting veterans and notetakers. Initiate analytics team to begin establishing DOMO dashboard (for Type Ahead and KPIs)
16367 | [Click Tracking] VA.gov Search Click Tracking API Back End Development | Y | Sam | 5 |  |  | Rolled over from Sprint 38. | Closed
14955 | [Click Tracking] VA.gov Search Click Tracking API Front End Development | Y | Sam | 5 |  |  | Rolled over from Sprint 38. | expected to close
18174 | Search analytics tagging fixes | Y | Sam | 3 |  |  |  | expected to close
17142 | [Type Ahead 1.0] BUG Safari - Unexpected tabbing focus | Y | Sam | 1 |  |  |  | Closed
12334 | [Discovery] - Recruit notetakers + schedule debrief sessions | Y | Megan |  | 2 |  |  | expected to close
18481 | Schedule user sessions with Perigean | Y | Megan |  | 2 |  |  | expected to close
18475 | Search.gov Exploration | Y | ALL | 1 | 1 | 1 |  | Denise to update with new email/exploration needs
17783 | [Type Ahead POC] General Type Ahead Usability Improvements | Y | Denise |  |  | 2 |  | Not Completed - Deprioritized. Want to establish a type ahead style guide before determining which of these improvements are relevant for 1.0
18476 | S+D Team DOMO dashboard preparation | Y | Denise |  |  | 5 |  | complete
| Totals Planned for the sprint |  | 28 | 15 | 5 | 8
Support Issues - Tracking for Reference
18785 | Analytics KPI dashboard request for Search & Discovery [Typeahead POC] | n/a | (Analytics) | 0 | 0 | 0 |  | Ongoing but this is just for awareness and not tracked in our sprint reports
Unplanned Issues added to the sprint
18552 | Solidify Style guide for typeahead suggestions | Y | Megan |  | 5 |  |  | expected to close
17868 | [Discovery] Define Search User Journey | no | Denise |  |  | 5 |  | Denise MIRO flow
| Completed Totals for the Sprint |  | #NAME? | #NAME? | #NAME? | #NAME?
| Sprint 40 (Jan 27 - Feb 9). #19480 | Focal | Dev | Design | Product | Notes | End of Sprint Status
Sprint Goals | 1.Conduct User Research Sessions 2. Planning for spelling improvements & Type Ahead 1.0 3. Establish DOMO Dashboard
12332 | [Discovery] Conduct user sessions for VA.gov sitewide search usability study | Megan |  | 8
18734 | [Type Ahead 1.0] Transition from Type Ahead POC to Type Ahead 1.0 | ALL | 3 | 2 | 3
19011 | Search.gov follow up discussions | John/Denise |  |  | 1
19017 | (Product Discovery) Planning Spelling Improvements | ALL | 1 | 1 | 1
19004 | Coordination to establish analytics dashboards | Denise/Sam | 1 |  | 1
| Totals | 22 | 5 | 11 | 6
Support Issues - Tracking for Reference
16778 | [Analytics] KPI Dashboard Request | (Analytics) | 0 | 0 | 0
18785 | Analytics KPI dashboard request for Search & Discovery [Typeahead POC] | (Analytics) | 0 | 0 | 0
Unplanned Issues added to the sprint
17783 | General Type Ahead Usability Improvements | All
19373 | Exploration + Collect VA Acronym Information | Sam
19017 | (Product Discovery) Spelling Suggestions Improvement | All

## Roadmap (hidden)
Search & Discovery Roadmap | [6 empty] | Established: Using Unauthenticated Roadmap
RELEASE | Status | Target Launch | Actual Launch | Current Sprint Sprint 49 (June 2-15) | "Up Next" | Product | Details
Typeahead POC | Closed |  |  |  |  | Typeahead
Baseline User Research | Closed | February | January 27 - February 8, 2021 |  |  | Onsite Search
Search.gov Production Endpoint | Closed | May | 2021-05-03 |  |  | Onsite Search
Click Tracking | Closed | January | 2021-01-27 |  |  | Onsite Search | Establish click tracking for va.gov
Click Tracking for Best Bets | Closed | May | 2021-05-05 |  |  | Onsite Search | Establish click tracking on best bet content
Typeahead POC2 | Closed | April 12-25 | April 12 - May 16 |  |  | Typeahead | Due to search.gov bug fix we pivoted from POC to establish suggestions list to be hardcoded. Folllowed by POC2 run for 2 weeks to 35% of VA.gov users
Typeahead 1.0 | Wrap Up | 2021-05-18 | Phase Rollout May 17 - 50% May 18 - 65% May 19 - 80% May 20 - 100% | - Monthly Suggestions Report #25483 Sam | - Remove "old search experience w feature flag" 24296 Sam - Visual Loading Indicator #24875 Megan -Collab Cycle Post-Launch Check-In | Typeahead | Styling enhancements and launch to 100% of users
Medallia Survey | BLOCKED | June/July |  | -Follow Up: (survey will take 2-3 weeks once Medallia starts the process. Start date: TBD) |  |  | Dependent on Medallia team to implement
SEO - OffSite Search Enhancements | Defining | ONGOING |  |  | - Google Search Console Exploration #21795 Sam - Exploration Metalsmith Plugin TBD Sam | OFFsite Search | Reviewing reports from SEM Rush and Google Search Console to identify improvments and SEO optimization strategies. Enhance veteran's ability to find VA content by leverage capabilities to enhance experience from search engines (eg. Google rich results, answer boxes, etc.)
Best Bets/Top Recommendation | Current Focus | ONGOING |  | -Collect VAMC & Vet Center Info #25532 Denise -Audit Best Bets + Define Initiatl Strategy #24328 Denise |  | Onsite Search | Establishing best bet strategy. Do not anticipate development or design effort
Search UI Consistency - Global | Current Focus | June |  | -UI Consistency -Part 2 #24988 Sam |  | Onsite Search | * Being informed by UI Search Consistency discussions
Search Reorganziation + Improvements | Current Focus | June |  | - Error Logging #24968 Sam -Modernization/Tech Debt #24118 Sam |  | Onsite Search
Spelling Enhancements | Current Focus | June |  | -"We think you meant" FE implementation |  | Onsite Search | Accomodating common spelling errors. For example: "We think you meant"
Surfacing VA Search Tools | BLOCKED | August |  | -Depo Design Review #22500 Megan |  | Onsite Search
Analytics + KPI Dashboards | BLOCKED | July |  |  |  | Onsite Search & Typeahead | Establish DOMO dashboards for Typeahead and Onsite Search * BLOCKED 3/29: Platform/Analytics pausing Domo Dashboard creation (see note) as a result, this will be picked back up in Q3 As a result we are blocked.
Search Landing Page | Defining | July |  | - PO Review of Initiative Brief #25547 John - Design Exploration #24300 Megan | - Design exploration (w Mockups) 24300 Megan | Onsite Search | va.gov/search
Search Input | Defining | August |  | -Establish Initiative Brief #25562 Denise |  | Onsite Search | Relocating and standardizing the search bar will offer a consistant experience and make it easier for veterans to leverage search when looking for information
Search Results Relevancy | Defining | August |  | -Remove stop Words #24892 Denise |  | Onsite Search | Improving the relevancy of organic search results
Faceted/Consolidated Search | Defining | October |  |  |  | Onsite Search | "Refining Search Results" -separating the different types of content, allowing Veterans to find relevant results more quickly -- making the Search experience more helpful and effective.
Related Content | Defining | November |  |  |  | Onsite Search | Presented users with sesarch results which are related to the query that they conducted
Personalizing Search | Defining | December |  |  |  | Onsite Search | Personalization of experience based on known "unauthenticated" information. (e.g. geographical location)
XML Sitemap | Defining | TBD |  |  |  | Onsite Search
Acronym Clarity | On Hold | TBD |  |  |  | Onsite Search | Dfn: Enhancing clarity for common VA acronyms *Data Exploration + User Research
Answer Engine/Symantic Search | Defining | TBD |  |  |  | Onsite Search | Enable users to ask full sentences versus keyword search.
Typeahead 2.0 | Defining | TBD |  |  |  | Onsite Search | Using user data to expand the list of typeahead suggestions to improve their usefulness
Veteran Recommendations | Defining | TBD |  |  |  | Onsite Search | Veterans share/learning from veteran feedback on content as it relates to their query.

## Planning
S+D Team uses this to tentatively plan out upcoming sprint. GH ticket numbers added when available; n/a if a reminder only |  | Team Capacity: | [20 empty] | Sam PTO July 29 Sam PTO half days Aug 2 - 6 | Denise PTO Aug 16 - 24 Megan PTO Aug 23 - 25 Cindy PTO Aug 16-24 | Denise PTO Aug 25 -27 Sept 6 - Federal Holiday - Labor Day Sept 7 - Rosh Hashana (Cindy PTO) Megan PTO Sept 7 + 8
STATUS | Epic # | Initiative | Product | Description + Details | Collab Cycle Required? | Target Launch | Actual Launch | S39 (1/13-1/26) | S40 (1/27-2/9) | S41 (2/10-2/23) | S42 (2/24-3/9) | S43 (3/10-3/23) | S44 (Mar 24 - Apr 6) | S45 (Apr 7 - 20) | S46 (Apr 21- May 4) | S47 (May 5-18) | S48 (May 19-Jun 1) | S49 | S50 | S51 | S52 | OLD "Up Next" ( need to update S50, 51 and 52) | S53 July 28 - Aug 10 | S54 Aug 11 - 24 | S55 Aug 25 - Sept 7 | S56 Sept 8 - 21 | S57 Sept 8 - 21 | S56 Sept 8 - 21 | "Up Next"
Current Focus | #26815 | Usability Research |  |  |  | September | [16 empty] | * Review Hi Fi Designs n/a Megan * Midpoint Review #27754 * Design Updates after midpoint review #27994 Megan * Start UXPin Prototype (x6) #26814 Megan | * Complete UXPin Prototype #28421 Megan | * Create conversation guide #26425 Cindy * QA prototype #28317 All * Refine prototype n/a Megan * Update Research Plan n/a (Cindy/Denise) * Request participants from Perigean (~Aug 30) TBD Cindy | * Conduct Usability Sessions #28598 Cindy * Observe User Research Session TBD Megan * Data Synthesis & Reporting Usability Sessions (~1 week) TBD Cindy * Research Pilot Tests TBD Cindy |  |  | *Determine links on 'more search tools' card (eg. Employment) TBD * Modify Designs based on user feedback TBD Megan
Current Focus | #27325 | Typeahead 2.0 (Drop Down Component) | Typeahead |  | Yes | September | [16 empty] | * Create Initiative Brief #? Denise * Review Initiative Brief n/a John * Collab Cycle Kickoff n/a Denise * Design Intent n/a Denise | * Build out drop down component PART 1 #28320 Sam | * Build out drop down component PART 2 #29144 Sam | * Add analytic event logging to component #28321 Sam |  |  | * Verify component meets 508 standards #28322 Sam Installation Phase: * Add to search result page TBD Sam * Add to search landing page TBD Sam * Add drop down component to legacy search header TBD Sam * Design Refinement (width of input field/other in production fixes) 28324 Megan
Current Focus | #27981 | VA Video Results | Onsite Search |  | Yes | September | [16 empty] | * Create Initiative Brief #28036 Denise * Results Research # 27999 Megan * Analytics Review #27991 Denise *Send Search.gov Video Bugs n/a Denise/Megan | Explore Search.gov video behavior and access to API for VA #28519 | * Synthesize Findings + prepare for PO debrief #28631 All * Collab Cycle Kickoff n/a Denise * Comparative Analysis #TBD Megan * Video API Exploration TBD Sam | * Design Exploration #27982 Megan |  |  | *BE implementation for VA Video Results #28453 (make 2 tickets over 2 sprints) *FE Video Implementation w/ feature flag ticket #28456 * S+D Team Review of Video Implementation #28458 *
Current Focus | 22132 | Analytics + Audits | Onsite Search | Establish DOMO dashboards for Typeahead and Onsite Search * BLOCKED 3/29: Platform/Analytics pausing Domo Dashboard creation (see note) as a result, this will be picked back up in Q3 As a result we are blocked. | No | July | [5 empty] | On Hold- Awaiting Analytics implementation | On Hold- Awaiting Analytics implementation of Onsite Search Dashboard, Bounce + Refinement Rate Enhancement on Typeahead | Acquire GA Reports to focus on Global Search #22501 Denise | Acquire GA Reports to focus on Global Search #22501 Denise | - Establish Inventory of Search Tagging 24292 Sam - Conduct an audit of Click Tracking Data 24294 Denise -Investigate Top Queries with Low Click Thrus 24299 Denise | - Follow up GA Custom Dimension #24482 Brian - Analytics ✅ - Establish GA custom report search-typeahead-used variable #24267 Sam | Document Search Design Pattern for Design System #24597 |  |  |  | 6/29- Anticipate Onsite Search Domo Dashboard in July | * SD Team Review of Domo Dashboard n/a All * Meet with Analytics Team to discuss questions n/a All * Medallia Feedback Summary Review n/a Denise | n/a | * Review Domo documentation n/a Denise |  |  |  | *
Temporary |  | Caregiver Team Assistance | [22 empty] | * Update healthcare wording #29093 Sam
Ongoing | 24331 | Best Bets/Top Recommendations | Onsite Search | Establishing best bet strategy. Do not anticipate development or design effort | No | Ongoing | [9 empty] | - Create Best Bet Template for new requests #24321 Denise | - Conduct Best Bet Audit + Define Initial Strategy #24328 Denise | -Collect VAMC & Vet Center Info #25532 Denise -Audit Best Bets + Define Strategy #24328 Denise -Best Bet Request for COVID-19 CLP #25969 John |  |  |  | -Establish VAMC & Vet Center Best Bets | n/a | n/a | n/a | * Follow up VAMC + Vet Center Best Bets ???
Ongoing | 16128 | SEO -Offsite Enhancements | OFFsite Search | Reviewing reports from SEM Rush and Google Search Console to identify improvments and SEO optimization strategies. Enhance veteran's ability to find VA content by leverage capabilities to enhance experience from search engines (eg. Google rich results, answer boxes, etc.) | No | Ongoing |  |  | n/a | Stretch Goal | Knowledge transfer from PW Delayed | Knowledge transfer from PW (3/18 meeting) (#20170 Sam + Denise) | - Discovery - John Definition/Clarity - especially red issues - SEM Rush Exploration (21807 Denise + John) - (From PW) VA.gov Site Map XML & Template Structured Data Issues (#20170 John) > this was broken into two new issues- 22442 & TBD - Google Search Console Exploration (#21795 Sam) ↩️ Deprioritized+ moved back to Ready | - Structured Metadata Exploration #22442 Sam | - Structured Metadata Exploration #22442 Sam - Legacy sites search switch-over #23322 John - Create Best Bet for Veteran Rapid Retraining Assistance Program (#23533 John) | - Enable Socks to access review instances 24290 Denise - Exploration of Site Indexing 21536 All |  | n/a |  |  |  | - Google Search Console Exploration #21795 Sam - Exploration Metalsmith Plugin TBD Sam | n/a | n/a | n/a |  |  |  | * Google Search Console Exploration ?? Sam * Exploration Metalsmith Plugin TBD Sam
Ongoing | 16752 | XML Sitemap | Onsite Search |  |  | TBD | [16 empty] | n/a | n/a | n/a
Ongoing | 25560 | Search.govEnhancements & Comms |  |  | No | Ongoing | n/a | [8 empty] | Communication Log - Current Topics: - Health Endpoint - Typeahead Endpoint Rate Limits | Current Topics: - boosting relevance of R+S - prioritizing feature list - Low CTR terms ex. 'health topics' | - updated best bet spreadsheet (any way to run that report ourselves, could we extend the spreadsheet to include other fields suchs as categories?) -is there a way to filter click tracking data by a data range? |  |  |  | -follow up on implementation of Stop Words. Last update 7/11 - they are validating | * Define agenda *Search.gov is evaluating removal of StopWords * Discuss Click Tracking Error | n/a
Ongoing |  | Search Results Relevancy | Onsite Search | Improving the relevancy of organic search results |  | August | [11 empty] | -Remove stop Words #24892 Denise |  |  |  |  | *Met with Search.gov | n/a | *Identify list of relevancy errors to send to search.gov TBD Denise/Megan
Ongoing | n/a | Miscellaneous Team Tasks *Catch All - Tech Debt, Bug Fixes, Etc. |  |  | No | [11 empty] | - Socks access for Megan 25012 | - Core Tunnel for Denise + Megan |  |  |  | [Product Discovery] COVID-19 Vaccine Finder - VA Data Distribution #19009 | * Remove temporary fix for double bars #27978 Sam * Resolve Click Tracking Error #28000 Sam * Investigate obfuscating secret key using fwdproxy / HAProxy #28024 (Sam to Track) * Continue resolving Microsoft transition tasks as needed | * Investigate obfuscating secret key using fwdproxy / HAProxy #28024 (Sam to Track) | * Investigate obfuscating secret key using fwdproxy / HAProxy #28024 (Sam to Track)
POTENTIAL FUTURE
On Hold | 24333 | Search Landing Page (404) | Onsite Search |  | Yes | July | [9 empty] | - Comparative Analysis #24303 Megan | - Update Initiative Brief for Search Landing Page #25003 Denise | - PO Review of Initiative Brief #25547 John - Design Exploration #24300 Megan |  |  |  | - Design exploration (w Mockups) 24300 Megan
On Hold | 20402 | Surfacing Search Tools | Onsite Search | Modernizing the design of the search results page -- reducing clutter and improving wayfinding -- will enable users to more effectively scan, comprehend and select relevant links -- and reduce bounce. | Yes | August |  |  | n/a | n/a | Define | Design Exploration (#21376 Megan) | - Cont'd Design Exploration (#21376 Megan)✅ - Veteran Touchpoint Review Summary (#18512 All)✅ - Explore/Audit Metadata Descriptions (#21386 Megan- unplanned)✅ | - Product Outline #21382 Megan - Exploration/Audit of Metadata Descriptions #21386 Megan | - Cont'd Product Outline discussions #21382 Megan - 8 | On Hold - Awaiting User Feedback Readout from Cindy (estimated 5/17) - Exploration - Other VA Search Tools 20217 Megan/Denise | - Update Product outline #24297 Megan/Denise (MON - Product Outline: SD Team Finalization. N/A (WED) | -Depo Design Review #22500 Megan - Describe "Search Start Page" with modified screenshots #26011 Megan |  |  |  | - ? Create Wireframes #22932 Megan - ? Final Design #22498 Megan - ? Create InVision Prototype #22764 Megan
Defining | 18060 | Search Input | Onsite Search | Relocating and standardizing the search bar will offer a consistant experience and make it easier for veterans to leverage search when looking for information |  | August | [11 empty] | -Establish Initiative Brief #25562 Denise
Defining |  | Typeahead 1.1 | Typeahead | Using user data to expand the list of typeahead suggestions to improve their usefulness |  | TBD
Defining |  | Related Content |  |  |  | November
Defining | 22092 | Faceted/Consolidated Search | Onsite Search | Providing users with a way to refine search results in an attempt to narrow down the results to find relevant results more quickly. |  | October
Defining |  | Personalizing Search | Onsite Search | Personalization of experience based on known "unauthenticated" information. (e.g. geographical location) |  | December
On Hold | 19371 | Acronym Clarity | Onsite Search | Enhancing clarity for common VA acronyms |  | TBD |  |  | n/a | n/a | Define/Exploration | On Hold | Data Analysis (#22128 Denise)✅ Connect with Cindy to add to existing research plans (4/1 Meeting)✅ | - - - |  | n/a | - n/a
Defining |  | Answer Engine/Symantic Search | Onsite Search | Enable users to ask full sentences versus keyword search. |  | TBD
Defining |  | Veteran Recommendations | Onsite Search | Veterans share/learning from veteran feedback on content as it relates to their query. |  | TBD
CLOSED
Closed | 16104 | Team Onboarding | n/a | Establish dedicated team to focus on search and discovery aspects of VA.gov |  | Q1 Mid December |  | closed
Closed | 16906 | Product Definition | Onsite Search | Define the problem space and potential initiatives for team to focus on |  | End of January |  | closed
Closed | 11638 | UX Discovery | Onsite Search | Baseline User Research. By conducting Veteran desktop and mobile user testing (with a representative sampling of veterans), we will better understand the problem space and identify solutions for improving the experience. |  | Mid- Late February | Jan 27-Feb 8,2021 | n/a | Conduct Research Sessions | User Research Synthesize + Readout | Integrate Next steps into roadmap, DEPO PO Readout | Closed
Closed | 8896 | Type Ahead POC | Typeahead | POC experience for 5% of all users - 4 weeks [Dec 23, 2020 - Jan 31, 2021]. By implementing type-ahead (suggested terms), Veterans will get more relevant results more quickly -- making the Search experience more helpful and effective. |  | End of January |  | n/a | Collecting Data/ Establish Dashboard | Explore Dashboard Data/ Address analytics defects | Planned to Refine Dashboard + Summarize Data and draw conclusions but after serach.gov purge of the typeahead suggestion database. Decision to implement POC2 after constructing list to hardcode on suggestion list and re-run the data | Closed
Closed |  | Search.gov Production Endpoint | Onsite Search |  |  | May | 2021-05-03
Closed |  | Click Tracking for Best Bets | Onsite Search | Establish click tracking on best bet content |  | May | 2021-05-05
Closed | 21316 | Typeahead POC 2 | Onsite Search | Due to search.gov bug fix we pivoted from POC to establish suggestions list to be hardcoded. Folllowed by POC2 run for 2 weeks to 35% of VA.gov users |  | April 12-25 | April 12 - May 16 |  | n/a | n/a | n/a | Define strategy & create list of terms to suggestion database. (#21325: Megan + Denise) Analytics Fixes (#21648 Sam) Stretch: Begin Validating terms with results | - Validate Suggestion List (#21325 All) ✅ - Send suggestion list to search.gov (n/a Denise)✅ - Test suggestionlist on Staging implementation (#17844 Denise unplanned)✅ - Establish BE requirements to connect to Search.gov Suggestion API (#21794 Sam)✅ - Analytics Fixes (#21648 Sam) ✅ - Meet w Search.gov Logic Levers:Threshold+Deprecate (4/5 Meeting) | Add terms that needed best bets #22540- John Run POC2 April 12 - 25 - 35% of all users #22497 | - Run POC2 April 12 - 25 - 35% of all users (#22497 Sam) - Validate typeahead data (#23870 Sam) - FE - Search.gov Production API (21793 Sam - 2) | -Support Typeahead rollout changes 24801 Sam | - Review POC2 data + summarize findings #22091- Denise/John✅
Closed | 21535 | Medallia | Onsite Search | Implementation of Medallia feedback form in Search we will be able track and improve customer satisfaction for the search experience. Dependent on Medallia team to implement | No | June/July | 2021-06-14 |  |  |  |  | On Hold- Awaiting Medallia implementation | On Hold- Awaiting Medallia implementation (Potentially coming soon "early Q2") | On Hold- Awaiting Medallia implementation (Potentially coming soon "early Q2") | n/a | - Follow up on Feedback Survey 21535 1) Did you find what you were looking for today? [‘yes’ or ‘no’] 2) What were you unable to find during your visit today? [text area] 3) What is your overall satisfaction with this site? [‘Very Dissatisfied’ through ’Very Satisfied”] | (survey will take 2-3 weeks once Medallia starts the process. Start date: TBD) | -Follow Up: (survey will take 2-3 weeks once Medallia starts the process. Start date: TBD)
CLOSED | 16444 | Click Tracking | Onsite Search | Establish inital version of click tracking on search.gov. By enabling Search.gov click tracking we will be able to conduct improved “closed loop analysis” of VA.gov search effectiveness. |  | Late January | 2021-01-27 | n/a | closed |  |  | (Stretch) Explore Best Bet Implementation (#21514 Sam) | - Explore Best Bet Implementation (#21514 Sam)✅ | - Add Click Tracking to Best Bet - Implementation- BE #22131 Sam | - Add Click Tracking to Best Bet - Implementation- FE #22949 Sam | No further work > collecting data, then will review. | - Define Strategy & Identify next steps TBD Denise |  |  | Remove IP Address from Click Tracking #26561 | Close out | N/A
Q2 Focus | 17558 | Typeahead 1.0 | Onsite Search | Styling enhancements and launch to 100% of users | Yes | 2021-05-18 | Phase Rollout May 17 - 50% May 18 - 65% May 19 - 80% May 20 - 100% |  | Define | Develop Enhancements | Resolve bugs, Search.gov bug fix purged suggestion database and altered plan to launch | On Hold - awaiting POC2 completion | On Hold - awaiting POC2 completion |  | n/a | - Collab Cycle Staging Review Follow Up # 20532 Denise - Change Font Color #24789 Sam - Phased rollout of typeahead 1.0 #24839 Sam | - Launch TA to 100% users <May 10-17th> #19368 Sam✅ - Clear suggestions if query is ever below the threshold #24837 Sam - Monitor Fetch Data #25066 - Define 'seeding' strategy for typeahead #24295 Denise - Respond to Staging Review Feedback - [Summary on #17558] | - Monthly Suggestions Report #25483 Sam -Establish Test Rail Account #25487 Denise | - Establish Automated testing for Typeahead #25364 Sam | n/a | Request CC Full accessibility + 508 office audit 27062 Denise | Explore ways to reduce Typeahead suggestions lag #26721 Sam CC Post-Launch Check-In N/A Denise Remove "old search experience w feature flag" 24296 Sam Visual Loading Indicator #24875 Megan (TBD)
launched | 21055 | UI Search Consistency | Onsite Search |  | n/a | [6 empty] | VA.gov Search Consistency - Compile possible fields (#21438 Megan) Meeting with Cassandra to discuss UI Consistency | - Global Search Consistency (#21977 Megan ) ✅ | - Search UI Consistency: Global Search #21977 Megan - Follow Collab Cycle Process - Lead by Marci | - Follow Collab Cycle Process - Lead by Marci (n/a) | - Final Design iterations -Mockup gray box #24270 Megan - Global Search - Design Intent Feedback Summary #23650 Megan - Support for comment #459 "Add New Search Pattern to design system" #24492 Megan | - Project Kickoff TBD Denise - Begin Development on UI Consistency #24972 Sam | n/a
On Hold |  | Search UI Consistency - Global | Onsite Search | * Being informed by UI Search Consistency discussions | Yes | 2021-07-06 | 2021-07-07 | [10 empty] | -UI Consistency -Part 2 #24988 Sam |  |  |  | - Finalize Development for UI Consistency - Part 2 #24988 Sam
Done | 22977 | Search Reorganization and Improvements | Onsite Search |  | No | 2021-07-06 | 2021-07-07 | [6 empty] | - Dev Exploration to optimize/rebuild search #22499 Sam | - Search Reorganization Strategy Discussion (#23503 Sam) | On Hold - Will be done with "surfacing search tools work" | - Error Logging Improvements #24968 Sam - Establish list of Stop Words #24994 Megan -Updated Design for Spell Check #25443 Megan | - Error Logging #24968 Sam -Modernization/Tech Debt #24118 Sam |  |  |  | - Remove Stop Words #24892 - Analytics #24116 Sam - Modernization/Tech Debt #24118 Sam
Done | 19190 | Spelling Enhancements | Onsite Search | Accomodating common spelling errors. For example: "We think you meant" | No | June |  | n/a | n/a | Define/Exploration | Due to Search.gov current limitations initial implementation will be to icebox; define new version to be added to results page redesign, Closed | Closed | [5 empty] | -"We think you meant" FE implementation
Note on N9: I've going to break this ticket into two -- one focused on the non-canonical URLs "issue" and the other on structured markup since they are two very different potential problems. For non-canonical URLs report -- I've done some probing and here is what I've come up with: #22242

## Process
| Functional Areas | Type-Ahead POC | Typeahead 1.0 | Click Tracking | Search UI Consistency Global Pages | Surfacing Search Tools | Typeahead 2.0 | VA Video Results | Search Landing Page
PRODUCT DISCOVERY + DEFINITION
Create Initiative Brief | PM | n/a | ✅ using product outline |  | ✅ using UI Consistency product outline | ✅ |  |  | ✅
PO Review/ Approvals as Needed | PO | n/a | ✅ |  | n/a | ✅ |  |  | ✅
Discovery research: comparative analysis, quantitative, qualitative data | Design | n/a | ✅ |  | ✅ | ✅ |  |  | ✅
Discovery research: quantitative, qualitative data collection | PM
DESIGN EXPLORATION
Design Exploration: initial exploration | Design | ✅ | ✅ |  | ✅ | ✅
Usability Testing Prep (if needed) | Research
Create Wireframes: Whiteboard sketch or other lo-fi prototypes or wireframes | Design | ✅ |  |  | n/a
SD Team Review Designs | SD Team | ❌ | ✅ |  | n/a
Review Wireframes with VSP Design during Office Hours (if usability testing is required) | Design
Design Refinements (if needed after team review) | Design | ❌ | ❌ |  | n/a
INITIATE COLLAB CYCLE
Request Project Kickoff (GH Issue) | PM | ✅ | ✅ |  | ✅
Collaboration Cycle Kickoff | Collab Cycle | ✅ | ✅ #20512 | ❌ | ✅ #25596 | #27753 | #28505
Create Research Plan (if needed) | Research | ❌ | ❌ |  | n/a
Add imput to research plan as needed | Design
Create Content Brief (if needed) | PM | ❌ | ❌ |  | n/a
Schedule Design Intent Review | PM | ❌ | ✅ |  | n/a
Design Intent (if needed) | Collab Cycle | ❌ | ❌ | ❌ | ✅ | #27754 | ❌
FINALIZE
Finalize Designs (High Fidelity) | Design |  | ✅ |  | n/a
Midpoint Review (if needed) | Collab Cycle | ❌ | ❌ | ❌ | ❌ | Required | #31219
Usability Testing Prep (if needed) | Collab Cycle | ❌ | ❌ | ❌ | ❌ |  | ❌
Create Release Plan (if needed) | PM |  | ✅
IA Request (if needed) | Collab Cycle | ❌ | ❌ | ❌ | ❌ | Required | ❌
Analytics request | Collab Cycle | ✅ | ✅ | ❌ | ❌ | Required | 31870
Contact Center Review (if needed) | Collab Cycle | ❌ | ❌ | ❌ | ❌ | Required | Required
BUILD
Development including Peer Code Reviews | Dev | ✅ | ✅ | ✅
Create Test Plan - unit and baseline accessibility tests. | Dev |  |  | ✅ | ❌
Internal Staging Review | SD Team | ❌ | ✅ | ✅
PRE-STAGING REVIEW ACTIVITIES
Research plan review (if needed) | Collab Cycle | ❌ | ❌ | ❌ | ❌ | Required | ❌
Create Product Guide | PM |  | ❌ | n/a
Run Foundational A11y tests (info) | Dev |  |  | n/a
100% ready 4 days before launch | FYI | ✅ | ✅ | ✅
LAUNCH
Request Staging Review | PM | ✅ | ✅ | ❌
Staging Review | Collab Cycle | ✅ | ✅ #20532 | ❌ | ✅ #26080 | Required | 31868
Resolve Staging Review Findings | PM |  | ✅ | ✅
Privacy + Security Review | Collab Cycle | ✅ | ✅ | ✅ #293 | ✅ #302 | Required | 341
Target Launch Date | PM | 2020-09-01 | 2021-05-20
VALIDATE
Full accessibility + 508 office audit | Collab Cycle | ✅ | ✅ #27591 | ❌ | ✅ #27624 | Required | Required
Post-launch Check-in | Collab Cycle | ❌ |  | ❌ | ✅ | Required | Required
Impact Review | PM | ❌

## OKRs
North Star | Make it easier for veterans to find the information they need and the tasks they want to complete on VA.gov To be the best search experience on a federal website.
Objectives & Key Results (OKRs) |  |  |  | Initiatives
Quarterly Target | Objective (OKR) | Key Results (Minimum of 2 goals) | Reflection Date | Initiative (Bet) | Iterations | Target Completion for Initiative (ie. Mid-February) | Actual Initiative Launch/Completion Date
Approximate Timing | What are we trying to do? | When we get there, what are we hoping for? | When we will review the status toward our objective (score yes/no) | Actions we want to make to help reach our destination. (Features, Iterations, etc.) | Approach to break down initiative when required into smaller manageable releases so we can continue to iterate and provide value sooner. | Approximate timing we are striving for | When initiative becomes user facing
Product - On Site Search
Q1 2021 | Objective 1: Collect a better understand of how effective VA.gov is at delivering relevant results -- and answering Veterans questions. | Key Result #1: Establish baseline effectiveness of Search.gov and results relevance as they relate to specific queries. Key Result #2: Collect data to establish baseline and build our understand of how VA.gov users are navigating the search experience today. Key Result #3: Collect user insights through user research and usage data. | TBD | Establishing Click Tracking By enabling Search.gov click tracking we will be able to conduct improved “closed loop analysis” of VA.gov search effectiveness. | None, singular implementation | Late January 2021 | 2021-01-25
|  |  |  | Examining Result Relevance By scoring VA.gov Top Five Results for most popular search terms (relevant, near relevant, misplaced, irrelevant), we will be able to baseline and track performance of search results relevance. | None | Now (MVP) - early jan - initial assessment Next - revisit Best - TBD | TBD
|  |  |  | Conducing User Research to build baseline understanding By conducting Veteran desktop and mobile user testing (with a representative sampling of veterans), we will better understand the problem space and identify solutions for improving the experience. | None - Initial discovery sessions done in one session. Future research conducted as needed. | End - February 2021 | TBD
|  |  |  | Customer Satisfaction By implementing a Medallia feedback form in Search we will be able track and improve customer satisfaction for the search experience. | None, singular implementation | TBD | TBD
| Objective 2: |  |  | Spelling Improvements Leverage Search.gov spelling suggestion feature allowing experience to be more tolerant of spelling errors. | MVP - | Now (MVP) - TBD Next - TBD Best - TBD | TBD
|  |  |  | Search.gov Improvements Search.gov needs to pick up metadata that already exists on VA.gov pages. Currently they are not the full description of the page. | TBD | TBD | TBD
End of Q1 Goal - Typeahead is available to 100% of users. Understanding problem space. (Stretch Goal: Spelling Improvements)
Q2 2021 | Objective 2: Reduce user frustraction by creating a better search experience implementing “table stakes” features | Key Result #1: 5-10% reduction in search refinement rate Key Result #2: Increase the use of onsite search by 5% Key Result #3: Reduction in search abandonment rates Key Result #4: increase in user satisfaction | TBD | Type-Ahead By implementing type-ahead (suggested terms), Veterans will get more relevant results more quickly -- making the Search experience more helpful and effective. | (MVP) - Type Ahead POC POC2- Type Ahead 1.0 - General UI improvements Best - Type Ahead 2.0 - Increase the usefulness of those suggestions | Now(POC) - Dec 23 - Jan 26 Next - Early March Best - Mid April | TBD
End of Q2 Goal -
Q3 2021 | Objective 3: Improve Results page performance | Key Result #1: Increase in % of queries where users click on result Key Result #2: Increase in % of users that use search Key Result #3: TBD
End of Q3 Goal -
Q4 2021 | Objective 4: Enhance VA.gov visitor confidence and trust in VA.gov's ability to surface relevant resources in a timely manner. | Key Result #1: Increase in % of queries where users click on result Key Result #2: Increase in % of users that use search Key Result #3: TBD
End of Q4 Goal -
Product - Off Site Search
TBD | Objective Optimize veteran search experience from search engines to VA.gov content | Key Result #1: Increase in traffic from google Key Result #2: Increase in overall CTR
TBD | Objective: Improve the overall health of the search experience on VA.gov | Key Result #1 Decrease the number of broken links from va.gov

## KPIs
| KPI Category Value, Trust or Health | Metric | Metric Description | Significance 1 High, 2 Medium or 3 Low | Narrative What does the audience need to know? |  | Dashboard Display Preference | Data Source /Dashboard | 2020-Q3 Reporting |  |  | 2020-Q4 Reporting |  |  | 2020 YEAR END TOTALS | 2021 Q1 Reporting |  |  | 2021 Q2 Reporting |  |  | 2021 Q3 Reporting |  |  | 2021 Q4 Reporting
| Value e.g. Findability, Ease of use, Service Completion, Conversion Trust e.g. Customer Satisfaction, Contact Center Health e.g. Uptime, Error Rates | Data we are tracking to monitor our progress | Clarification description | Importance indicator for Team | What does data tell us? | If applicable- What doesn't data tell us? - Considerations when looking at the data | Idea display for data -wireframes- |  | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-02 | 2020-11-01 | 2020-12-02 |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-02
POC 1 Dec 23 - Jan 31
| PRODUCT: Typeahead Dashboard Link: | [6 empty] | GH #18785
| Value | Overall Volume | Number of users for which type ahead feature flag was enabled (regardless of whether it was used or not) | 2 | How many users who were presented with typeahead suggestions |  | # of users broken out by month | typeahead dashboard | n/a | n/a | n/a | n/a | n/a | Report Link POC1 - December 23, 2020- Jan 31, 2021) |  | 2021-01-01: n/a; 2021-02-01: n/a; 2021-03-01: n/a
| Value | Type Ahead Searches by Page | Indicates from which page(s) type ahead searches have occurred/presented (regardless of whether they were chosen or not) | 3 | Tells us which page users are leveraging the typeahead feature the most |  | Total # of searches by page by month | typeahead dashboard | n/a | n/a | n/a | n/a | n/a | Report Link (select All VA.gov Website Data [Production]) |  | 2021-01-01: n/a; 2021-02-01: n/a; 2021-03-01: n/a
| Value | Type Ahead Usage | A breakdown report of Type Ahead "Options" (suggestion 1 - 5) and "not set" (indicating a user ignored the type ahead options they were presented and proceeded to search organically (i.e. without selecting a suggestion). | 1 | Explains how users are interacting with the suggestions that are being presented. |  | breakdown (% ignored + % engaged - indicated by suggestion #) | typeahead dashboard | n/a | n/a | n/a | n/a | n/a | Report Link |  | 2021-01-01: n/a; 2021-02-01: n/a; 2021-03-01: n/a
| Value | Top Type Ahead Terms | An overall glimpse of the top keywords that were chosen from type ahead options | 1 | A list of most used suggestion terms |  | list of keywords with corresponding # of times chosen by | typeahead dashboard | n/a | n/a | n/a | n/a | n/a | Report Link |  | 2021-01-01: n/a; 2021-02-01: n/a; 2021-03-01: n/a
| Value | Comparing Conversion Rates with and without typeahead | Comparing the two data points that highlight the amount to time it took to get from (search query) to (click on result) one with typeahead and one without. | 1 | Outlines the difference between conversion rate for users with typeahead versus users without typeahead |  | two line charts showing percentage of successful users over time (one with typeahead and one without typeahead) | typeahead dashboard | n/a | n/a | n/a | n/a | n/a | n/a |  | 2021-01-01: n/a; 2021-02-01: n/a; 2021-03-01: n/a
| Value | Conversion Rate for type ahead users | # of people who selected a typeahead suggestion and then selected one of the results from the results page | 1 | Conversion Rate for users with typeahead enabled |  | line chart showing percentage of users over time | typeahead dashboard | n/a | n/a | n/a | n/a | n/a | n/a |  | 2021-01-01: n/a; 2021-02-01: n/a; 2021-03-01: n/a
PRODUCT: Onsite Search Dashboard Link: TBD - estimated Q3 | [7 empty] | MVP Dashboard #16778
KPI | Value | Total Queries | # of searches conducted | 1 | Captures difference in overall query numbers over time. | Does it correlate to increase of visitors? | Total queries associated with adjustable date range line chart | search.gov | 472461 | 490745 | 488737 | 495388 | 468448 | 485718 |  | 2021-01-01: 862163; 2021-02-01: 585572; 2021-03-01: 674869
KPI | Health | Search Exits (Bounce Rate) | % of queries that lead users to exit the site without selecting a result. (We can separate global search and mini searches so we need to define what) | 1 | Percentage of searches overall where a user leaves the search results page without clicking on a link | Users may have exited because they found what they are looking for on the search results pages | % of queries that lead users to exit the site with adjustable date range line chart | Google Analytics | 24.57% | 24.1% | 23.78% | 23.18% | 22.63% | 21.75% |  | 2021-01-01: 19.68%; 2021-02-01: 18.56%
KPI | Value | Refinement Rate | % searches with query refinement | 1 | Percentage of searches overall where a user rephrases their search term | Cause of refinement rate, is it just the nature of an information-heavy site? What is the refinement rate of similar sites? What are the search terms with the highest refinement rates? | % searches with query refinement with adjustable date range line chart | Google Analytics | 30.4% | 29.98% | 29.65% | 30.15% | 29.33% | 29.16% |  | 2021-01-01: 28.94%; 2021-02-01: 28.39%
KPI | Trust | Conversion Rate for search users | % of users who conducted a query and were able to proceed to a VA page after selecting from the results page | 1 | How many users were successful in moving from "point A" (conducing a search) to "Point B".. (clicking on one of the search results page). | None so far | # of users who conducted a query and were able to proceed to a VA page after selecting from the results page with adjustable date range line chart | Google Analytics | n/a | n/a | n/a | n/a | n/a | n/a |  | 2021-01-01: n/a; 2021-02-01: 43.37
KPI | Value | Average Search Depth | The number of pages visitors viewed after getting results for the search term. | 1 | Measures health of search result relevancy. More pages viewed means users need to look harder to find what they were looking for. | None so far | # of pages visitors viewed after getting results for the search term with adjustable date range line chart | Google Analytics | 3.11 | 3.22 | 3.19 | 3.28 | 3.29 | 3.41 |  | 2021-01-01: 3.64; 2021-02-01: 3.67
KPI | Value | Click Through Rate | Click thru Rate from "conduct query" to search result page | 1 | Number of clicks between conducing a search and selecting on of the results page. |  |  | search.gov | n/a | n/a | n/a | n/a | n/a | n/a |  | 2021-01-01: n/a; 2021-02-01: 23.2%; 2021-03-01: 21.9%
Supportive |  | Total Clicks | [5 empty] | search.gov | n/a | n/a | n/a | n/a | n/a | n/a |  | 2021-01-01: n/a; 2021-02-01: 198863; 2021-03-01: 224274
Informative | Trust | Zero Result Searches | # of queries resulting in zero results | 1 | number of searches that produce zero search results and the terms that produce zero results | What the data doesn't tell us is what are users searching for with typos yet still showing results. Larger # of zero result searches may be good. | bar chart per month | search.gov | 3 | 2 | 3 | 3 | 2 | 9 |  | 2021-01-01: 6; 2021-02-01: 1; 2021-03-01: 10
KPI | Trust | Customer Satisfaction | Question 1: Did you find what you were looking for today? [‘yes’ or ‘no’] | 1 | Defines user perception of their own success in finding what they were looking for |  | Rating over time (adjustable date range) Did you find what you were looking for today?(Y/N): grouped bar chart [2], every month? Line chart over time? | Medallia | n/a | n/a | n/a | n/a | n/a | n/a |  | 2021-01-01: n/a
|  |  | Question 2: What were you unable to find during your visit today? [text area] | 1 | Captures search terms that users were not able to find results for and provides examples of user phrasing |  | What were you unable to find during your visit today? (text) table
|  |  | Question 3: What is your overall satisfaction with this site? | 1 | How content users are with the search experience on va.gov | Do users say they are content with the site after not finding what they are looking for and vice versa? | Score ratings over time for all 3 elements of NPS (Total score, promotors & Detractor)
KPI | Value | Search Usage | Percentage of va.gov visitors who conducted a search (Extracting global search data from the "mini search" experiences) | 2 | What is the increase a result of? | What conclusion do we draw from this data? Less helpful information on homepage/nav? | line chart over time | Google Analytics | 2.01% | 1.94% | 1.9% | 1.89% | 1.55% | 1.42% |  | 2021-01-01: 1.8%; 2021-02-01: 1.78
| Value | Unique Searches Per Session | Avg. # search queries per session | 3 | How many searches a single user conducts during one visit to va.gov |  | line chart over time | TBD
| Health | Result Page Load Time | length of time to load the results page | 2 | Length of time users spend waiting for search results page to load. | What is considered the optimal time? Research industry standards and what it is today to compare |  | Google Analytics
PRODUCT: Off-Site Search Dashboard Link: TBD
Other Data Points of Interest /Future Consideration
| Health | Source Location | Page (within va.gov) where users are searching from | 3
| Value | Search Trends
Top Search Terms (Overall)
| Value | Comparing User success to user satisfaction |  |  | Shows us how many people are content with the experience despite not being able to find what they were looking for
Note on D5: users or queries?
Note on R19: Maybe 24%? Click tracking was just established in January so we need to validate the metrics we are seeing
Note on K21: certificate of ellityeigibility [87] alcohol teattment [22] ma caleb lanthorn the camanda [21]
Note on L21: bill for my surgergyc [30] form22-5490 [21]
Note on M21: where can i go to get a nocost flu shot [31] eut [26] change oede [24]
Note on N21: change my home address i have movedd [28] associations of va handymen [21] voulenteer [20]
Note on O21: va disaility 100 2021 [43] btss [37]
Note on P21: 6xxrq:jxv5tsazdm [173] bisablilltytates [117] kangaroo12345 [69] 60isabilitrating [47] master sargent nelson e. jackson first sargent 3902nd head quarters sq. u.s. air force [44] what diability qualify for cg10-10 program [38] bisablilltytates60 [37] btss [23] direct depost [20]
Note on R21: Queries with No Results superbowl tickets [65] 1095a [36] matthew bittel od [34] error code e4200 [33] btss [30] roanokeroanokejogs [21]
Note on T21: vrrap [133] compreensive assistance for family caregives [99] brumbles meister psychiatric elopement: using evidence to examine causative factors and preventative measures [62] dd2765 [57] btss [49] how much money can you make and be eligabe for hear aids [49] boca tsyin [34] milage [31] 1095a [28] how do i apply for lost va bernifits? [28]
Note on D27: Alt: Percentage of users waiting longer than 3 seconds for a page to load

## Planned (hidden)
|  | Sprint Plan for Current and Upcoming Sprints | Focal | Dev | Design | Product | Notes
GH Issue # | Initiative | Sprint 41 (Feb 20 - Feb 23) #19627 | Focal | Dev | Design | Product | Notes
12336 | Discovery | [Discovery] - Synthesize data and provide recommendations | Megan
12335 | Discovery | [Discovery] - Topline summary for VA.gov sitewide search usability study | Megan
19369 | Typeahead 1.0 | [Typeahead1.0] Order Suggestions based on character length | Sam
19370 | Typeahead 1.0 | [Typeahead1.0]Typeahead Styling Improvements | Sam
19682 | Analytics | [KPI Dashboard] Typeahead analytics tagging bug fixes | Sam
19683 | Onsite Search Enhancement | Search Autofocus exploration | Sam | 2021-03-05
9494 | XML Sitemap | [XML Sitemap] Remove Playbook from VA.gov XML Site Map | Sam | 4
19731 | Spelling Enhancement - Did you mean? | User Design for Spelling Suggestions | Megan
19730 | Spelling Enhancement - Did you mean? | product outline for spelling suggestions | Denise
19443 | Onsite Search Enhancement | Enhance Best Bets to include keyword variations for top form searches. | Denise/John
18512 | Discovery | [Discovery] Veteran Touchpoints Review | ALL
|  | Sprint 42 (Feb 24 - Mar 9). #19694 | Focal | Dev | Design | Product | Notes
Sprint Goals |  | TBD
18169 |  | [Discovery] Phrasing and Commonly Asked Questions Research | Megan |  |  |  | we may want to extract the two low priority items and knock the others out.
|  | data visualization for phrasing work above? | Megan
1
20168 |  | Right Rail Analytics | (analtyics)
|  | Sprint 43 (Mar 10- Mar 23) #19695 | Focal | Dev | Design | Product | Notes
Sprint Goals |  | TBD
19368 |  | Extend TypeAhead to All Users
|  | Backlog | Focal | Dev | Design | Product | Notes (Sprint Projections)
18512 |  | Veteran Touchpoints Review | All | 1 | 1 | 1
16190 |  | [Discovery] Rally Point Exploration | Megan |  |  |  | close for now. may circle back after user sessions
16191 |  | [Discovery] IRIS Exploration | Megan |  |  |  | close for now - change label to customer care (IRIS is being depricated. a blackhole of information)
16481 |  | [Search Results] Making modern VA.gov content 'preferred' in results | Denise/John
14143 |  | Investigate legacy search index subdomain | John |  |  |  | Not sure where this falls?
13939 |  | [XML Sitemap] On-Site Search: Generate a sitemap XML file via Facilities API | Sam |  |  |  | TBD - talk to Dave Conlon (Icebox)
9538 |  | Review & Update Best Bets/Top Recommendations | (Content)
17631 |  | Monitoring - Check that search functionality is working on va.gov | (Support)
11026 |  | [Offsite Discovery] Site Performance and SEO Optimization | Denise/John |  |  |  | team should review this and determine what is actionable
17535 |  | [Offsite Search] Identify KPIs for Off Site Search | Denise/John
11673 |  | [Offsite] Google Indexing Issue - Submitted URL Returns Unauthorized Request
18083 |  | [Offsite]Product Research SEO Audit + Optimization | Denise
19009 |  | [Product Discovery] COVID-19 Vaccine Finder - VA Data Distribution #19009
19224 |  | Search Spelling Suggestions Backend Implementation
19225 |  | Search Spelling Suggestions Frontend implementation
19372 |  | Create Acronym Database reader tool
19374 |  | Connect Acronym reader to search suggestions / reformat suggestions
17844 |  | [Type Ahead 1.0] Integrating canned suggestions for Type Ahead | John/Denise
To Be Added Tracking As of : 19627 (included)
|  | Discuss typeahead design suggestions with S+D team and Platform, accessiblity | Megan |  |  |  | does it need a collab cycle? do we do that or would platform?
|  | Create Wireframes (example graphics) to depict Analytics for KPIs on MVP Dashboard | Megan |  |  |  | see PW issue for reference. Need to determine if this is needed for MVP or v2 or V3

## Data Validation (hidden)
Data Validation Elements
Roadmap Status | Product
Current Focus | Onsite Search
Closed | OFFsite Search
BLOCKED | Typeahead
Defining
On Hold
Wrap Up
Status