## Phase 1
Change Request Control No. | Change Request Description | Request Origin | Date Requested | Priority | Level of Effort | CCB Review Date | CCB Acceptance | GitHub Issue No. | Comments | Phase | PROPOSED CONTENT
9 | Veterans are not clear that the references to VA Form 22-0994 are directly tied to the application they will be completing. FIX: Update content on the intro page so it's clear that the application they'll be completing is the VA Form 22-0994. | BAH (UX) | 2019-02-07 | Must have for launch | S | 2019-02-20 | 2019-02-20 | https://github.com/department-of-veterans-affairs/vets.gov-team/issues/17001 | DSVA said Must Have; This is a must-do; clarity | 1 | Complete this VET TEC application form (VA Form 22-0994). After submitting the application form, you’ll get a confirmation message. You can print this for your records. Then, complete an Application for VA Education Benefits (VA Form 22-1990), if you haven’t already. Note: If you're already receiving VA education benefits, you’ve already completed that application form and don’t need to submit it again. If you haven’t applied for VA education benefits yet, you’ll be able to do that from the confirmation page that appears after you submit your VET TEC application.”
8 | Veterans do not easily recognize VA Form 22-1990 by the number only when it's refered to on the introductory page. FIX: Update content on the intro page to include the name and purpose of VA Form 22-1990 in plain language so it's clear what it is. | BAH (UX) | 2019-02-07 | Must have for launch | S | 2019-02-20 | 2019-02-20 | https://github.com/department-of-veterans-affairs/vets.gov-team/issues/17013 | DSVA said Must Have; This is a must-do; providing absolute clarity to veterans is non-negotiable | 1 | **Incorporated into proposed content for CR #9 (above)
10 | Veterans are required to complete a 1990 if they have not already and we need to let them know this before they start the 0994 workflow. FIX: Update content on the INTRO page to let Veterans know they will be routed to VA Form 22-1990 after they've completed VA Form 22-0994. | BAH (UX) | 2019-02-07 | Must have for launch | S | 2019-02-20 | 2019-02-20 | https://github.com/department-of-veterans-affairs/vets.gov-team/issues/17015 | DSVA said Must Have | 1 | **Incorporated into proposed content for CR #9 (above)
16 | On the Intro page, mention that the benefit is only available to Veterans (in case someone lands on this form, without reading the program description and eligibility criteria that reside on the Education Services area on VA.gov). FIX: Content TBD | BAH (Usability Testing) | 2019-02-08 | Must have for launch | S | 2019-02-20 | 2019-02-20 | https://github.com/department-of-veterans-affairs/vets.gov-team/issues/17016 | DSVA: This is a must-do; it affects clarity about eligibility and affects who fills out the form | 1 | To be eligible for VET TEC, you must be a Veteran with at least one day of unexpired education benefits remaining.
18 | On the Work Experience page, define High-tech - is it only IT? What are the confines? FIX: Content TBD | BAH (Usability Testing) | 2019-02-08 | Must have for launch | S | 2019-02-20 | 2019-02-20 | https://github.com/department-of-veterans-affairs/vets.gov-team/issues/17017 | DSVA: This is a must-do; clarity | 1 | VET TEC focuses on 5 areas of high-tech training: *Information science *Computer programming *Data processing *Media applications *Computer software Are you working in one, or more, of these high-tech industries now? (*Required) { radio } Yes No { if no } Have you worked in any of these high-tech industries in the past? (*Required) { radio } Yes No
19 | On the Personal Information page, expand the helper text to apply to those who do not have OR do not want to provide their bank account information. FIX: Content TBD | BAH (Usability Testing) | 2019-02-08 | Must have for launch | S | 2019-02-20 | 2019-02-20 | https://github.com/department-of-veterans-affairs/vets.gov-team/issues/17018 | DSVA: This is a must-do; clarity | 1 | If you don’t have a bank account, or don’t wish to provide your bank account information, you must receive your payment through Direct Express Debit MasterCard.
31 | On the Applicant Information, (*Required) is not in line with the question that it is tied to. FIX: (*Required) needs to be inline with the question above, at the end of it. | BAH (UX) | 2019-02-05 | Must have for launch | S | 2019-02-20 | 2019-02-20 | https://github.com/department-of-veterans-affairs/vets.gov-team/issues/17020 | DSVA: This is an accessibility issue and is therefore a must-do | 1 | N/A
36 | On the Contact Information page, the page title "Contact information" needs to be sentence case. FIX: Change page title to sentence case: Contact information. | BAH (UX) | 2019-02-05 | Must have for launch | S | 2019-02-20 | 2019-02-20 | https://github.com/department-of-veterans-affairs/vets.gov-team/issues/17022 | DSVA: This is a basic design standards mismatch; this is a must-do | 1 | N/A

## Phase 2
Change Request Control No. | Change Request Description | Request Origin | Date Requested | Priority | Level of Effort | GitHub Issue No. | Comments | UX Refinment? | Phase | Additional comments from 2/21 meeting | Proposed Content
13 | On Program entry page the user should not be able to put in a date before 2019 FIX: Date field validation on program page for 2019 or later | EDU | 2019-02-12 | Nice to have for launch | M |  | DSVA said Must Have; This is a must-do; an invalid date 1. puts yet MORE bad data into VA systems, and 2. potentially causes confusion to application processing staff, which would result in a delay in the application review process | Should program start date be today + future or is it really anything after Dec 31,2 018. Will review on 2/21 Education team: If possible -Allow for Jan 1, 2019 and after | 2 | DSVA & Eduction decided: Leave it as is for now and revisit after go-live | N/A
7 | Review Page yes is being displayed as "true". FIX: Replace "True" with "Yes" on the Review page. **BAH concern- this is a global update and a limitation of the form system as it exists today. | BAH (UX) | 2019-02-05 | Nice to have for launch | L |  | DSVA said Must Have | Yes - Need clarification from DSVA on if they want us to move forward on this update. Will review on 2/21 | 2 | Matt will open issue for this on broader platform team; no action needed from BAH | N/A
45 | Round 2 for the language on confirmation page urging user to complete 1990 if haven't done so yet (CR #3) It doesn't seem sufficient to do it on the confirmation page. Must be clear on the static landing page (implemented by DSVA), and on the subway map application intro. We would explore the feasibility of a design pattern that automatically redirects users to the 1990 if they select "No" to the 1990 status check question at the start of the form | DSVA | 2019-02-15 | Nice to have for launch |  |  | DSVA said Must Have | Yes - this requires additional discovery with DSVA before UX can begin working on this. Will review on 2/21 | 2 | Next round of usability testing make sure user are seeing the bullet on the intro page and understand what they are expected to do if they have NOT completed a 1990 | TBD
46 | Round 2 for the notes at the bottom of the Address and Banking Info page (CR #5 & #6) We will want to do a final sanity check on the content that is provided by EDU; specifically looking to ensure content matches what is actually happening, and where changes are propogated (or not) | DSVA | 2019-02-15 | Nice to have for launch |  |  | DSVA said Must Have | Yes - this requires additional discovery with DSVA and EDU before UX can finalize the approach to this. Will review on 2/21 | 2 | Education confirmed this is the process; no further action needed | N/A
47 | Round 2 for question that asks user if applied for education benefits in the past (CR #14) The new text is NOT plain language. Must be reviewed by DSVA. | DSVA | 2019-02-15 | Nice to have for launch | S |  | DSVA said Must Have | Yes - Need vetting from DSVA on this before implementation. Amy to share content update with them via slack and then get started | 2 | Amy (BAH UX) says we have this content- so should be good | Have you applied for VA education benefits in the past?{ radio } *Yes *No { if no, display: You’ll also need to complete an Application for VA Education Benefits (VA Form 22-1990), so we can determine if you qualify for VA education benefits. We’ll take you to that application after you’ve finished filling out this one. }
21 | On the Bank Information page, add a Confirm Account Number field to mitigate data entry errors. FIX: Display Confirm Account Number field | BAH (Usability Testing) | 2019-02-08 | Post-MVP |  | DSVA: This is a must-do; clarity |  | Yes - This would be a new pattern so requires consultation with DSVA. This would include the routing number too. Review on 2/21 | 2 | Agree that not going to do this one | N/A