## Form 0994_ VET TEC-2019-02-27
Issue Number | Issue Title | Pipeline | Story Points | Milestone | Labels
16467 | Vet Tec: Routing 1990 when submitted on same day as 0994 | Backlog |  |  | bah-0994,technical
16631 | VetTec: Produce Contact Center Product Demo, Transcription & Guide | Current Sprint |  | BAH Sprint 15 | bah-0994,bah-sprint-14,bah-sprint-15,carryover,devsupporting,mvp
16637 | VetTec: BA Review of Staging against Prototype & Content Doc | In Progress | 3 | BAH Sprint 15 | bah-0994,bah-sprint-14,bah-sprint-15,carryover,devsupporting,mvp
16695 | VetTec: Prioritize Content (or Prototype) Feedback from DS, Tone & Voice Expert | Current Sprint | 3 | BAH Sprint 15 | UX,bah-0994,bah-sprint-14,bah-sprint-15,carryover,mvp
16715 | VetTec: Integration testing of routing | Backlog |  |  | bah-0994,testing
16909 | VET TEC: Ensure Automated E2E tests are running in Production | Backlog |  |  | bah-0994,technical
16960 | VET TEC: 0994 Content Refinements based on Tone & Voice Expert (v.5) | Current Sprint | 5 | BAH Sprint 15 | UX,bah-0994,bah-sprint-15
16961 | VET TEC: 0994 Update Prototype with Content post-DS VA Review (v.5) | Current Sprint | 5 | BAH Sprint 15 | UX,bah-0994,bah-sprint-15
16962 | VET TEC: Review prototype with Uxers (after DS review) | Current Sprint | 5 | BAH Sprint 15 | UX,bah-0994,bah-sprint-15
16965 | VetTec: Compile session notes from usability testing | Current Sprint | 3 | BAH Sprint 15 | UX,bah-0994,bah-sprint-15
16966 | VET TEC: Usability Testing Findings & Recommendations | Current Sprint | 5 | BAH Sprint 15 | UX,bah-0994,bah-sprint-15
16967 | VetTec: Usability Testing Readout Deck | Current Sprint | 13 | BAH Sprint 15 | UX,bah-0994,bah-sprint-15
16979 | VET TEC: Complete Integration Testing | In Progress | 21 | BAH Sprint 15 | bah-0994,bah-sprint-15,testing
17054 | VET TEC: Year to date report not displaying expected numbers for Submitted" and "YTD Daily"" | In Progress |  | BAH Sprint 15 | bah-0994,bug
17071 | Cannot create new account on Bank Information page after entering and saving initial payment information | Validate |  | BAH Sprint 15 | bah-0994,bug
17088 | VET TEC: Create a password protected feature flag for VetTec URL (FE) | Ready |  | BAH Sprint 15 | bah-0994,devops,front end,platypus-tools
17089 | VET TEC: Deploy VetTec tool to production (Internal Engineer) | Ready |  | BAH Sprint 15 | bah-0994,devops,front end,platypus-tools
17107 | VET TEC: Testing of the spool files, spool submission report and year to date report | Current Sprint |  | BAH Sprint 15 | bah-0994
16623 | Request Pre-Launch ATO Review VA Form 22-0994 (VetTec) | Closed |  | BAH Sprint 15 | bah-0994,bah-sprint-14,bah-sprint-15,carryover,devops,devsupporting,external-request
16824 | Request IA Review - VET TEC | Closed |  | BAH Sprint 15 | bah-0994,devsupporting,external-request,ia
17015 | VetTec: Update Intro page (reference to 1990, explain routing to 1990 & VET TEC is exclusive to Veterans) | Closed | 2 | BAH Sprint 15 | approved change request,bah-0994,functional
17020 | VetTec: Make *Required" display in-line with correlating question on Applicant Information page" | Closed |  | BAH Sprint 15 | approved change request,bah-0994,functional
17022 | VetTec: Case sensitivity for title on Contact Information page | Closed |  | BAH Sprint 15 | approved change request,bah-0994,functional
15876 | VetTec: Create VetTec Technical Design Document | Closed | 8 | BAH Sprint 12 | bah-0994,bah-526,bah-sprint-11,bah-sprint-12,dev-support,mvp
15892 | Create VetTec 0994 Schema | Closed | 8 | BAH Sprint 12 | bah-0994,bah-526,bah-sprint-11,bah-sprint-12,mvp,technical
15893 | Configure pre-fill for VetTec 0994 Form | Closed | 13 | BAH Sprint 12 | bah-0994,bah-526,mvp,technical
15895 | Create VetTec Web Form 0994 Prototype Page | Closed | 21 | BAH Sprint 12 | bah-0994,bah-526,bah-sprint-12,functional
15896 | Define 0994 Template for vets-api | Closed | 13 | BAH Sprint 11 | bah-0994,bah-526,bah-sprint-11,mvp
15897 | Research VetTec 0994 Form Controller | Closed | 1 | BAH Sprint 12 | bah-0994,bah-526,bah-sprint-11,mvp,technical
15898 | Generate & Route VetTec 0994 Spool File | Closed | 8 | BAH Sprint 13 | bah-0994,bah-sprint-13,mvp,technical
15899 | VetTec: Add 0994 to existing Daily Report | Closed | 8 | BAH Sprint 13 | bah-0994,bah-sprint-13,mvp,technical
15900 | VetTec: Update Transform for VetTec 0994 | Closed | 8 | BAH Sprint 14 | bah-0994,bah-sprint-14,mvp,technical
15921 | Form 0994: UX Discovery | Closed | 5 | BAH Sprint 11 | UX,bah-0994,bah-526,bah-sprint-11,mvp
15922 | Form 0994: Veteran Discovery Discussion Guide | Closed | 5 | BAH Sprint 12 | UX,bah-0994,bah-526,bah-sprint-12,mvp
15923 | Form 0994: Claims Examiner Discovery Discussion Guide | Closed | 5 | BAH Sprint 12 | UX,bah-0994,bah-526,bah-sprint-12,mvp
16066 | Test Case & Test Execution for story 15895 - Create VetTec Prototype 0994 | Closed |  | BAH Sprint 12 | bah-0994,bah-526,bah-sprint-11,bah-sprint-12,testing
16118 | 0994 Create Research Plan | Closed | 3 | BAH Sprint 12 | UX,bah-0994,bah-526,bah-sprint-12,mvp
16121 | 0994 Conduct Claims Examiner Discovery Interviews | Closed | 8 | BAH Sprint 12 | UX,bah-0994,bah-526,bah-sprint-12,mvp
16127 | 0994 Draft Content (v.1) based on Discovery Findings | Closed | 8 | BAH Sprint 12 | UX,bah-0994,bah-526,bah-sprint-12,mvp
16128 | 0994 Prototype: Internal Draft | Closed | 13 | BAH Sprint 12 | UX,bah-0994,bah-526,bah-sprint-12,mvp
16131 | 22-0994 Form Prototype Header, Missing fields, and field validation | Closed |  | BAH Sprint 12 | bah-0994,bah-526,bah-sprint-12,bug
16426 | VetTec: Determine Integration Testing Approach for Spool File Routing | Closed | 8 | BAH Sprint 13 | bah-0994,bah-sprint-13,mvp,testing
16430 | VetTec: Add new question to trigger 0994 interview | Closed | 5 | BAH Sprint 13 | bah-0994,bah-sprint-13,functional,mvp
16434 | VetTec: 0994 Interview Introduction page | Closed | 8 | BAH Sprint 13 | bah-0994,bah-sprint-13,functional,mvp
16435 | VetTec: Personal Information page | Closed | 3 | BAH Sprint 13 | bah-0994,bah-sprint-13,functional,mvp
16440 | VetTec: Contact Information page | Closed | 3 | BAH Sprint 13 | bah-0994,bah-sprint-13,functional,mvp
16441 | VetTec: Page that asks if user completed 22-1990 | Closed | 3 | BAH Sprint 13 | bah-0994,bah-sprint-13,functional,mvp
16442 | VetTec: Military Service page | Closed | 3 | BAH Sprint 13 | bah-0994,bah-sprint-13,functional,mvp
16443 | VetTec: Banking information page | Closed | 3 | BAH Sprint 13 | bah-0994,bah-sprint-13,functional,mvp
16444 | VetTec: Work and Training page | Closed | 3 | BAH Sprint 13 | bah-0994,bah-sprint-13,functional,mvp
16445 | VetTec: Education and Training page | Closed | 3 | BAH Sprint 13 | bah-0994,bah-sprint-13,functional,mvp
16448 | VetTec: Program entry page | Closed | 3 | BAH Sprint 14 | bah-0994,bah-sprint-13,bah-sprint-14,blocked,functional,mvp,not on staging
16449 | VetTec: 0994 Review/Summary page | Closed | 5 | BAH Sprint 13 | bah-0994,bah-sprint-13,functional,mvp
16450 | VetTec: Frontend logic for when user answers if completed 1990 Form | Closed | 3 | BAH Sprint 13 | bah-0994,functional,mvp,pulledin
16451 | VetTec: Content updates | Closed | 3 | BAH Sprint 14 | bah-0994,bah-sprint-14,functional
16481 | Test Case and Execution Record for VetTec: 0994 Interview Introduction page #16434 | Closed |  | BAH Sprint 13 | bah-0994,bah-sprint-13,mvp,testing
16483 | VetTec: Integration Testing | Closed | 21 | BAH Sprint 14 | bah-0994,bah-sprint-14,testing
16484 | VetTec: Update 0994 Schema | Closed | 8 | BAH Sprint 13 | bah-0994,mvp,technical
16485 | Test Case and Execution Record for VetTec: Add new question to trigger 0994 interview #16430 | Closed |  | BAH Sprint 13 | bah-0994,bah-sprint-13,testing
16491 | Test Case and Execution Record for VetTec: 0994 Review/Summary page #16449 | Closed |  | BAH Sprint 13 | bah-0994,bah-sprint-13,mvp,testing
16532 | Recruit Veterans for User Research (Sprint 13) | Closed | 1 | BAH Sprint 13 | UX,bah-0994,bah-sprint-13,mvp
16534 | Test Case and Execution Record for VetTec: Program entry page #16448 | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-13,bah-sprint-14,mvp,testing
16536 | VetTec: Create Usability Testing Script | Closed | 8 | BAH Sprint 13 | UX,bah-0994,mvp,pulledin
16537 | VetTec: Create Usability Testing Prototype variation | Closed | 5 | BAH Sprint 13 | UX,bah-0994,mvp,pulledin
16538 | VetTec: Conduct Usability Test | Closed | 13 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14,mvp
16539 | VetTec: Compile session notes from usability testing | Closed | 3 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14,mvp
16541 | VetTec: Usability Testing Findings & Recommendations | Closed | 5 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14,mvp
16544 | VetTec: Usability Testing Readout Deck | Closed | 13 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14,mvp
16545 | VetTec: Final Content (v.6) Refinements based on Usability Findings | Closed | 5 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14,mvp
16546 | VetTec: Refine Prototype based on testing inputs | Closed | 5 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14,mvp
16547 | VetTec: Final UX Review of Prototype | Closed | 3 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14,mvp
16548 | VetTec: Final DSVA Review of Prototype | Closed | 5 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14,mvp
16549 | VetTec: Prototype Checkpoint Prep (includes analytics?) | Closed | 5 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14,mvp
16551 | VetTec: Share prototype & design assets with Dev team | Closed | 1 | BAH Sprint 13 | UX,bah-0994,bah-sprint-13,mvp
16599 | VetTec: DSVA/Stakeholder Requirements Mtg 1/24/19 | Closed | 1 | BAH Sprint 13 | UX,bah-0994,bah-sprint-13,mvp
16600 | VetTec: MVP Content Document | Closed | 8 | BAH Sprint 13 | UX,bah-0994,bah-sprint-13,mvp
16601 | VetTec: MVP Prototype | Closed | 13 | BAH Sprint 13 | UX,bah-0994,bah-sprint-13,mvp
16602 | MVP Content Doc - Post Stakeholder Review Updates | Closed | 5 | BAH Sprint 13 | UX,bah-0994,bah-sprint-13,mvp
16603 | MVP Prototype - Post Stakeholder Review Updates | Closed | 8 | BAH Sprint 13 | UX,bah-0994,bah-sprint-13,mvp
16604 | 0994 Review prototype with B.A. | Closed | 1 | BAH Sprint 13 | UX,bah-0994,bah-sprint-13,mvp
16605 | VetTec: MVP Content - Intro Page | Closed | 3 | BAH Sprint 13 | UX,bah-0994,bah-sprint-13,mvp
16606 | VetTec: MVP Prototype - Intro Page | Closed | 3 | BAH Sprint 13 | UX,bah-0994,bah-sprint-13,mvp
16610 | VetTec: Pre-Usability Testing UX Review of Prototype | Closed | 5 | BAH Sprint 13 | UX,bah-0994,mvp
16624 | VetTec: Accessibility/508 Testing | Closed | 8 | BAH Sprint 14 | bah-0994,bah-sprint-14,mvp,testing
16625 | VetTec: Conduct cross-browser QA testing | Closed | 8 | BAH Sprint 14 | bah-0994,bah-sprint-14,mvp,testing
16633 | VetTec: Write e2e tests for all functionality in the launched product through submission | Closed | 5 | BAH Sprint 14 | bah-0994,bah-sprint-14,mvp,technical
16635 | VetTec: Request for Load Testing (Form 22-0994) | Closed |  | BAH Sprint 15 | Kraken,bah-0994,bah-sprint-14,bah-sprint-15,carryover,devops,devsupporting,external-request,loadtest
16636 | VetTec: UX Review of Staging against Prototype & Content Doc | Closed | 8 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14,mvp
16648 | VetTec: Research routing for 0994 and 1990 | Closed | 8 | BAH Sprint 14 | bah-0994,bah-sprint-14,technical
16654 | VetTec: Unable to Continue your application" for 0994 from https://staging.va.gov/education/how-to-apply/" | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug
16682 | VetTec: Banking information should not be required | Closed | 2 | BAH Sprint 14 | bah-0994,bah-sprint-14,blocked,functional
16683 | VetTec: Metrics for Success | Closed | 3 | BAH Sprint 14 | UX,bah-0994,bah-sprint-14
16686 | VetTec: UAT Plan & Recruiting | Closed | 8 | BAH Sprint 14 | bah-0994,bah-sprint-14,devsupporting
16688 | VetTec: Update Research Plan | Closed | 3 | BAH Sprint 13 | UX,bah-0994,mvp,pulledin
16714 | 508: VET TEC form Program Entry page focus should shift to the beginning of the New Program" form when adding additional programs" | Closed |  | BAH Sprint 14 | 508/Accessibility,bah-0994,bah-sprint-13,bah-sprint-14,bug
16730 | VetTec: Error on submission of form | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug
16742 | VET TEC: Saved bank information not deleted when new account information | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug
16747 | VET TEC: Program City, State, Start date not required | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug
16754 | VET TEC: View and manage your forms on your Account page link is wrong | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug
16763 | VET TEC: Receiving 48 daily YTD" and "Spool Submission" report emails every day " | Closed |  | BAH Sprint 15 | bah-0994,bah-sprint-14,bah-sprint-15,bug,carryover
16780 | VetTec: Defect- page titles within 0994 workflow | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug
16795 | VetTec: Defect - Street address fields on Contact Info page | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug
16797 | VetTec: Defect- label for Benefits eligibility (chapter 1 of 7) | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug,not on staging
16799 | VET TEC: Veteran Name, DOB, SSN not displaying for some users | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug
16812 | VET TEC: Unable to submit | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug
16818 | Test case for VetTec: Banking information should not be required #16682 | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,testing
16819 | VetTec: Defect- masked banking info (account/routing number) should send on spool file | Closed |  | BAH Sprint 14 | bah-0994,bah-sprint-14,bug
16820 | VET TEC: Postal code required for international address | Closed |  |  | bah-0994,bah-sprint-14,bug
16845 | VetTec: Remove upper Start VET TEC Application" button on Intro page" | Closed | 2 | BAH Sprint 14 | approved change request,bah-0994,pulledin
16846 | VetTec: Change reference to schools/trainings within the 0994 workflow | Closed | 1 | BAH Sprint 14 | approved change request,bah-0994,pulledin
16885 | VetTec: Remove reference to VET TEC as an 'educational benefit' or 'benefit' | Closed | 1 | BAH Sprint 14 | approved change request,bah-0994,functional,mvp,pulledin
16887 | VetTec: Add language to 0994 confirmation page if user has NOT completed 1990 | Closed | 1 | BAH Sprint 14 | approved change request,bah-0994,mvp,pulledin
16888 | VetTec: Update the Note" text at the bottom of the Address and Banking info page for 0994" | Closed | 1 | BAH Sprint 14 | approved change request,bah-0994,functional,mvp,pulledin
16931 | VET TEC: Update page URLs for the workflow | Closed |  | BAH Sprint 15 | bah-0994,bah-sprint-15,mvp,technical
16933 | VET TEC: Increase Code Coverage | Closed | 5 | BAH Sprint 15 | bah-0994,bah-sprint-15,technical
16945 | VET TEC: Date always required on Review Application screen | Closed | 8 | BAH Sprint 15 | bah-0994,bah-sprint-15,bug,mvp
16963 | VET TEC: CCB Nice to Have & Post MVP Updates | Closed | 13 | BAH Sprint 15 | UX,bah-0994,bah-sprint-15
16964 | VetTec: Observe UAT for UX Findings | Closed | 8 | BAH Sprint 15 | UX,bah-0994,bah-sprint-15
16976 | VET TEC: Unable to start VET TEC application with certain staging test users | Closed |  | BAH Sprint 15 | bah-0994,bah-sprint-15,bug
17019 | VET TEC: Update required program information | Closed | 2 |  | bah-0994,bah-sprint-15,bug
17060 | Selecting Continue Application for VET TEC application on Education/Training How to Apply page does not send user to application | Closed |  | BAH Sprint 15 | bah-0994,bah-sprint-15,bug
16123 | 0994 Claim Examiner Session Notes | Closed
16661 | Duplicate: VetTec: Review prototype with Devs (pre-usability testing) | Closed
16533 | OBE: Send User Research Thank You Notes (Sprint 13) | Closed
16550 | VetTec: DSVA Checkpoint / Jan 24 Stakeholder Requirements Mtg | Closed
16609 | OBE: VetTec: Update Non-Veteran Discovery Discussion Guide for Version 2.0 | Closed
16124 | OBE: VetTec: Conduct Veteran Discovery Interviews for Version 2.0 | Closed
16125 | OBE: VetTec: Veteran Discovery Discussion Session Notes for Version 2.0 | Closed
16612 | OBE: VetTec: Non-Veteran Discovery Discussion Session Notes for Version 2.0 | Closed
16126 | obe: VetTec: Synthesize Interview Findings for Version 2.0 | Closed
16596 | OBE: Recruit Non-Veterans for User Research (Sprint 13) | Closed
16613 | OBE: VetTec: Draft Content based on Discovery Findings for Version 2.0 | Closed
16692 | VetTec: Pre-Usabaility Testing UX Review of Protytype | Closed
16608 | VetTec: Update Research Plan for Version 2.0 | Closed
16597 | VetTec: Update Research Plan | Closed
16660 | VetTec: Review prototype with B.A. (pre-usability testing) | Closed
16611 | VetTec: Conduct Non-Veteran Discovery Interviews for Version 2.0 | Closed
16607 | VetTec: Form Discovery - V2 | Closed
16598 | OBE: VetTec: MVP Form Discovery - Round 2 | Closed
16694 | OBE: VetTec: Solicit Content (or Prototype) Feedback from DS, Tone & Voice Expert | Closed
16881 | Form System: Formatting of high-tech work experience | Closed |  |  | bug,forms-library,front end,platypus-tools
16634 | DUPLICATE: VetTec: Request IA Review (Form 22-0994) | Closed
17050 | [SCREENREADER]: VET TEC - NVDA does not read the error if I forget to agree to the privacy policy | Closed |  |  | 508/Accessibility,forms-library,platypus-tools,sev 2,sitewide