## Tracker
Section | Priority | Iteration | In Development | In Staging | QA Sign-off | UX Sign-off | BA Sign-off | EDU Sign-off | Ready for Production | In Production | Status | Note
501 | 1 | Solution | N/A | Y | 2019-05-17 | N/A | 2019-05-14 | 2019-06-06 | Y | Y | Development Complete
|  | Learn More Content | N/A | Y | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-07-02 | Y | Y (07-03) | Development Complete
107 | 2 | MVP | N/A | Y | 2019-07-02 | N/A | 2019-07-02 | 2019-07-02 | Y | Y (07-03) | Development Complete
|  | Static GI Bill Page | N/A | Y | 2019-07-02 | 2019-07-03 | 2019-07-02 | 2019-07-03 | Y | Y (07-03) | Development Complete
|  | Phase 2 | Y | N | [6 empty] | In Usability Testing | Phase 2 includes UI + GIDS updates
102 | 3 | Solution | N/A | Y | 2019-04-25 | N/A | 2019-04-30 | Y | Y | Y | Development Complete
203 | 4 | Solution | N/A | Y | 2019-05-08 | N/A | 2019-05-14 | 2019-06-06 | Y | Y | Development Complete
116 | 5 | MVP | Y | Y | 43676 | 43677 | 43677 | 43677 | Y | Y | Development Complete | MVP Includes Preferred Provider / Logo updates
|  | Phase 2 | N | N | [6 empty] | Not Started
111 | 6 | MVP | Y | Y | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-15 | Y | Y (07-16) | Development Complete
|  | Phase 2 | Y | Y | 2019-08-19 | 2019-08-21 | 2019-08-12 | 2019-08-15 | Y | Y (08-20) | Development Complete
109 | 7 | Solution | N | Y | 2019-06-19 | N/A | 2019-07-02 | 2019-07-02 | Y | Y (07-03) | Development Complete | EDU: OK with current behavior and having to manually rearrange columns in the meantime
|  | Column Order | Y | Y | 43663 | N/A | 43663 | 43665 | Y | Y (07-23) | Development Complete
|  | New 109 File | Y | Y | 43685 | N/A | 43689 | 43696 | Y | Y (08-20) | Development Complete
105 | 8 | Solution | Y | Y | 2019-07-01 | N/A | 2019-07-01 | 2019-08-05 | Y | N | Ready for Production | Cannot be released to production until 08/01/2019 2019-07-08: EDU may request that this not be delivered on 08/01/19. Awaiting feedback on how to proceed. 2019-08-05: EDU signed off on functionality. Awaiting legislation to deploy to production.
104 | 9 | Solution | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2019-06-27: Received confirmation from EDU that no work is necessary due to future effective date.