## Run_Book_RAID
Task # | Workstream | Status | Milestone | Sprint | Target Date | Actual Date | Owner | Dependancy | In Progress Tracker | Notes:
0 |  | In progress | VAMC - Upgrade - VISN - 4 (8 Systems, 48 Facilities, 413 Health Services) | Sprint 28 | 2020-08-17 | TBD
1 | Drupal/CMS | Complete | System creation in Drupal |  | Unknown | Unknown | Kevin Marsh |  | 100%
2 | Drupal/CMS | Complete | Facility creation and data input in Drupal |  | 2019-12-02 | 2019-12-02 | Kevin Marsh | 2 | 100% | Creates Facility API associations and provides Facility ID
1.1 | Drupal/CMS | Not Started | Creation of System Facility Pages (8 systems, 48 Facilities) |  | TBD |  | TBD | Being determined | 0%
1.2 | Drupal/CMS | Not Started | Alert Banner configured for All "NEW" VISN 4 Sites - Stating "Beta Launch" |  | TBD |  | Kevin Marsh | Being determined | 0%
3 | Backend Engineer | In progress | System Menu and Detail Page Creation (8 complete Systems) | Sprint 16 | 2020-03-04 |  | Sundar K. | 1, 2 | 60%
3.1 | Backend Engineer | Complete | *Lebanon, PA Menu - Standard (With added items) | Sprint 12 | 2020-01-14 | 2020-01-14 | Sundar K. |  | 100%
3.1.1 | Backend Engineer | Complete | *Creation of Lebanon, PA Tier II System (30 Pages) | Sprint 12 | 2020-01-14 | 2020-01-14 | Sundar K. |  | 100%
3.2 | Backend Engineer | Complete | *Altoona, PA - Standard | Sprint 13 | 2020-01-28 | 2020-01-28 | Sundar K. |  | 100%
3.2.1 | Backend Engineer | Complete | *Creation Altoona, PA Systems - Tier I (30 pages) | Sprint 13 | 2020-01-28 | 2020-01-28 | Sundar K. |  | 100%
3.3 | Backend Engineer | Complete | *Butler & Coatesville - Standard | Sprint 14 | 2020-02-11 | 2020-02-05 | Sundar K. |  | 100%
3.3.1 | Backend Engineer | Complete | *Creation of Butler and Coatesville, Tier I systems (60 Pages) | Sprint 14 | 2020-02-11 | 2020-02-11 | Sundar K. |  | 100%
3.4 | Backend Engineer | Not Started | *Erie, Wilkes-Barre, Wilminghton (DE) - Standard | Sprint 15 | 2020-02-25 |  | Sundar K. |  | 0%
3.4.1 | Backend Engineer | Not Started | *Creation of Erie, Wilkes-Barre, Wilmington (DE), (Tier I) Systems (90 Pages) | Sprint 15 | 2020-02-25 |  | Sundar K. |  | 0%
3.5 | Backend Engineer | Not Started | *Philadelphia - Standard Menu with added Research Page | Sprint 16 | 2020-03-04 |  | Sundar K. |  | 0%
3.5.1 | Backend Engineer | Not Started | *Creation of Philiadelphia (Tier III) System 30 + Specialized Pages | Sprint 16 | 2020-03-04 |  | Sundar K. |  | 0%
4 | Build Optimization | Not Started | VAMC - Facility Model and Page Optimization/Automation |  | 2020-04-21 |  | Sundar K. |  | 0% | "Determine if any pages can be cloned/copied from previous iterations (Pittsburgh) and then content updated"
4.1 | Build Optimization | Not Started | Troubleshoot and test Cloning in Dev environment | Sprint 17 | 2020-03-24 |  | Sundar K. |  | 0%
4.2 | Build Optimization | Not Started | Hardening of Content pages, Automation of page creation in package/script | Sprint 19 | 2020-04-21 |  | Sundar K. |  | 0%
4.3 | Build Optimization | Not Started | Hardening of Menus, Automation of standard Menus per system | Sprint 19 | 2020-04-21 |  | Sundar K. |  | 0%
5 | Migration | In progress | Migration of all "Static - Unchanging Legacy Content" | Sprint 21 | 2020-05-19 |  |  |  | 0%
5.1 | Migration | In progress | *Creation and Migration of System Leadership Profiles (8 systems) | Sprint 16 | 2020-03-10 |  | TBD | 1,2 | 40%
| Migration | Complete | **Lebannon, PA - Leadership | Sprint 13 | 2020-01-28 | 2020-01-21 | TBD |  | 100%
| Migration | Complete | **Altoona, PA - Leadership | Sprint 14 | 2020-02-11 | 2020-02-04 | TBD |  | 100%
| Migration | In progress | **Butler & Coatesville - Leadership | Sprint 15 | 2020-02-25 |  | TBD |  | 0%
| Migration | Not Started | **Erie & Wilkes-Barre - Leadership | Sprint 15 | 2020-02-25 |  | TBD |  | 0%
| Migration | Not Started | **Philadelphia & Wilmington - Leadership (2 sites) | Sprint 16 | 2020-03-10 |  | TBD |  | 0%
5.2 | Migration | In progress | *Migration of (Static) News Releases/Feature Stories from Legacy sites | Sprint 17 | 2020-03-24 |  | TBD |  | 33.33%
5.2.1 | Migration | Complete | **Lebannon, PA - Images and Stories | Sprint 13 | 2020-01-28 | 2020-01-27 | Stan G | 24 | 100%
5.2.2 | Migration | Complete | **Altoona, PA - Images and Stories | Sprint 14 | 2020-02-11 | 2020-02-11 | Stan G | 25 | 100%
5.2.3 | Migration | In progress | **Butler & Coatesville - Images and Stories | Sprint 15 | 2020-02-25 |  | TBD | 26 | 0%
5.2.4 | Migration | Not Started | **Erie & Wilkes-Barre - Images and Stories | Sprint 16 | 2020-03-10 |  | TBD | 27 | 0%
5.2.5 | Migration | Not Started | **Wilmington - Images and Stories | Sprint 17 | 2020-03-24 |  | TBD | 28 | 0%
5.2.6 | Migration | Not Started | **Philadelphia - Images and Stories | Sprint 17 | 2020-03-24 |  | TBD |  | 0%
5.3 | Migration | Not Started | *Migration of (Static) Mission/Vision System Pages | Sprint 22 | 2020-06-02 |  | TBD |  | 0%
5.3.1 | Migration | Not Started | **Lebannon, PA | Sprint 18 | 2020-04-07 |  | TBD |  | 0%
5.3.2 | Migration | Not Started | **Altoona, PA | Sprint 18 | 2020-04-07 |  | TBD |  | 0%
5.3.3 | Migration | Not Started | **Butler & Coatesville | Sprint 19 | 2020-04-21 |  | TBD |  | 0%
5.3.4 | Migration | Not Started | **Erie & Wilkes-Barre | Sprint 20 | 2020-05-05 |  | TBD |  | 0%
5.3.5 | Migration | Not Started | **Wilmington - | Sprint 21 | 2020-05-19 |  | TBD |  | 0%
5.3.6 | Migration | Not Started | **Philadelphia - | Sprint 22 | 2020-06-02 |  | TBD |  | 0%
5.4 | Migration | Not Started | *Migration of (Static) Transportation Page information | Sprint 21 | 2020-05-19 |  | TBD |  | 0%
5.4.1 | Migration | Not Started | **Lebannon, PA | Sprint 18 | 2020-04-07 |  | TBD |  | 0%
5.4.2 | Migration | Not Started | **Altoona, PA & Butler, PA | Sprint 18 | 2020-04-07 |  | TBD |  | 0%
5.4.3 | Migration | Not Started | **Coatesville & Erie, PA | Sprint 19 | 2020-04-21 |  | TBD |  | 0%
5.4.4 | Migration | Not Started | **Wilkes-Barre, PA & Wilmington(DE) | Sprint 20 | 2020-05-05 |  | TBD |  | 0%
5.4.5 | Migration | Not Started | **Philadelphia, PA | Sprint 21 | 2020-05-19 |  | TBD |  | 0%
5.5 | Migration | Not Started | *Migration of (Static) Policies Page information | Sprint 21 | 2020-05-19 |  | TBD |  | 0%
5.5.1 | Migration | Not Started | **Lebannon, PA | Sprint 18 | 2020-04-07 |  | TBD |  | 0%
5.5.2 | Migration | Not Started | **Altoona, PA & Butler, PA | Sprint 18 | 2020-04-07 |  | TBD |  | 0%
5.5.3 | Migration | Not Started | **Coatesville & Erie, PA | Sprint 19 | 2020-04-21 |  | TBD |  | 0%
5.5.4 | Migration | Not Started | **Wilkes-Barre, PA & Wilmington(DE) | Sprint 20 | 2020-05-05 |  | TBD |  | 0%
5.5.5 | Migration | Not Started | **Philadelphia, PA | Sprint 21 | 2020-05-19 |  | TBD |  | 0%
6 | Business Analytics | In progress | Collection of required Analytics for Content and API Page Creation | Sprint 22 | 2020-06-02 |  | BA Group |  | 31.33%
6.1 | Business Analytics | In progress | Analytics-Research - System Health Services (8 Systems) | Sprint 15 | 2020-02-25 |  | Lisa T, Chanelle B |  | 75%
6.2 | Business Analytics | In progress | Analytics-Research - Creation of System Analytics Playbooks (8 Systems) | Sprint 15 | 2020-02-25 |  | Lisa T, Chanelle B |  | 75%
6.2 | Business Analytics | In progress | Analytics-Research - System Facility emenities (8 Systems, 48 Facilities) | Sprint 17 | 2020-03-24 |  | Ed B. |  | 38%
6.3 | Business Analytics | Not Started | Analytics-Research - System (Caregiver/POC) for Health Service Program information | Sprint 20 | 2020-05-05 |  | Lisa T, Chanelle B |  | 0% | Total of 8 systems, 9 pages per system, 1-5 caregivers per page (72 pages, est: 216 contacts)
6.4 | Business Analytics | Not Started | Analytics-Research - System specific (Action Button/Top Task Local information) | Sprint 22 | 2020-06-02 |  | Lisa T, Chanelle B |  | 0%
6.5 | Business Analytics | Not Started | Playbook automation creation for data collection | Sprint 24 | 2020-06-30 |  | Lisa Trombly |  | 0%
7 | Content Writer | In progress | Custom Content Creation | Sprint 27 | 2020-08-11 |  |  |  | 0%
7.1 | Scrum Master | In progress | Creation of Content Page Templates (How to Guides for each Content page) | Sprint 16 | 2020-03-10 |  | Stan G |  | 50%
7.2 | Content Writer | In progress | Write "Primary" Content Pages: (See Content Checklist) | Sprint 25 | 2020-07-14 |  |  |  | 55%
7.2.1 | Content Writer | Complete | *About | Sprint 13 | 2020-01-28 | 2020-01-24 | Larry West |  | 100%
7.2.3 | Content Writer | In progress | *Work with US | Sprint 15 | 2020-02-25 |  | Kim M |  | 80%
7.2.4 | Content Writer | In progress | *Jobs and Careers | Sprint 15 | 2020-02-25 |  | Kim M |  | 80%
7.2.5 | Content Writer | In progress | *Internships and Fellowships (Residency programs) | Sprint 15 | 2020-02-25 |  | Kim M |  | 80%
7.2.6 | Content Writer | In progress | *Volunteer and Donate | Sprint 15 | 2020-02-25 |  | Kim M |  | 80%
7.2.7 | Content Writer | Complete | *Home Page (includes: Health Svc Intro, Locations, Leadership, all Stories) | Sprint 15 | 2020-02-25 |  | Larry West |  | 100%
7.2.8 | Content Writer | In progress | *History | Sprint 14 | 2020-02-11 | 2020-02-10 | Larry West |  | 15%
7.2.9 | Content Writer | Not Started | *Health Services - From Playbook (Complete System Services from 95 list) | Sprint 25 | 2020-07-14 |  | Larry & Kim |  | 15% | CRITICAL PATH ITEM
7.2.10 | Content Writer | Not Started | *Faclity Pages Intro | Sprint 17 | 2020-03-24 | 2020-02-21 | Larry & Kim |  | 0%
7.2.11 | Content Writer | Not Started | *Contact_Us | Sprint 19 | 2020-04-21 | 2020-02-22 | Larry & Kim |  | 0% | Top task page - System Specific
7.3 | Copy Editor | In progress | Copy Editing and Load content to Drupal | Sprint 27 | 2020-08-11 |  |  |  | 26%
7.3.1 | Copy Editor | In progress | *About | Sprint 17 | 2020-03-24 |  | Lou C |  | 50%
7.3.2 | Copy Editor | In progress | *Work with US | Sprint 17 | 2020-03-24 |  | Lou C |  | 50%
7.3.3 | Copy Editor | In progress | *Jobs and Careers | Sprint 17 | 2020-03-24 |  | Lou C |  | 50%
7.3.4 | Copy Editor | In progress | *Internships and Fellowships (Residency programs) | Sprint 17 | 2020-03-24 |  | Lou C |  | 50%
7.3.5 | Copy Editor | In progress | *Volunteer and Donate | Sprint 17 | 2020-03-24 |  | Lou C |  | 50%
7.3.6 | Copy Editor | Not Started | *Home Page (includes: Health Svc Intro, Locations, Leadership, all Stories) | Sprint 18 | 2020-03-24 |  | Lou C |  | 10%
7.3.7 | Copy Editor | In progress | *History | Sprint 17 | 2020-02-11 | 2020-02-10 | Lou C |  | 0%
7.3.8 | Copy Editor | Not Started | *Health Services - From Playbook (Complete System Services from 95 list) | Sprint 27 | 2020-08-11 |  | TBD |  | 0% | CRITICAL PATH ITEM
7.3.9 | Copy Editor | Not Started | *Faclity Pages Intro | Sprint 19 | 2020-04-21 |  | TBD |  | 0%
7.3.10 | Copy Editor | Not Started | *Contact_Us | Sprint 20 | 2020-05-05 |  | TBD |  | 0%
7.4 | UAT | Not Started | PAO and Product Lead - UAT review content pages | Sprint 27 | 2020-08-11 |  |  |  | 0%
7.4.1 | Public Affairs Office | Not Started | *About | Sprint 17 | 2020-03-24 |  | *Site Spec. |  | 0%
7.4.2 | Public Affairs Office | Not Started | *Work with US | Sprint 17 | 2020-03-24 |  | *Site Spec. |  | 0%
7.4.3 | Public Affairs Office | Not Started | *Jobs and Careers | Sprint 17 | 2020-03-24 |  | *Site Spec. |  | 0%
7.4.4 | Public Affairs Office | Not Started | *Internships and Fellowships (Residency programs) | Sprint 17 | 2020-03-24 |  | *Site Spec. |  | 0%
7.4.5 | Public Affairs Office | Not Started | *Volunteer and Donate | Sprint 17 | 2020-03-24 |  | *Site Spec. |  | 0%
7.4.6 | Public Affairs Office | Not Started | *Home Page (includes: Health Svc Intro, Locations, Leadership, all Stories) | Sprint 18 | 2020-03-24 |  | *Site Spec. |  | 0%
7.4.7 | Public Affairs Office | Not Started | *History | Sprint 17 | 2020-02-11 |  | *Site Spec. |  | 0%
7.4.8 | Public Affairs Office | Not Started | *Health Services - From Playbook (Complete System Services from 95 list) | Sprint 27 | 2020-08-11 |  | *Site Spec. |  | 0% | CRITICAL PATH ITEM
7.4.9 | Public Affairs Office | Not Started | *Faclity Pages Intro | Sprint 19 | 2020-04-21 |  | *Site Spec. |  | 0%
7.4.10 | Public Affairs Office | Not Started | *Contact_Us | Sprint 20 | 2020-05-05 |  | *Site Spec. |  | 0%
7.5 | Copy Editor | Not Started | Drupal final updates and archive of template/copy in Sharepoint | Sprint 28 | 2020-08-17 |  | TBD |  | -
8 | Load-Content | Not Started | Load - Business Data and Intro Content - (Global/Local mix)
8.1 | Load-Content | Not Started | Creation and Association of System HEALTH SERVICES pages (System-Facility) | Sprint 26 | 2020-07-28 |  | TBD | 72 | 0%
8.1.1 | Load-Content | Not Started | *Lebannon and Altoona | Sprint 23 | 2020-06-16 |  | TBD | 72 | 0%
8.1.2 | Load-Content | Not Started | *Butler and Coatesville | Sprint 24 | 2020-06-30 |  | TBD | 72 | 0%
8.1.3 | Load-Content | Not Started | *Erie and Wilkes-Barre | Sprint 25 | 2020-07-24 |  | TBD | 72 | 0%
8.1.4 | Load-Content | Not Started | *Philadelphia, PA & Wilmington, DE | Sprint 26 | 2020-07-28 |  | TBD | 72 | 0%
8.2 | Load-Content | Not Started | Load of information into Facility Pages, Creation of Accordions, links to outside info | Sprint 22 | 2020-06-02 |  | TBD | 58,73 | 0%
8.2.1 | Load-Content | Not Started | *Altoona & Butler Facilities | Sprint 19 | 2020-04-21 |  | TBD | 58, 73 | 0%
8.2.2 | Load-Content | Not Started | *Coatesville & Erie Facilities | Sprint 20 | 2020-05-05 |  | TBD | 58, 73 | 0%
8.2.3 | Load-Content | Not Started | *Lebannon and Philadelpia Facilities | Sprint 21 | 2020-05-19 |  | TBD | 58, 73 | 0%
8.2.4 | Load-Content | Not Started | *Wilkes-Barre and Wilmington Facilities | Sprint 22 | 2020-06-02 |  | TBD | 58, 73 | 0%
8.3 | Load-Content | Not Started | Load information for ALL - Caregiver Pages, per system from Analytics (HS & CareGiver) | Sprint 26 | 2020-07-28 |  | TBD | 59, 72 | 0%
8.3.1 | Load-Content | Not Started | *Altoona & Butler Facilities | Sprint 23 | 2020-06-16 |  | TBD | 59, 72 | 0%
8.3.2 | Load-Content | Not Started | *Coatesville & Erie Facilities | Sprint 24 | 2020-06-30 |  | TBD | 59, 72 | 0%
8.3.3 | Load-Content | Not Started | *Lebannon and Philadelpia Facilities | Sprint 25 | 2020-07-14 |  | TBD | 59, 72 | 0%
8.3.4 | Load-Content | Not Started | *Wilkes-Barre and Wilmington Facilities | Sprint 26 | 2020-07-28 |  | TBD | 59, 72 | 0%
8.4 | Load-Content | Not Started | Load information for All - Top Task and Action Button Pages (9 Total) | Sprint 26 | 2020-07-28 |  | TBD |  | 0%
8.4.1 | Load-Content | Not Started | *Altoona & Butler Facilities | Sprint 23 | 2020-06-16 |  | TBD | 60 | 0%
8.4.2 | Load-Content | Not Started | *Coatesville & Erie Facilities | Sprint 24 | 2020-06-30 |  | TBD | 60 | 0%
8.4.3 | Load-Content | Not Started | *Lebannon and Philadelpia Facilities | Sprint 25 | 2020-07-14 |  | TBD | 60 | 0%
8.4.4 | Load-Content | Not Started | *Wilkes-Barre and Wilmington Facilities | Sprint 26 | 2020-07-28 |  | TBD | 60 | 0%
9 | 508/Accessability | Not Started | QA: - Accessability, Content, and 508 acceptance testing
9.1 | 508/Accessability | In progress | Content language review - Audit of plain language, voice, and standardization
9.2 | 508/Accessability | Not Started | Accessability and 508 acceptance testing
9.2.1 | 508/Accessability | Not Started | *Altoona
9.2.2 | 508/Accessability | Not Started | *Butler
9.2.3 | 508/Accessability | Not Started | *Coatesville
9.2.4 | 508/Accessability | Not Started | *Erie
9.2.5 | 508/Accessability | Not Started | *Philadelphia
9.2.6 | 508/Accessability | Not Started | *Wilkes-Barre
9.2.7 | 508/Accessability | Not Started | *Wilmington
9.3 | Bug Fix | Not Started | Resolve issues detailed in Content/Accessability/508 testing
10 | UAT | Not Started | Cross-check contact phone numbers on contact-us against workbooks & enter content
11 | Build Optimization | Not Started | Optimation testing on VISN-19 - Montana System
11.1 | Build Optimization | Not Started | Automation of Hardened Content Page testing
11.1.1 | Build Optimization | Not Started | Confirm Menu and all pages are in place and working and accessible
117
118
119
120
Formulas:
Target Date = LARGE([Target Date, row below]:F113,1)

## Page_Content_Type
No of Pgs | Level | Page # | Page Title | Root | Content Location | Content Type: | Content Types/Future Actions:
1 | 0 | 1 | System-Name Page (Home) | va.gov/ | /"system"-health-care/ | Detail | WYSIWYG | Content for: Location, Health Services, Leadership, Stores, Events, News Releases, Link Teasers
2 | 1 | 2 | /health-services | /"system"-health-care/ | /System-health-care/(Health-services intro) | API/DataLoad | Intro on Home, Load Content
3 | 1 | 3 | /locations | /"system"-health-care/ | locations intro | API/DataLoad | Associated by linking Facilities, Intro on Home
4 | 1 | 4 | /Events | /"system"-health-care/ | Events-intro | API/DataLoad | Intro on Home, Load Content
5 | 1 | 5 | /Stories | /"system"-health-care/ | Featured-Stories Intro | API/DataLoad | Intro on Home, Load Content
6 | 1 | 6 | /News Releases | /"system"-health-care/ | news-release intro | API/DataLoad | Intro on Home, Load Content
7 | 1 | 7 | /about-us | /"system"-health-care/ | /about-us/ | Detail | WYSIWYG
8 | 1 | 8 | /work-with-us | /"system"-health-care/ | /work-with-us/ | Detail | WYSIWYG
9 | 1 | - | /Programs |  |  | Detail | Not a Required Page
10 | 1 | - | /Research |  |  | Detail | Not a Required Page
11 | 1 | 9 | /make-an-Appointment | /"system"-health-care/ | /make-an-appointment | Detail | TOP TASK
12 | 1 | 10 | /register-for-care | /"system"-health-care/ | /register-for-care | Detail | TOP TASK
13 | 1 | 11 | /billing-insurance | /"system"-health-care/ | /billing-insurance | Detail | TOP TASK
14 | 1 | 12 | /contact-us | /"system"-health-care/ | /contact-us | Detail | TOP TASK
15 | 1 | 13 | /dav-vans-transporation-for veterans | /"system"-health-care/ | /dav-vans-transporation-for veterans | Detail | Migrate
16 | 1 | 14 | /medical-records | /"system"-health-care/ | /medical-records | Detail | TOP TASK
17 | 1 | 15 | /operating-status | /"system"-health-care/ | /operating-status | API-Link | API link to database/program
18 | 1 | 16 | /pharmacy | /"system"-health-care/ | /pharmacy | Detail | TOP TASK
19 | 1 | 17 | /policies | /"system"-health-care/ | /policies | Detail | Migrate
20 | 2 | 18 | /Caregiver | /health-services | /Caregiver | Detail | Health Service Program
21 | 2 | 19 | /Homeless Veteran Care | /health-services | /Homeless Veteran Care | Detail | Health Service Program
22 | 2 | 20 | /LGBT-Veteran-Care | /health-services | /LGBT-Veteran-Care | Detail | Health Service Program
23 | 2 | 21 | /Mental Health-care | /health-services | /Mental Health-care | Detail | Health Service Program
24 | 2 | 22 | /Minority Veteran Care | /health-services | /Minority Veteran Care | Detail | Health Service Program
25 | 2 | 23 | /Patient-advocates (Customer Service) | /health-services | /Patient-advocates (Customer Service) | Detail | (Patient Advocate Listing)
26 | 2 | 24 | /Returning-service-member | /health-services | /Returning-service-member | Detail | Health Service Program
27 | 2 | 25 | /Suicide-prevention | /health-services | /Suicide-prevention | Detail | Health Service Program
28 | 2 | 26 | /Women-veteran-care | /health-services | /Women-veteran-care | Detail | Health Service Program
29 | 2* | * | /Facility_Pages* | /Locations/ | /Facility_ | Facility | Detail with Acordions
30 | 2 | - | /Events |  |  |  | Migrate
31 | 2 | - | /Stories |  |  |  | Migrate
32 | 2 | - | /News Releases |  |  |  | Migrate
33 | 2 | 27 | /Mission-Vision | /about |  | Detail | Migrate
34 | 2 | 28 | /History | /about |  | Detail | WYSIWYG
35 | 2 | 29 | /Leadership | /about |  | API/DataLoad | Intro on Home, Load Content
36 | 2 | 30 | /Performance | /about |  | API-Link | API link to database/program
37 | 2 | 31 | /jobs-careers | /work-with-us |  | Detail | WYSIWYG
38 | 2 | 32 | /volunteer-or-donate | /work-with-us |  | Detail | WYSIWYG
39 | 2 | 33 | /internship-fellowship | /work-with-us |  | Detail | WYSIWYG
40 | Add | - | /doing-business-with-us | /work-with-us |  |  | WYSIWYG
41 | Add | - | /Program-names | /Programs |  |  | WYSIWYG
42 | Add | - | /research-names | /research |  |  | WYSIWYG
43
44
45

## Req.HealthSvcs_chklst
VISN-4 Site:
(if pages exist in Legacy sites?) | Caregiver Support | Homeless Vetean Care | LGBT-Veteran-Care | Mental Health-care | Minority Veteran Care | Patient-advocates | Returning-service-member | Suicide-prevention | Women-veteran-care | Notes:
Altoona, PA | X | X | X | * | X | - | X | X | X
Butler, PA | X | X | X | X | X | - | X | X | X
Coatesville, PA | X | X | X | X | X | - | X | X | X
Philadelphia, PA | X | X | X | X | *** | - | X | X | X
Erie, PA | X | X | X | X | *** | - | X | X | X | Mental Health=Behavioral Health
Lebanon, PA | X | X | X | X | X | X | X | X | X | X = PA, FOUND with NO content.
Wilkes-Barre, PA | X | X | X | X | *** | - | X | X | X
Wilmington, DE | X | X | X | X | *** | - | X | X | X
LEGEND:
| X | Page exists in Legacy Site
Story has been created in ZenHub
| * | Link to mentalhealth.va.gov
| ** | Link to va.gov/HEALTH/patientadvocate/
| *** | Link to va.gov/centerformnorityveterans/
| X | Page exists, Hyperlink provided on cell

## Data
Workstream | Status
Drupal/CMS | Not Started
Backend Engineer | Ice Box
Business Analytics | Back Log
Content Writer | In progress
Copy Editor | On Hold
Front End Eng. | Blocker
Scrum Master | Complete
508/Accessability | Cancelled
Bug Fix
Beta Launch
Build Optimization
Google Analytics
UAT
Public Affairs Office
VSP Facilities
Migration
Load-Content