## Payment history
My VA
Sprints | Payment info updates
Sprint 58 (10/6 - 10/19) | Meet with edu team
Sprint 59 (10/20 - 11/2) | Scope project PM: Schedule discussion on discovery findings for end of sprint Design: Discovery -- determine the direction of work
Sprint 60 (11/3- 11/16) | Determine next steps PM: Nothing Design: Present findings; work with team to determine next steps; FE: Technical discovery, if needed
Sprint 61 (11/17 - 11/30) | Project pivot to payment information PM: Collab kickoff Design: Additional payment info discovery; Meet with debt team to understand feature; preliminary designs; Define scope FE: Do we need any technical discovery now? I don't think so.
Sprint 62 (12/1 - 12/14) | Design intent - Design; Design intent - Technical discovery
Sprint 63 (12/15 - 12/28) | Research/midpoint review planning - Midpoint review planning, including starting to put together list of test cases - Finish design if not already done - Technical discovery
Sprint 64 (12/29 - 1/11) | Midpoint review; Research planning - Hold midpoint review - Research planning/convo guide/ recruit; If not done, finish design on how to handle "benefits you might be interested in"; if done, create FE tickets - Prototype build on payment info
Sprint 65 (1/12 - 1/25) | Continue build - Conduct and summarize research - Update documentation if time - Updates from user research (may go into the following sprint depending on updates) - Determine what, if anything, still needs to happen with FE build, and complete build
Sprint 66 (1/26 - 2/8) | Finish build - PM: Do we need UAT? - Design for any updates coming out of testing; Onboard Angela - Request QA depending where build is at -- Are we ready for QA? - Update documentation if needed - Finish build
Sprint 67 (2/9 - 2/22) | Liz to transition My VA work over to Angela; All final updates ahead of QA - PM: Review QA test cases and make sure they are accurate given any updates from user testing - Team does informal click through of the feature to make sure it is ready for QA - Design: Contact center guide; maybe My VA sketch file clean up - FE: Error states; user testing updates
Sprint 68 (2/23 - 3/8) | QA - PM: Analytics request (Look at what we set for KPIs to give Heather details on what she should include in this request; add yo exisiting My VA dashboard) - QA (doesn't need to be day 1 of the sprint) - UAT planning
Sprint 69 (3/9 - 3/22) | PRE LAUNCH!! This assumes call center guide is all done. - PM: Make sure analytics updates get implemented; Put together launch plan; Prep for staging review; Hold staging review if we don't need to do any significant updates from QA (can be towards the end of the sprint if necessary) - Design: Updates from QA, if applicable - FE: Updates from QA if applicable; Prep for privacy and security review - BE: Prepare any technical diagrams or other documentation needed for the privacy and security review
Sprint 70 (3/23 - 4/5) | Because of BGS delays… - QA updates - Finish prep and hold staging review - Privacy and security review - UAT go/no-go - Start recruiting for UAT?
Sprint 71 (4/6 - 4/19) | Pre-launch prep - Updates from the staging review, if necessary - If we are good to go, recruit and hold UAT - PM: During UAT, make sure we can see analytics come in - Privacy and security review (ticket open and pending review)
Sprint 72 (4/20 - 5/3) | PM Monitor launch to 25% Monitor launch to 50% For V2 updates: Collab cycle kickoff For V2 updates: Collab cycle design intent FE Flip feature flag for launch to 25% Flip feature flag for launch to 50% Design For V2 updates: Collab cycle design intent
Sprint 73 (5/4 - 5/17) | Angela is out 5/3 - 5/10 (here 5 days this sprint) V1: Launch to 100% V2: Updates coming out of design intent (assuming we held design intent in sprint 72)
Sprint 74 (5/18 - 5/31) | V1: Observe stats after launch V2: Design updates if they didn't happen or werent't finished in sprint 73; Sitewide content/IA review (collab cycle); Research planning
Sprint 75 (6/1 - 6/14) | On hold for other work
Sprint 76 (6/15 - 6/28) | Design on hold while we prep for midpoint review PM: Midpoint review prep, including starting a preliminary list of QA tasks; Hold midpoint review by the end of the sprint if possible Design: On hold bc of midpoint review
Sprint 77 (6/29 - 7/12) | Updates from midpoint review;
Sprint 78 (7/13 - 7/26) | Another midpoint?; Research recruiting
Sprint 79 (7/27 - 8/9) | Research sessions/write-up/updates | Rough plan from here on -- plan may need adjustment
Sprint 80 (8/10 - 8/23) | Design -- FE documentation for build
Sprint 81 (8/24 - 9/6) | FE build; Contact center guide updates;
Sprint 82 (9/7 - 9/20) | FE build; QA request if we are ready; UAT planning
Sprint 83 (9/21 - 10/4) | FE build; QA go/no-go; Release plan;
Sprint 84 (10/5 - 10/18) | Design updates to account for existing copay functionality; FE implementation when those changes are ready; QA; Updates from QA; Analytics request; Staging review prep; do we need a privacy review?; Privacy review prep
Sprint 85 (10/19 - 11/1) | QA; Updates; privacy review
Sprint 86 (11/2 - 11/15) | QA updates; If time, staging review; Staging review updates; Stretch goal is UAT kickoff and recruiting
Sprint 87 (11/16 - 11/29) | UAT go/no-go; UAT recruiting; UAT if time; Launch to 25%
Sprint 88 (11/30 - 12/13) | Launch to 50%; Launch to 100% (if time); Update Documentation
Sprint 89 (12/14 - 12/27) | Onboard new team; Launch to 100% if not already done; Documentation
Sprint 1 (1/4 - 1/17) | Onboard new team; Update Payment V2 post-launch stats (1 month)
Sprint 2 (1/18 - 1/31) | None
Sprint 3 (2/1 - 2/14) | Update Payment V2 post-launch stats (2 months)

## My VA Audit
My VA: Audit
Sprints | Planned tasks
Sprint 69 (3/9 - 3/22) | Research review; Discuss next steps
Sprint 70 (3/23 - 4/5) | Design: - Audit nametag - Audit claims & appeals - Exploration for showing amount in debts & copays section/not showing debt and copay info as a notification style.
Sprint 71 (4/6 - 4/19) | Design: - Audit health care - Audit benefit payments and debts - Audit applications in progress - If time, regroup with Samara/AJ (or Heather if she is still here) on existing states
Sprint 72 (4/20 - 5/3) | On hold due to other work
Sprint 73 (5/4 - 5/17) | On hold due to other work
Sprint 74 (5/17 - 5/31) | Design: - Come up with use cases
Sprint 75 (6/1 - 6/14) | PM: Collab cycle kickoff Design: Assuming use cases are done, outline design updates and start on changes. | - Start streamlining states for each section - Start with nametag and payment info (since we are working on it anyway) - Each section should always appear on the page - Each section should have the following: loadin; blank state(s); content state(s); error state(s). Note: the nametag might be a little different, as there's never a totally blank state, and we don't show big error alerts for content we can't load.
Sprint 76 (6/15 - 6/28) | PM: None Design: Design for Claim status & health care sections
Sprint 77 (6/29 - 7/12) | On hold due to other work | NOTE: Consider smaller, iterative launches
Sprint 78 (7/13 - 7/26) | On hold due to other work
Sprint 79 (7/27 - 8/9) | On hold due to other work
Sprint 80 (8/10 - 8/23) | On hold due to other work
Sprint 81 (8/24 - 9/6) | PM: None Design: Design for Claim status & health care sections
Sprint 82 (9/7 - 9/20) | Design: Nametag and apply for benefits;
Sprint 83 (9/21 - 10/4) | Review all designs with team; Design intent; Updates from design intent; Preliminary research conversations -- do we want to test in code?
Sprint 84 (10/5 - 10/18) | Finish FE documentation; Put together FE tickets; Start FE build if tickets are ready
Sprint 85 (10/19 - 11/1) | FE build; Conversation guide prep; midpoint review
Sprint 86 (11/2 - 11/15) | FE build; Design updates from midpoint review
Sprint 87 (11/16 - 11/29) | Finish FE build; Research recruiting; PM: Analytics planning; Use case documentation for QA
Sprint 88 (11/30 - 12/13) | FE: Finish FE; PM: Analytics request/review; Continue/Finish QA use cases
Sprint 89 (12/14 - 12/27) | On hold due to contract switch (pending team); Onboard any new team members; QA prep if AJ is still here?
Sprint 1 (1/4 - 1/17) | Research recruiting; Finalize QA prep
Sprint 2 (1/18 - 1/31) | Conduct research; Research write-up
Sprint 3 (2/1 - 2/14) | FE changes as needed; Submit QA request for next sprint; Where are we at with analytics?
Sprint 4 (2/15 - 2/28) | QA go/no-go; QA; Updates from QA; Contact center guide updates; FE to implement analytics updates
Sprint 5 (3/1 - 3/14) | Staging and privacy review prep; UAT prep
Sprint 6 (3/15 - 3/28) | Staging and privacy review; UAT recruiting
Sprint 7 (3/29 - 4/11) | UAT; Launch to 25% & 50%
Sprint 8 (4/12 - 4/25) | Launch to 100%; DOCUMENTATION SPRINT
Sprint 9 (4/26 - 5/9)
Sprint 10 (5/10 - 5/23)

## On-site notifications
On-site notifications V2
Sprints | Q1 goals: Intake process, backlog inventory; add 1 -2 new notifications | Q1 goals, if time/people: Notification center discovery | Notes
Sprint 1 (1/4 - 1/17) | Internal team kickoff (not collab cycle); Discovery; Start scoping V2; Come up with V2 plan - Talk to each other to wrap our heads around what this effort could be - Talk to VANotify about their intake process - Figure out what relevant notifications VANotify supports now - Determine development level for adding new notifications - Discuss notification center concept: What do we need to answer to determine if this is the right path? How do we do this without being too leading in research?
Sprint 2 (1/18 - 1/31) | Finalize Scope of work - Set up meeting to talk to VANotify about notification questions - Set up meeting to talk about VANotify intake process
Sprint 3 (2/1 - 2/14) | Collab kickoff/Design/FE discovery - PM: Collab cycle kickoff ticket; Finalize intake process? - Design: Start on copy for new notification(s); Design updates for My VA; Complete research plan - FE & BE: Technical discovery (FE & BE) -- How hard is implementing new notification design? How much FE work is required for a new notification if we don't update the design? Is there any BE work involved?
Sprint 4 (2/15 - 2/28) | Finalize intake process/ Design intent - PM: Use VANotify spreadsheet to create My VA inventory/backlog for notifications to add. - Design: Finalized design/copy for notifications and My VA updates; Design intent Create research convo guide; Kick off recruiting - FE: Implement new notifications with old designs
Sprint 5 (3/1 - 3/14) | User testing - PM: QA use cases; Request QA for next sprint; Assuming FE build is done, request analytics implementation - Design: User testing for My VA updates; Write-up - FE: Add new notification page (assuming we have one) - PM/FE/VANotify: Test new onsite notifications | Research: Notification center discovery research plan
Sprint 6 (3/15 - 3/28) | More time for FE build? User testing updates | Research: Notification center discovery convo guide; Start stakeholder interviews
Sprint 7 (3/29 - 4/11) | QA QA: Complete QA FE: Make updates, if needed | Research: Finish stakeholder interviews; write-up | End of Q1 - 3/31/23
Sprint 8 (4/12 - 4/25) | Staging review; Privacy review; Team does prod testing (no UAT); Make sure analytics are implemented | Continue research if we determine there's other research needed
Sprint 9 (4/26 - 5/9) | Launch to 25%; Launch to 50%
Sprint 10 (5/10 - 5/23) | Launch to 100% | Collab kickoff? Ready to start on designs?
Sprint 11 (5/24 - 6/6)
Sprint 12 (6/7 - 6/20)
Sprint 13 (6/21 - 7/4) |  |  | End of Q2 - 6/30/23
Sprint 14 (7/5 - 7/18)
Sprint 15 (7/19 - 8/1)
Sprint 16 (8/2 - 8/15)
Sprint 17 (8/16 - 8/29)
Sprint 18 (8/30 - 9/12) |  | Goal: launch notification center in nav | End of Q3 - 8/31/23

## Update claim status integration
Update claim status integration - Have Adam do this work if Allison is too busy with onsite notifications
Sprints |  | Notes
Sprint 2 (1/18 - 1/31) | On hold until we have someone available
Sprint 3 (2/1 - 2/14) | On hold until we have someone available
Sprint 4 (2/15 - 2/28) | On hold until we have someone available
Sprint 5 (3/1 - 3/14) | On hold until we have someone available
Sprint 6 (3/15 - 3/28) | PM: Collab cycle kickoff FE: Discovery; Effort scoped by end of sprint BE: Discovery (likely does not need any backend updates, but Tom should confirm)
Sprint 7 (3/29 - 4/11) | FE implementation
Sprint 8 (4/12 - 4/25) | FE implementation/testing; Do we need analytics updates?
Sprint 9 (4/26 - 5/9) | QA; Bug fixes
Sprint 10 (5/10 - 5/23) | Privacy review; Launch to 25%
Sprint 11 (5/24 - 6/6) | Launch to 50%; Launch to 100%
Sprint 12 (6/7 - 6/20)
Sprint 13 (6/21 - 7/4)
Sprint 14 (7/5 - 7/18)
Sprint 15 (7/19 - 8/1)
Sprint 16 (8/2 - 8/15)
Sprint 17 (8/16 - 8/29)
Sprint 18 (8/30 - 9/12)

## LT planning by person
Long-term planning by person
| Angela (Design) | Liz (Design) | Florence (Design) | Allison (FE) | Adam (FE) | Tom (BE)
Sprint 1 (1/4 - 1/17) | My VA Audit | Notification preferences | Onboarding | N/A | Profile accessibility | Direct deposit EVSS > Lightouse
Sprint 2 (1/18 - 1/31) | My VA Audit | Notification preferences | Military info research | Onboarding | Profile accessibility | Direct deposit EVSS > Lightouse
Sprint 3 (2/1 - 2/14) | Onsite notifications | Notification preferences | Military info research | Onsite notifications | Profile accessibility | Direct deposit EVSS > Lightouse
Sprint 4 (2/15 - 2/28) | Onsite notifications | Logged in nav research | Military info research | Onsite notifications | Profile accessibility | Direct deposit EVSS > Lightouse
Sprint 5 (3/1 - 3/14) | Onsite notifications | Logged in nav research | Notification center discovery? | Onsite notifications | Profile accessibility | Direct deposit EVSS > Lightouse
Sprint 6 (3/15 - 3/28) | Onsite notifications | Logged in nav research | TBD | Onsite notifications | My VA: Update claims integration | Direct deposit EVSS > Lightouse
Sprint 7 (3/29 - 4/11) | Onsite notifications | TBD | TBD | Onsite notifications | My VA: Update claims integration | Direct deposit EVSS > Lightouse
Sprint 8 (4/12 - 4/25) | Onsite notifications | TBD | TBD | TBD | My VA: Update claims integration | TBD
Sprint 9 (4/26 - 5/9) | Onsite notifications | TBD | TBD | TBD | My VA: Update claims integration | TBD
Sprint 10 (5/10 - 5/23) | Onsite notifications | TBD | TBD | TBD
Sprint 11 (5/24 - 6/6)
Sprint 12 (6/7 - 6/20)
Sprint 13 (6/21 - 7/4)
Sprint 14 (7/5 - 7/18)
Sprint 15 (7/19 - 8/1)
Sprint 16 (8/2 - 8/15)
Sprint 17 (8/16 - 8/29)
Sprint 18 (8/30 - 9/12)

## Task list for projects
General project tasks (updated April 2021)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings