## Accessibility updates
Accessibility updates
Sprints | Planned tasks | Notes
Sprint 81 (8/24 - 9/6) | Christina to go through tickets in icebox to see if they relate to existing list Liz - Regroup with accessibility about completing a full audit; Set up a meeting (?)
Sprint 82 (9/7 - 9/20) | Assuming accessiility has completed a full audit: - Go through each item as a team, rate severity and complexity, get tickets created - Prioritize tickets - Talk about potential solutions - Collab kickoff - Begin design
Sprint 83 (9/21 - 10/4) | Continue design; Talk about build and usability testing plan (will need to happen in code)
Sprint 84 (10/5 - 10/18) | Research write-up; Determine next steps; Continue any FE tickets that are fully groomed; Determine if Christina can research another issue
Sprint 85 (10/19 - 11/1) | TBD based on Liz and Christina's work for this sprint; Continue FE work if it exists
Sprint 86 (11/2 - 11/15) | Any general FE tickets, or tickets based on Liz's and Christina's work, if applicable; Christina -- updates to personal info based on nametag recommendations and move on to account settings work if time, if time; Liz -- Finish any notification-related updates, if applicable, move on to address validation work, if time
Sprint 87 (11/16 - 11/29) | Any general FE tickets, or tickets based on Liz's and Christina's work, if applicable; Christina -- Continue on work from last sprint, if applicable, or start new work; Liz -- Continue on work from last sprint, if applicable, or start new work
Sprint 88 (11/30 - 12/13) | FE to implement any tickets Christina and Liz have ready; Liz and Christina to update documentation based on newly launched work
Sprint 89 (12/14 - 12/27) | Onboard new team
Sprint 1 (1/4 - 1/17) | Onboard new team members; Personal info updates
Sprint 2 (1/18 - 1/31) | Account settings updates; Semantic lists discovery; Potentially pull in other small tickets depending on LOE on these larger tickets
Sprint 3 (2/1 - 2/14) | Address validation updates; Review what else we still have outstanding and add tickets to sprint
Sprint 4 (2/15 - 2/28) | Add mobile number updates
Sprint 5 (3/1 - 3/14) | Once all updates are done, have Adam remove any feature flags we no longer need (tickets not created yet; I know we have at least one for account security; Ask Adam if there are others)
Sprint 6 (3/15 - 3/28)
Sprint 7 (3/29 - 4/11)
Sprint 8 (4/12 - 4/25)
Sprint 9 (4/26 - 5/9)
Sprint 10 (5/10 - 5/23)

## Migrate direct deposit to LH
Direct deposit for comp & pen: Migrate from EVSS > Lighthouse
Sprints | Planned tasks | Notes
Sprint 89 (12/14 - 12/27) | Initial conversations with Lighthouse; Potentially start tech discovery
Sprint 1 (1/4 - 1/17) | BE technical discovery; Scope project with Tom; Collab cycle kickoff
Sprint 2 (1/18 - 1/31) | BE: Sandbox access and configuration; Build Client Authentication; Review existing code with Benefits Team
Sprint 3 (2/1 - 2/14) | Tom on PTO 2/6 - 2/10 BE: Migrate GET Direct Deposit Info;
Sprint 4 (2/15 - 2/28) | BE: Migrate POST Direct Deposit Info; Create Comp and Pen Controller; Review changes with Mobile App Team PM: QA planning; QA request
Sprint 5 (3/1 - 3/14) | BE: Configure and Test Staging access; Vets-API Review with Adam; Integration Testing between FE and BE (Staging) FE: Adam to review with Tom; determine if we need any analytics changes Design: UAT planning
Sprint 6 (3/15 - 3/28) | BE: Update BE Documentation; Make any necessary changes coming out of QA QA: Run QA
Sprint 7 (3/29 - 4/11) | BE: Privacy and security review Design: Recruit for UAT; Run sessions
Sprint 8 (4/12 - 4/25) | Launch to 10%; Launch to 25%
Sprint 9 (4/26 - 5/9) | Launch to 50%; Launch to 100%
Sprint 10 (5/10 - 5/23)

## Notification prefs
Notification preferences: Ongoing work
Sprints | Planned tasks | Notes
Sprint 86 (11/2 - 11/15) | Liz: Initial thinking around whether we need to change our edit model on this page
Sprint 87 (11/16 - 11/29) | TBD based on what Liz came up with last sprint
Sprint 88 (11/30 - 12/13) | On hold due to contract ending
Sprint 89 (12/14 - 12/27) | Onboard new team
Sprint 1 (1/4 - 1/17) | Email research: Research plan, convo guide, create prototype
Sprint 2 (1/18 - 1/31) | Recruiting, Research
Sprint 3 (2/1 - 2/14) | Writeup and readout
Sprint 4 (2/15 - 2/28)
Sprint 5 (3/1 - 3/14)
Sprint 6 (3/15 - 3/28) | If Tom is available, start him on default send work. This is required in order for us to be able to remove the explicit opt-out radio button design we have now. | See #7 https://github.com/department-of-veterans-affairs/va.gov-team/blob/master/products/identity-personalization/profile/notification-preferences/discovery-and-research/default-send/july-2022-notes.md
Sprint 7 (3/29 - 4/11)
Sprint 8 (4/12 - 4/25)
Sprint 9 (4/26 - 5/9)
Sprint 10 (5/10 - 5/23)

## Logged in nav research
Generative logged-in IA/nav research
Sprints | Planned tasks | Notes
Sprint 1 (1/4 - 1/17) | Settle on scope; meet with Danielle and Dave; Determine what questions can be answered in each research effort so we can get them scoped and defined for folks; Liz to complete research review
Sprint 2 (1/18 - 1/31) | Mikki -- pull tool inventory and clean it up; Mikki pull some initial analytics; Medallia/call center review planning; Analytics planning;
Sprint 3 (2/1 - 2/14) | Complete Medallia/Call center review (Chante's team); Submit analytics questions to analytics team;
Sprint 4 (2/15 - 2/28) | User research planning; Complete analytics write-up (assumes we have all the information we need)
Sprint 5 (3/1 - 3/14) | User research recruiting; Run research
Sprint 6 (3/15 - 3/28) | Write up of user research; Begin final synthesis
Sprint 7 (3/29 - 4/11) | Final research write-up and share out
Sprint 8 (4/12 - 4/25) |  | Samara out -- how will this move forward while I'm gone?
Sprint 9 (4/26 - 5/9)
Sprint 10 (5/10 - 5/23)

## Military info research
Military info generative research
Sprints | Planned tasks | Notes
Sprint 1 (1/4 - 1/17) | Samara scopes this effort
Sprint 2 (1/18 - 1/31) | [Pending Florence's access to GH] Familiarize with VA.gov military info; Research plan; Convo guide (stretch goal) -- Remember to add ticket for Liz to provide support
Sprint 3 (2/1 - 2/14) | Determine if we need an analytics review (would require Florence to have GA access and enough expertise to navigate it); Research recruiting; Research | Should I deprioritize for notification center discovery?
Sprint 4 (2/15 - 2/28) | Write-up and readout
Sprint 5 (3/1 - 3/14)
Sprint 6 (3/15 - 3/28)
Sprint 7 (3/29 - 4/11)
Sprint 8 (4/12 - 4/25)
Sprint 9 (4/26 - 5/9)
Sprint 10 (5/10 - 5/23)

## Forms system updates
Forms system updates
Sprints | Planned tasks | Notes
Work on hold indefinitely

## LT profile planning
Long term planning until end of contract
Project | Sprint 82 (9/7 - 9/20) | Sprint 83 (9/21 - 10/4) | Sprint 84 (10/5 - 10/18) | Sprint 85 (10/19 - 11/1) | Sprint 86 (11/2 - 11/15)
Profile
Personal information revisions
Military reintegration with VA Profile
Notification preferences
Bad address indicator | Staging and privacy and security reviews; UAT recruiting | UAT | Launch; Documentation
Documentation updates | Personal info (team) | Updates ongoing | Updates ongoing | Updates ongoing
Accessibility audit/updates | Scoping/kickoff | Updates ongoing | Updates ongoing | Updates ongoing | Updates ongoing
Forms system updates
Direct deposit

## Task list for projects
General project tasks (updated April 2021)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings

## Profile_1095B work
1095B work rough estimate -- Work on hold until 2024
Sprints | Conservative estimate | Aggressive estimate
Sprint 79 (7/27 - 8/9) | Estimate 1095B work; Requirements gathering | Estimate 1095B work; Requirements gathering
Sprint 80 (8/10 - 8/23) | Kickoff (collab cycle); Design & content -- send to legal; | Kickoff (collab cycle); Design & content -- send to legal; Draft frontend docs
Sprint 81 (8/24 - 9/6) | Send design & content to 1095B team for legal review; Design intent; Updates from stakeholder feedback, if possible | Design intent (collab cycle); Updates based on legal/stakeholder feedback; Update frontend docs; Midpoint review prep
Sprint 82 (9/7 - 9/20) | Midpoint review prep; Usability testing prep | Usability testing prep; Midpoint review; Recruiting
Sprint 83 (9/21 - 10/4) | Midpoint review; Recruiting; Start testing? | Usability testing, Write up, Design updates
Sprint 84 (10/5 - 10/18) | Usability testing and research write up | Frontend build in VA.gov; Backend set up of confirmation email
Sprint 85 (10/19 - 11/1) | Design updates; frontend docs | E2E testing/QA
Sprint 86 (11/2 - 11/15) | Frontend build in VA.gov; Backend set up of confirmation email | Staging and privacy reviews (collab cycle)
Sprint 87 (11/16 - 11/29) | E2E testing/QA | Phased launch to 25%/50%/100%
Sprint 88 (11/30 - 12/13) | Staging and privacy reviews (collab cycle)
Sprint 89 (12/14 - 12/27) | Phased launch to 25%/50%/100%
Sprint 90 (12/28 - 1/10)