## Recommendations
UI element | Order in Report | Issue Severity | # p's w/issue | Issue | Recommentations from Research Report | Team Ideas & Discussion | Relevant Team(s) | Decision/Next Steps | Status | PW | S&D | DT | Fac | Ben | Sitewide Content/ IA | Design
header | 2 | high | 9 | looking for VA forms but not finding the Find a Form link in the footer | consider putting a Forms link into the header somewhere | Meg is open to making Forms prominent in the header. also part of search tools redesign--how to surface these other tools | Sitewide Content/IA and Design | Ryan might consider | [6 empty] | 1 | 1
header | 1 | medium | 10 | people looking for something (travel pay info) but not finding the Resources & support link in the footer | consider making it easier to find Resources & Support (e.g., could provide additional link in the header (i.e., "Resources" or "Help") or link to from content pages)--brainstorm ideas. | need to work on strategy for post-beta R&S. What do people think they would get from a "Resources" link? | Sitewide Content/IA and Design | Ryan might consider | [6 empty] | 1 | 1
header | 9 | medium | 3 | site search isn't used (or noticed?) by 1/3 of the people | consider adding a search box next to the word Search in the header and/or just above the "top 4" boxes. | Search & Discovery has an epic about moving around Search and improving its presentation. Megan working on designs Cindy recommends a comparison test w/a mocked up version of alternate version | Search & Discovery, Sitewide Content/IA, Design | epic already created. discuss w/group | will make a ticket to describe; discuss w/Sitewide team |  | 1 |  |  |  | 1 | 1
header | 10 | z low |  | site search queries scroll off the end of the box | consider making the search box wider |  | Search & Discovery, Sitewide Content/IA and Design | discuss w/group | Denise will make a ticket to describe it; discuss w/Sitewide team |  | 1 |  |  |  | 1 | 1
top 4 boxes | 3 | high | 8 | People spend so much time looking at links in the "top 4" boxes but not elsewhere on the home page | consider adding additional links and/or a "View more" link in each box. Additional links to consider are in other rows here. | could consider removing some existing links that aren't used--look at analytics to see what's being used and not. there's currently a limit of 5 links per box | Sitewide Content/IA (possibly Design if another visual presentation or need more links) | Ryan might consider | [6 empty] | 1 | 1
top 4 boxes | 8 | medium | 11 | can't find form to appoint a representative | Appoint representative (add to Disability box) |  | Sitewide Content/IA | discuss w/group (and show analytics) | [6 empty] | 1
top 4 boxes | 4 | medium | 5 | can't find travel pay reimbursement info | Travel pay reimbursement (add to Health care box and VA Benefits and Health Care megamenu under health care and/or disability) | travel reimbursement is not only for medical appointments but also for claim exams or compensation & pension exams, so maybe also need a link elsewhere Meg is looking at a financial "hub" for Veterans--maybe put a link there. but isn't going to exist for while, per discussion with Debt Team. Could check if can find via Google/SEO (search engine optimization) | Sitewide Content/IA, Digital Health Modernization team | discuss w/group (and show analytics) | [6 empty] | 1
top 4 boxes | 5 | medium |  | hard to find how to update direct deposit | Update direct deposit (add to Records box) | might combine this with change address link? part of your profile | Sitewide Content/IA + loop in Account Experience | discuss w/group (and show analytics) | [6 empty] | 1
top 4 boxes | 7 | medium |  | hard to find how to update dependents | consider adding link to update dependents from the Records box |  | Sitewide Content/IA | discuss w/group (and show analytics) | [6 empty] | 1
top 4 boxes | 6 | z low |  | hard to find medical records page | Medical records (add to the Health care box, in addition to Records) |  | Sitewide Content/IA, Digital Health Modernization team | discuss w/group (and show analytics) | [6 empty] | 1
top 4 boxes--font | 21 | medium | 1 | Font size in "top 4" boxes is too small for an older participant to read | Consider increasing the font size of the links in the "top 4" boxes from the current 16px to 19px, which is the current recommendation (though not required) for older users, per Josh Kim and our peers (including Gov.uk, NHS, Health Literacy Online), because many of our users are older. We could conduct more research on the VA.gov home page with people age 55-64 or older. | Ryan is open to doing this Public Websites would make any changes | Sitewide Content/IA, Design, Accessibility (in sitewide crew) | [7 empty] | 1 | 1
z other--banner alert | 19 | high | 3 | COVID banner alert on home page is annoying | Consider making the COVID banner alert on the home page dismissable (as it is on other content pages)--could be session-based instead of user-based | Public Websites would make any changes. on Public Websites backlog to drive. | Sitewide Content/IA, Design, Lauren Alexanderson (Health Crew Chief) and Danielle Thierry, Josh Tuscher | discuss w/group John will talk with Josh Tuscher about this John will invite Danielle to the sitewide mtg | [6 empty] | 1 | 1
z-other images | 12 | medium | 4 | didn't scroll down past the row of images | Consider moving the row of images down to the actual bottom of the page so it doesn't give a false "bottom of the page" signal in the middle of the page. | Ryan not sure this is a problem | Sitewide Content/IA, Design | [7 empty] | 1 | 1
z other--authentication | 24 | z low | 1 | didn't know about any non-texting options to do two-factor authentication for the VA | Consider adding an article to Resources and support about two-factor authentication. |  | Sitewide Content/IA (write an article) | [7 empty] | 1
z other--research | 25 | z low |  | the header wasn't widely used but could have additional links | Consider conducting further user research on the VA.gov header and potential redesigns on mobile and desktop (especially if add new links to Forms, Resources or Help) to make sure that the most useful links are visible and others are not. |  | Sitewide Content/IA, Design, Public Websites | [7 empty] | 1 | 1
| 7 |  |  | can't find how to update dependents | Consider adding a way to update dependents from the Family Member Benefits page | Sabrina is particularly interested in this recommendation | Sitewide Content/IA, Benefits and Memorials Team | discuss | plan to talk week of Jun 14 |  |  |  |  | 1
| 11 |  |  | search results not relevant | Is site search indexing all of the content accessible via Find a Form, Resources & support, and Find a VA Location? Should make sure they show up in the search results so we can ensure that we are returning all relevant results from VA.gov. | if Search & Discovery team needs help w/metadata, work w/Content team | Search & Discovery | recommendations shared and discussed | Denise already has an issue for this; there may be a problem to resolve |  | 1
| 13 |  |  | many people thought you could get proof of your VA income from View payment history | Consider making it possible to get proof of income from site searches for "income" or "proof of income" or "va income". | make this a best bet if figure out where to point them (benefit letters page?) | Search & Discovery | discuss after 6/8 readout | Denise will make a ticket; Cindy can fill in some of the research finding background |  | 1
| 13 |  |  | many people thought you could get proof of your VA income from View payment history | Consider making it possible to get proof of income in the form of benefit letters from the View payment history page |  | Benefits and Memorials Team | discuss | plan to talk week of Jun 14 |  |  |  |  | 1
| 14 |  |  | Find a Form search results not relevant | Work on improving the Find a Form search: | Marci is working on improvements w/Lighthouse team | Decision Tools | recommendations shared and discussed | covered in detailed points below |  |  | 1
| 15 |  |  | Find a Form search results not relevant | Remove articles and other helper words (e.g., "a", "the", "how do I") from search queries before searching. [SHOW SLIDE #30 from long reportout presentation] | Mark on the Lighthouse Forms API team is using a library that does this and more--ignores the words depending on the length of the search query | Decision Tools | recommendations shared and discussed. Cindy sent test cases to Marci | planned/in process--see on Staging < July 6 release |  |  | 1
| 16 |  |  | Find a Form search results not relevant | Search on only the first few words of a long search query | also will benefit from library--disregard extra words based on search query length | Decision Tools | recommendations shared and discussed | planned/in process--see on Staging < July 6 release |  |  | 1
| 17 |  |  | Find a Form search results not relevant | Provide typeahead suggestions for common search queries while entering a search query | Marci and John have talked about doing this, maybe in Q3 | Decision Tools | recommendations shared and discussed | will consider |  |  | 1
| 18 |  |  | Find a Form search results not relevant | Add some fixed links per search query (e.g., a search for "spouse" should return the form to add/update dependents) | Lighthouse Forms API has a new metadata field where you can add keywords that will also match the form when searching, so add "spouse" should be added to the dependent form (if it's in fact relevant). Also will add common abbreviations, too. Metadata needs to get added by the CMS team. | Decision Tools | Lighthouse API now has the new metadata field, so it just needs to be populated--work w/Lighthouse to do that | planned/in process |  |  | 1
| 20 |  |  | COVID banner alert on home page is annoying to screen reader user | accessibility specialist Josh Kim recommends making the alert less annoying to screen reader users by changing the current aria-live attribute from assertive (interrupts user actions) to polite, which tells the screen reader to wait until the user is done to announce updates. | Given that the banner alert isn't changing, is the behavior different with the polite vs. assertive attribute? Maybe need to test, get Josh and Angela's input. This is only for the COVID banner alert. Will it be dismissable? Other alerts, such as short-term maintenance alerts, maybe should stay assertive? | Public Websites | ticket already created. meet with Josh and Angela to learn more about this issue | need to discuss with Josh and Angela--Brian will schedule | 1
| 22 |  |  | Site search is hard to find while using a screen reader because have to look for a form | Consider revising the site search box to make it easier to find quickly while using a screen reader by coding search as a landmark role (per Josh Kim and Angela Fowler). | Does this affect anything else besides screen reader users? don't think so Do we know why we didn't consider doing this earlier? hadn't been flagged as an issue | Public Websites? Search & Discovery? | Public Websites/Search discuss and do--create a ticket, put Josh and Angela on to validate. | will make a ticket | 1 | 1
| 23 |  |  | Site search results didn't load due to JavaScript that didn't load | Investigate the JavaScript https://dap.digitalgov.gov/Universal-Federated-Analytics-Min.js?agency=VA that didn't load, causing a "your browser is out of date" error message instead of search results. Could watch the session recording to see browser and other details | PW can look into--get session recording and try to recreate the issue (p16: 14:29 - 17:30 when searched for "form claim representative") Kelson: checking to see if browser is old IE but no other browser | Public Websites | Public Websites investigate | create a ticket and put into our tech debt--check into code, which has old IE case Kelson will ask Nick and Marci re when/how often they've seen this error before. Also check into recent PR by Johnny on this code: https://github.com/department-of-veterans-affairs/content-build/pull/76 | 1
| 24 |  |  | Participant didn't know about any non-texting options to do two-factor authentication for the VA | See if it's possible to use to select a photo to authenticate like eBenefits does. Possible to authenticate via email? | they want to have facial recognition for authentication, which is where they're headed (so might not want to talk about anything else) | Identity team (under Account Experience--Kevin Hoffman is crew chief) | Cindy slacked Kevin on 6/11 to share w/Identity team | Kevin: looking at transitioning people to login.gov, which provides these options--not email but authentication app on phone or computer
| 26 |  |  | 2 of 12 participants didn't find "Find a VA Location" and instead used site search. One was successful (searched for “VA in Cincinnati OH”), but the other was not (searched for “Knoxville” and didn’t notice the clinic result amidst all of the cemetery results). |  | share location results w/Facilities team | Sitewide Content/IA, Design, Search & Discovery, Facilities | discuss w/group (after readout mtg on 6/8) | John working w/Dave Conlon and Michelle to add to type-ahead and best bets; existing ticket |  | 1 |  | 1 |  |  | 1
| 27 |  |  | site search for a location sometime didn't return VAMC's |  | for Type-Ahead, add VAMCs for relevant city searches with a Best Bet link | Search & Discovery, Facilities | recommendations shared and discussed | working w/Dave Conlon and Michelle to add to type-ahead and best bets; existing ticket is Establish Best Bets for all VAMC & Vet Center Locations #25534 |  | 1 |  | 1