## My VA
My VA redesign: Long term planning
Sprints | Planned tasks
Sprint 44 (3/24 - 4/6) | PM: Design: Finish design; Update My VA test cases; Talk to Trevor about assistive tech review FE: Continue build
Sprint 45 (4/7 - 4/20) | PM: Assist with call center guide; Thorough review of FE build; Submit analytics request Design: Start call center guide; Thorough review FE build; FE: Finish build
Sprint 46 (4/21 - 5/4) | PM: Hold go/no-go for QA; Request QA for this sprint; Finish call center guide; submit for call center review Design: Finish contact center guide; attend QA go/no-go FE: Final tickets; Attend QA go/no-go
Sprint 47 (5/5 - 5/18) | PM: Meet with analytics team if needed/available; begin filling out ticket for staging review; begin filling out ticket for privacy review Design: Accessibility tests for staging review; UAT research plan if not already done; UAT convo guide if not already done; post-launch planning, if time FE: Accessibility tests for staging review; Technical docs for privacy and security review; If time/needed, start on QA fixes QA: Conduct QA
Sprint 48 (5/19 - 6/1) | PM: Hold staging review; Submit privacy and security ticket; Meet with comms (Leslie Byford); Hold UAT go/no-go if dependencies allow Design: No tasks for redesign work. - Action items work: Discovery: how can we better elevate action items FE: QA fixes
Sprint 49 (6/2 - 6/15) | PM: UAT go/no-go Design: Tressa out 6/10 - 6/17 Attend UAT go/no-go; UAT recruiting** Don't schedule sessions until Tressa is back from leave - Action items work: Continue comparative analysis and other discovery tasks; Begin exploration of elevating action items FE: Any outstanding fixes if still needed
Sprint 50 (6/16 - 6/29) | PM: Make sure analytics are set up correctly. Design: Tressa's out until 6/16 - 6/18; back 6/21 Conduct UAT; Create tickets if there are issues - Action items work: Finish explorations and discuss with team; Determine method for testing; Plan research FE: Erik out 6/21 UAT fixes if necessary Stretch goals: If there are no fixes or anything needed from UAT, and if all analytics tracking is in place, feel free to hold the launch go/no-go and launch to 25% as soon as UAT is over!! If not, do that next sprint.
Sprint 51 (6/30 - 7/13) | PM: Launch go/no go; Monitor launch to 25%, 50% Design: - Action items work: Recruit for research; Conduct research FE: Launch to 25%; Launch to 50%
Sprint 52 (7/14 - 7/27) | PM: Monitor launch to 100%; Reach out to Leslie Byford and let her know launch is complete Design: - Action items work: Summarize research FE: Launch to 100%
Sprint 53 (7/28 - 8/10) | PM: Continued monitoring of analytics; Submit for full accessibility review; Talk to Kevin about whether we should start scoping out action items MVP based on Tressa's research (he may need to be involved in this)
Sprint 54 (8/11 - 8/24) | PM: Post-launch checkin with VSP; Action items MVP tasks TBD
Sprint 55 (8/25 - 9/7)
Sprint 56 (9/8 - 9/21)
Sprint 58 (9/22 - 10/5)
Sprint 59 (10/6 - 10/19)

## Comms_Notification prefs
Communications permissions/notification preferences: Long term planning
Sprints | Planned tasks | Notes
Sprint 44 (3/24 - 4/6) | Design/Backend integration PM: Schedule and hold design intent collab; Meet with Terry to better understand timeline so we can scope/plan Design: Continue design; Attend design intent collab BE: Finish build
Sprint 45 (4/7 - 4/20) | Design/backend integration PM: IA review with VSP Design: IA review; Work with content on all content that is *not* coming from VA Profile; Design documentation for frontend BE: Finish build if extra time needed
Sprint 46 (4/21 - 5/4) | Start tech discovery PM: Samara to do KPI planning; Check in with VA Profile on progress; Work with VANotify and VEText to refine list of notifications Design: Work with content and IA to refine list of notifications FE: Technical discovery | We'll need to know what the groups are in case we need special filters like filtering out health care notifications for people who don't have VA health care
Sprint 47 (5/5 - 5/18) | Has frontend tech discovery happened? Design: Content review and finalize items and groups; Share these with VANotify and VEText for concurrence; Share back to VA Profile team; IA review FE: Tech discovery if it didn't happen; Break down tickets
Sprint 48 (5/19 - 6/1) | Research prep PM: Check in with VA Profile on progress; Put test cases together; Prep for midpoint review Design: Work with AJ to put together test cases; Research plan and convo guide FE:
Sprint 49 (6/2 - 6/15) | Frontend build PM: Hold midpoint review Design: ; Attend midpoint review; Any required updates coming out of the midpoint review; Recruit for research; Start research if time FE: Attend midpoint review; Start build; additional ticket creation
Sprint 50 (6/16 - 6/29) | Frontend build/Conduct research & summarize PM: Design: Run/finish research; Summarize research; If time, update designs and frontend documentation as necessary FE: Continue build; implement changes from research
Sprint 51 (6/30 - 7/13) | PM: Request QA for sprint 53 --> ONLY DO THIS IF FRONTEND AND VA PROFILE ARE READY FOR QA; Otherwise, postpone QA and continue with whatever other tasks you can. Design: If needed, update designs and frontend documentation FE: Finish build; implement changes from research
Sprint 52 (7/14 - 7/27) | QA go/no-go PM: QA go/no-go; Submit ticket for analytics review; Submit for contact center review Design: Complete call center guide updates --> You can update the existing profile call center guide and just add a section to it for notification preferences FE: Attend QA go/no-go BE: Attend QA go/no-go
Sprint 53 (7/28 - 8/10) | QA PM: Start prep for staging and privacy reviews Design: UAT planning; Accessibility tests for staging review QA: Hold QA and create tickets FE: Fixes from QA; Accessibiility tests for staging review BE: Fixes from QA, if needed
Sprint 54 (8/11 - 8/24) | PM: Plan end end-to-end testing with VA Profile, VEText, and VANotify; Hold Staging and privacy reviews; UAT go/no-go FE: Fixes from staging and privacy reviews, if necessary BE: Fixes from staging and privacy reviews, if necessary
Sprint 55 (8/25 - 9/7) | Hold end-to-end testing Assuming end-to-end testing between all systems goes well, you can move on to the following: PM: Make sure end-to-end testing is completed; Hold Staging and privacy reviews; UAT go/no-go Design: Recruit for UAT FE: Participate in end-to-end testing as needed BE: Participate in end-to-end testing as needed
Sprint 56 (9/8 - 9/21) | PM: Launch go/no-go Design: Hold UAT FE: Fixes from UAT, if needed BE: Fixes from UAT, if needed
Sprint 58 (9/22 - 10/5) | PM: Monitor launch to 25%/50% FE: Flip switch to 25%/50%
Sprint 59 (10/6 - 10/19) | PM: Monitor launch to 100% FE: Flip switch to 100%
Sprint 60 (10/20 - 11/2) | Full 508 accessibility review
Sprint 61 (11/3- 11/16) | Full 508 accessibility review
Sprint 62 (11/17 - 11/30)
Sprint 63 (12/1 - 12/14)
Sprint 64 (12/15 - 12/28)
Additional notes
Things to consider for this project/planning: - After meeting with Terry and coming up with internal plan, we should regroup with FE to discuss. - Should we do InVision testing? This seems pointless if we don't have real data. We may want to start frontend build and wait until we have real content in live code to do usability testing (and then QA and the rest of the VSP checks). - How are we going to handle staging users? — We'll need to know exactly what notifications need to go out so we can find users that will see those.

## Preferred med facility
Preferred medical facility
Sprints | Planned tasks
Sprint 44 (3/24 - 4/6) | PM: Schedule and hold design intent collab; Meet with VAOS to better understand timeline so we can scope/plan; Internal long term planning Design: Finish design; Attend design intent collab
Sprint 45 (4/7 - 4/20) | PM: IA review with VSP Design: Content?; IA review; Design documentation for frontend
Sprint 46 (4/21 - 5/4) | VAOS works on design PM: Work with Liz on list of test cases/test users for the profile; Future planning with VAOS; Samara to talk to Lauren about KPI planning Design: Work with AJ on list of test cases/test users for the profile; Collaborate with Peter as needed on design; Start on research plan (though we won't be able to finish until next sprint)
Sprint 47 (5/5 - 5/18) | VAOS finishes design; Auth exp mini study PM: Coordinate on ticketing and to-dos with Lauren Ernest; Meet with VAOS as needed Design: Work with Peter to make sure design *and copy* is finished; Liz to run mini study; IA review for this work; Collab with Peter on convo guide
Sprint 48 (5/19 - 6/1) | VAOS & Auth exp recruit and run research PM: Coordinate on ticketing and to-dos with Lauren Ernest; Prep for Midpoint review Design: Work with Peter to recruit and run research; Update FE documentation if there were copy changes as a result of review with content and IA FE:
Sprint 49 (6/2 - 6/15) | VAOS & Auth exp summarize research; FE starts build PM: Coordinate on ticketing and to-dos with Lauren Ernest; Hold Midpoint review? Design: Work with Peter on research summary; Update designs as needed; Update FE documentation as needed FE: Technical discovery; Break down tickets for build
Sprint 50 (6/16 - 6/29) | Start build PM: Continued coordination with VAOS team; Finalize test cases; Design: Finalize test cases FE: Start build
Sprint 51 (6/30 - 7/13) | Continue build or finish build PM: Submit ticket for analytics review (VSP); Request QA for Sprint 53; Submit for contact center review Design: Update profile documentation for contact center guide FE: Continue build or FInish build
Sprint 52 (7/14 - 7/27) | Finish build if not done ** Note on QA**: It might help to have our QA around the same time as the VAOS QA simply so that doesn't hold up our/their progress moving towards launch. But this is optional and you should coordinate with Lauren on this. PM: QA go/no-go (Assuming completed build); Thoroughly review build Design: Attend QA go/no-go; Thoroughly review build FE: FInish build if not done; Attend QA go/no-go BE: Attend QA go/no-go
Sprint 53 (7/28 - 8/10) | QA PM: Coordinate on release plan with Lauren Ernest; Prep for staging review; Prep for privacy review Design: Work with Peter on UAT research plan and convo guide; Accessibility tests for staging review FE: Fixes from QA; Accessibility tests for staging review QA: Conduct QA and create tickets as needed
Sprint 54 (8/11 - 8/24) | Hold staging & privacy review PM: Hold staging & privacy review; Coordinate UAT go/no-go with Lauren Ernest; Hold UAT go/no-go Design: Attend UAT go/no-go; Recruit for UAT FE: Attend UAT go/no-go
Sprint 55 (8/25 - 9/7) | UAT PM: Coordinate Launch go/no-go with Lauren Ernest; Hold launch go/no-go Design: Hold UAT FE: UAT fixes
Sprint 56 (9/8 - 9/21) | Begin launch PM: Coordinate launch with VAOS; Monitor phased launch FE: Flip switch to 25%; Flip switch to 50%
Sprint 57 (9/22 - 10/5) | Complete launch PM: Coordinate launch with VAOS; Monitor phased launch FE: Flip switch to 100%
Sprint 59 (10/6 - 10/19) | Submit for full 508 accessibility audit
Sprint 60 (10/20 - 11/2)
Sprint 61 (11/3- 11/16)
Sprint 62 (11/17 - 11/30)

## Additional research
Preferred medical facility
Sprints | Planned tasks
Sprint 48 (5/19 - 6/1) | N/A
Sprint 49 (6/2 - 6/15) | N/A
Sprint 50 (6/16 - 6/29) | N/A
Sprint 51 (6/30 - 7/13) | Liz: Dependent's user roles research: Planning and recruiting
Sprint 52 (7/14 - 7/27) | Liz: Dependent's user roles research: Conduct research and summarize findings
Sprint 53 (7/28 - 8/10) | Liz's auth experience research project: Refine the plan we've started, start grabbing screenshots #24973
Sprint 54 (8/11 - 8/24) | Liz's auth experience research project: Wrap up screenshots, do any supplemental reading needed to answer questions, start synthesis #24974
Sprint 55 (8/25 - 9/7) | Liz's auth experience research project: Complete synthesis + present to team #24977
Sprint 56 (9/8 - 9/21)
Sprint 57 (9/22 - 10/5)

## Long term resourcing by person
| Sprint 50 (6/16 - 6/29) | Sprint 51 (6/30 - 7/13) | Sprint 52 (7/14 - 7/27) | Sprint 53 (7/28 - 8/10) | Sprint 54 (8/11 - 8/24) | Sprint 55 (8/25 - 9/7) | Sprint 56 (9/8 - 9/21) | Sprint 57 (9/22 - 10/5)
| Q2 2021 | Q3 2021 | [5 empty] | Q3/Q4/2021
Tressa Furner
My VA | 100% | 50% | 50% | 0% | 0% | 0% | 0% | 0%
Liz Lantz
Notification preferences | 60% | 30% | 30% | 10% | 30% | 0% | 0% | 0%
Preferred facility | 10% | 20% | 30% | 10% | 30% | 0% | 0% | 0%
Auth exp. research project | 0% | 0% | 0% | 0% | 20% | 20% | 20% | 0%
Dependents user roles research | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 0%
General profile updates | 10% | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Erik Hansen
My VA | 20% | 10% | 10% | 0% | 0% | 0% | 0% | 0%
Notification preferences | 60% | 20% | 20% | 0% | 20% | 10% | 10% | 0%
Preferred facility | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0%
General profile updates | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Taylor Mitchell
Preferred facility | 70% | 20% | 20% | 10% | 20% | 10% | 10% | 0%
General profile updates | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Lihan Li
Notification preferences | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 0%
Preferred facility | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 0%
User roles & permissions | 80% | TBD | TBD | TBD | TBD | TBD | TBD | TBD

## Task list for projects
General project tasks
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings