## Sheet1
| Notifications |  | Monitoring | Auth Updates | Deploy |  |  | QA/UAT |  | Documentation
Pre-Release | VA Notified of impending deployments | All Teams Notified of impending deployments |  |  |  | RTT Implements linting rules to prevent use of the old 'api.va.gov' hostname. |  |  |  | SRE Prepares playbooks to use the *platform-api.va.gov hostname(s)
VA Virtual Agent Team informed of change to use *platform-api.va.gov hostname
Rollback Prep |  |  |  | ID Works with Auth partners to prepare rollback process for reverting auth callback changes |  | RTT Prepares rollback PR and build
Staging Release | All Teams Notified of impending Staging deployment | Infra On-Call Notified of impending Staging deployment | SRE Staging Monitoring | IAM (via ID) Adds platform-api.va.gov API callback URLs for Dev and Staging |  | RTT Updates globally configured API URL for Dev and Staging |  | ID QA/UAT Dev & Staging | RTT QA/UAT Dev & Staging
|  | SRE Notified of impending Staging deployment |  | ID Updates vets-api authentication URLs for Dev and Staging. |  |  |  |  | All Teams QA/UAT Dev & Staging
Production Release | All Teams Notified of impending Production deployment | Infra On-Call Notified of impending Production deployment | SRE Production Monitoring | IAM (via ID) Adds platform-api.va.gov API callback URLs for Production |  | RTT Updates globally configured API URL for Production |  | ID QA/UAT Production | RTT QA/UAT Production
| Users Notified of login unavailability | SRE Notified of impending Production deployment |  | ID Updates vets-api authentication URLs for Production. |  |  |  |  | All Teams QA/UAT Production
Post-Release |  |  | SRE All Environment Monitoring |  | Infra Removes ‘api.va.gov’ references from revProxy; schedules cert renewals | RTT Search and replace 'api.va.gov' with 'platform-api.va.gov' in README files, scripts, comments, etc | Mobile Flagship Updates global configuration variables for new versions of the app |  |  | SRE Updates playbooks to use the *platform-api.va.gov hostname(s)
[5 empty] | Console Services Adds linting rules, or triggered Github action, to prevent use of the *api.va.gov hostname. | Lighthouse Configures new Apigee gateway to continue honoring Mobile and VANotify requests to api.va.gov | GIDS Edits global 'link_host' variable to use *platform-api.va.gov value in BRD and EKS deployment configurations. |  |  | Platform Content Edits documentation to use *platform-api.va.gov hostname