## My VA_Payment history
My VA
Sprints | Payment info updates
Sprint 58 (10/6 - 10/19) | Meet with edu team
Sprint 59 (10/20 - 11/2) | Scope project PM: Schedule discussion on discovery findings for end of sprint Design: Discovery -- determine the direction of work
Sprint 60 (11/3- 11/16) | Determine next steps PM: Nothing Design: Present findings; work with team to determine next steps; FE: Technical discovery, if needed
Sprint 61 (11/17 - 11/30) | Project pivot to payment information PM: Collab kickoff Design: Additional payment info discovery; Meet with debt team to understand feature; preliminary designs; Define scope FE: Do we need any technical discovery now? I don't think so.
Sprint 62 (12/1 - 12/14) | Design intent - Design; Design intent - Technical discovery
Sprint 63 (12/15 - 12/28) | Research/midpoint review planning - Midpoint review planning, including starting to put together list of test cases - Finish design if not already done - Technical discovery
Sprint 64 (12/29 - 1/11) | Midpoint review; Research planning - Hold midpoint review - Research planning/convo guide/ recruit; If not done, finish design on how to handle "benefits you might be interested in"; if done, create FE tickets - Prototype build on payment info
Sprint 65 (1/12 - 1/25) | Continue build - Conduct and summarize research - Update documentation if time - Updates from user research (may go into the following sprint depending on updates) - Determine what, if anything, still needs to happen with FE build, and complete build
Sprint 66 (1/26 - 2/8) | Finish build - PM: Do we need UAT? - Design for any updates coming out of testing; Onboard Angela - Request QA depending where build is at -- Are we ready for QA? - Update documentation if needed - Finish build
Sprint 67 (2/9 - 2/22) | Liz to transition My VA work over to Angela; All final updates ahead of QA - PM: Review QA test cases and make sure they are accurate given any updates from user testing - Team does informal click through of the feature to make sure it is ready for QA - Design: Contact center guide; maybe My VA sketch file clean up - FE: Error states; user testing updates
Sprint 68 (2/23 - 3/8) | QA - PM: Analytics request (Look at what we set for KPIs to give Heather details on what she should include in this request; add yo exisiting My VA dashboard) - QA (doesn't need to be day 1 of the sprint) - UAT planning
Sprint 69 (3/9 - 3/22) | PRE LAUNCH!! This assumes call center guide is all done. - PM: Make sure analytics updates get implemented; Put together launch plan; Prep for staging review; Hold staging review if we don't need to do any significant updates from QA (can be towards the end of the sprint if necessary) - Design: Updates from QA, if applicable - FE: Updates from QA if applicable; Prep for privacy and security review - BE: Prepare any technical diagrams or other documentation needed for the privacy and security review
Sprint 70 (3/23 - 4/5) | Because of BGS delays… - QA updates - Finish prep and hold staging review - Privacy and security review - UAT go/no-go - Start recruiting for UAT?
Sprint 71 (4/6 - 4/19) | Pre-launch prep - Updates from the staging review, if necessary - If we are good to go, recruit and hold UAT - PM: During UAT, make sure we can see analytics come in - Privacy and security review (ticket open and pending review)
Sprint 72 (4/20 - 5/3) | PM Monitor launch to 25% Monitor launch to 50% For V2 updates: Collab cycle kickoff For V2 updates: Collab cycle design intent FE Flip feature flag for launch to 25% Flip feature flag for launch to 50% Design For V2 updates: Collab cycle design intent
Sprint 73 (5/4 - 5/17) | Angela is out 5/3 - 5/10 (here 5 days this sprint) V1: Launch to 100% V2: Updates coming out of design intent (assuming we held design intent in sprint 72)
Sprint 74 (5/18 - 5/31) | V1: Observe stats after launch V2: Design updates if they didn't happen or werent't finished in sprint 73; Sitewide content/IA review (collab cycle); Research planning
Sprint 75 (6/1 - 6/14) | On hold for other work
Sprint 76 (6/15 - 6/28) | Design on hold while we prep for midpoint review PM: Midpoint review prep, including starting a preliminary list of QA tasks; Hold midpoint review by the end of the sprint if possible Design: On hold bc of midpoint review
Sprint 77 (6/29 - 7/12) | Updates from midpoint review;
Sprint 78 (7/13 - 7/26) | Another midpoint?; Research recruiting
Sprint 79 (7/27 - 8/9) | Research sessions/write-up/updates | Rough plan from here on -- plan may need adjustment
Sprint 80 (8/10 - 8/23) | Design -- FE documentation for build
Sprint 81 (8/24 - 9/6) | FE build; Contact center guide updates; QA request
Sprint 82 (9/7 - 9/20) | FE build; QA go/no-go; Analytics request; Release plan; UAT planning
Sprint 83 (9/21 - 10/4) | QA; Updates from QA; Staging review prep; do we need a privacy review?
Sprint 84 (10/5 - 10/18) | Staging review; UAT go/no-go; UAT recruiting
Sprint 85 (10/19 - 11/1) | UAT; Launch go/no-go; Launch to 25%
Sprint 86 (11/2 - 11/15) | Launch to 50%; Launch to 100%

## My VA_Audit
My VA: Audit
Sprints | Planned tasks
Sprint 69 (3/9 - 3/22) | Research review; Discuss next steps
Sprint 70 (3/23 - 4/5) | Design: - Audit nametag - Audit claims & appeals - Exploration for showing amount in debts & copays section/not showing debt and copay info as a notification style.
Sprint 71 (4/6 - 4/19) | Design: - Audit health care - Audit benefit payments and debts - Audit applications in progress - If time, regroup with Samara/AJ (or Heather if she is still here) on existing states
Sprint 72 (4/20 - 5/3) | On hold due to other work
Sprint 73 (5/4 - 5/17) | On hold due to other work
Sprint 74 (5/17 - 5/31) | Design: - Come up with use cases
Sprint 75 (6/1 - 6/14) | PM: Collab cycle kickoff Design: Assuming use cases are done, outline design updates and start on changes. | - Start streamlining states for each section - Start with nametag and payment info (since we are working on it anyway) - Each section should always appear on the page - Each section should have the following: loadin; blank state(s); content state(s); error state(s). Note: the nametag might be a little different, as there's never a totally blank state, and we don't show big error alerts for content we can't load.
Sprint 76 (6/15 - 6/28) | PM: None Design: Design for Claim status & health care sections
Sprint 77 (6/29 - 7/12) | On hold due to other work | NOTE: Consider smaller, iterative launches
Sprint 78 (7/13 - 7/26) | On hold due to other work
Sprint 79 (7/27 - 8/9) | On hold due to other work
Sprint 80 (8/10 - 8/23) | PM: None Design: Design for Claim status & health care sections
Sprint 81 (8/24 - 9/6) | Broader research planning (testing in code?); Maybe some tasks from next sprint's plan, if time.
Sprint 82 (9/7 - 9/20) | Design intent; Payment & debts and Apply for benefits updates; Does nametag need updates?
Sprint 83 (9/21 - 10/4) | Research prep/midpoint review prep
Sprint 84 (10/5 - 10/18) | Midpoint review; Research
Sprint 85 (10/19 - 11/1) | FE build
Sprint 86 (11/2 - 11/15) | FE build
FE build
QA
Pre-launch
Pre-launch
Launch
DOCUMENTATION SPRINT

## My VA_Redirect
My VA: Audit
Sprints | Planned tasks
Sprint 74 (5/17 - 5/31) | Planning Collab cycle kickoff; Figure out who needs to be involved in the redirect; Make sure we'll be able to get weekly Medallia reports as needed; Determine preliminary launch date
Sprint 75 (6/1 - 6/14) | PM tasks from last sprint, assuming we didn' get them done.
Sprint 76 (6/15 - 6/28) | Code implementation (identity); IA request if it didn't already happen; UAT planning (Liz); Figure out what updates need to happen for the contact center guide (which guide); "QA" once the feature is on staging
Sprint 77 (6/29 - 7/12) | Research recruiting, UAT/usability testing ON HOLD; Contact center guide updates
Sprint 78 (7/13 - 7/26) | On hold while we figure out the feature flag issue; Research recruiting
Sprint 79 (7/27 - 8/9) | UAT/usability testing & write up; Staging review prep; Do we need a privacy review? If so, prep for that; Release plan
Sprint 80 (8/10 - 8/23) | We can move on to these if there are no issues in the usability testing/UAT sessions that cause us to reevaluate our strategy. Hold Staging review; Privacy review; Launch go/no-go (maybe)
Sprint 81 (8/24 - 9/6) | Launch go/no-go; Launch to 25%; Launch to 50%
Sprint 82 (9/7 - 9/20) | Launch to 100%

## My VA_On-site notifications
On-site notifications MVP
Sprints | Planned tasks
Sprint 58 (10/6 - 10/19) | PM: Meet with VANotify Design: Finalize MVP design; meet with VANotify; meet with IA; finalize MVP notification list. FE: Support as needed. BE: Talk to platform; Technical diagram;
Sprint 59 (10/20 - 11/2) | Kickoff collab cycle; start build PM: Collab cycle kickoff; Collab cycle design intent; meet with VANotify Design: Design intent; content; meet with VANotify FE: Meet with VANotify BE: Start build ; meet with VANotify
Sprint 60 (11/3- 11/16) | Finalize designs, if possible; Determine next steps and timeline for VANotify; Continue build PM: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates Design: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates; Finalize designs, if not already done; Work with content, if not already done FE: Work with team to define requirements for VANotify updates; Support team as necessary BE: Work with team to define requirements for VANotify updates; Continue build
Sprint 61 (11/17 - 11/30) | Revisit this work - Talk to Chris and make sure that pivoting is OK - Redefine MVP (elevate all appointments, messages, debt?; Maybe just elevate appointments?) - PM: Given this pivot, do we need to redo any of the collab cycle? - Tressa: Mockup/explorations
Sprint 62 (12/1 - 12/14) | Project on hold
Sprint 63 (12/15 - 12/28) | Resume project - Define needs for VANotify, determine what they need to do, and determine timeline for any work they need to do. - Figure out what design needs to be updated; Update design; determine if we need additional user testing or not based on updates; follow-up with collab cycle design intent issues/tickets and let them know about our pivot. - Determine next steps for backend build; If possible, Tom can start to implement build if possible | Research - Midpoint review - Finish design if not already done - Research planning/convo guide - Start FE build? Finish backend build.
Sprint 64 (12/29 - 1/11) | Start build - PM: Determine VANotify's timeline based on availability; Determine QA/testing strategy -- talk to Leah/Denise/Maria about this; Midpoint review prep (note: testing for this is going to happen as part of payment info testing) - Design: Research prep is happening as part of payment info - FE: Start FE build if possible - BE: Lihan to meet with VANotify to determine how the backend should receive data from VANotify; Start build | Research - Conduc research/summarize research if needed - Continue/finish FE build - QA prep
Sprint 65 (1/12 - 1/25) | Hold midpoint review - PM: Midpoint review - Design: Research (as part of payment info work) - FE: Is there anything that still needs to happen? - BE: Build -- how many sprints? -- Is VANotify going away again because of contract issues? | Finish build - Contact center guides - Finish build
Sprint 66 (1/26 - 2/8) | Continue BE build as necessary Are we on hold until VANotify can work on this?
Sprint 67 (2/9 - 2/22) | On hold until VANotify is available
Sprint 68 (2/23 - 3/8) | On hold until VANotify is available
Sprint 69 (3/9 - 3/22) | 3/15: Intro work to the new VANotify team PM: Regroup with VANotify on this work and determine what next steps are for them; determine timelines for VANotify and FE work FE: Connect FE to backend API Lihan created
Sprint 70 (3/23 - 4/5) | VANotify to start work; evaluate what they need to do so we can plan our own timelines; Do we have a plan for QA?
Sprint 71 (4/6 - 4/19) | Determine next steps for VANotify; Determine next steps for Tom
Sprint 72 (4/20 - 5/3) | Get connected to DMC; Is frontend done?
Sprint 73 (5/4 - 5/17) | Continue frontend - Continue/finish frontend, including handling of multiple alerts - Regroup to figure out if we need to remove debt alert in benefit payments and debts before notifications launch - Figure out QA plan with DMC (backend team)
Sprint 74 (5/17 - 5/31) | Are we done with the frontend build? What is the status of this work? Finish FE if it's not done; Continue to figure out QA strategy with DMC; Analytics request;
Sprint 75 (6/1 - 6/14) | Request QA; Figure out how to get the backend to support test users; Coordinate QA with all necessary parties; QA go/no-go
Sprint 76 (6/15 - 6/28) | Get DMC to add test data and determine if everything is working
Sprint 77 (6/29 - 7/12) | VANotify to fix some bugs; Try again to get DMC to add debts
Sprint 78 (7/13 - 7/26) | On hold while we get e2e issues sorted out; Call center guide (can use My VA guide); End-to-end testing July 22 (if possible)
Sprint 79 (7/27 - 8/9) | QA; Release plan; Make sure we know where we are tracking analytics for launch
Sprint 80 (8/10 - 8/23) | Staging review and privacy review prep
Sprint 81 (8/24 - 9/6) | Staging review and privacy review; updates if needed
Sprint 82 (9/7 - 9/20) | Launch go/no-go; Launch to 10% and 25% (launch to 25% sooner if we aren't getting data at 10%)
Sprint 83 (9/21 - 10/4) | Launch to 50% and 100%
Have Tom document the backend (diagram); Design documentation

## My VA_Documentation
My VA documentation
Sprints | Planned tasks
Sprint 77 (6/29 - 7/12) | If time: create documentation update plan
Sprint 78 (7/13 - 7/26) | On hold due to other work
Sprint 79 (7/27 - 8/9) | On hold due to other work
Sprint 80 (8/10 - 8/23) | Continue planning; determine next steps -- unclear if work needs to start now or should wait until audit updates have been fully vetted through research
Sprint 81 (8/24 - 9/6)
Sprint 82 (9/7 - 9/20)

## LT My VA planning
Long term planning
Project | Sprint 78 (7/13 - 7/26) | Sprint 79 (7/27 - 8/9) | Sprint 80 (8/10 - 8/23) | Sprint 81 (8/24 - 9/6) | Sprint 82 (9/7 - 9/20) | Sprint 83 (9/21 - 10/4) | Sprint 84 (10/5 - 10/18) | Sprint 85 (10/19 - 11/1) | Sprint 86 (11/2 - 11/15)
My VA
Payment history V2 | Another midpoint/research recruiting | Research/write up | FE build | FE build | Pre-launch | Pre-launch | Pre-launch | UAT; Launch | Launch
My VA redirect | Figure out feature flag issues | UAT (postponed) | Release plan and reviews | Launch to 25% | Launch to 50% & 100%
On-site notifications MVP | Figure out e2e issues | QA | Final reviews prep | Final reviews | Launch to 10% & 25% | Launch to 50% & 100% | Documentation sprint
My VA audit & updates | On hold | On hold | Angela resumes work | Ongoing work
Documentations | On hold | On hold | TBD

## Task list for projects
General project tasks (updated April 2021)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings