## Profile_LGBTQ data
Personal information updates (LGBTQ data)
Sprints | Planned tasks | Notes
Sprint 58 (10/6 - 10/19) | Team onboards - Meet with team - Collab cycle kickoff - Collab cycle design intent - Create tickets for design, content, and frontend - Get relevant data points (ie What is populating dropdown menus?) - Complete initial mockups
Sprint 59 (10/20 - 11/2) | Continue design and FE build PM: Collab cycle IA review; Create frontend documentation as designs are finalized Design: Meet with content and update designs accordingly FE: Continue frontend build
Sprint 60 (11/3- 11/16) | PM: Continue to work behind the scenes to collab with MPI to get work ready for backend development Design: Transition call with Kevin; Update designs, if needed; Usability research plan FE: Continue build BE: Sit in on MPI calls
Sprint 61 (11/17 - 11/30) | PM: Start putting together list of test cases; Prep for midpoint review Design: Usability research plan & convo guide FE: Continue build (how much longer is this going to take?) BE: Start backend integration if MPI is ready
Sprint 62 (12/1 - 12/14) | Midpoint review, Recruit for user testing, Start testing (?) continue FE build; BE build (tickets TBD after we talk to this team on Wednesday) | Unclear when we'll be able to start backend build
Sprint 63 (12/15 - 12/28) | Recruit for testing if possible - Recruit for testing if contract is back - Continue whatever is left of the frontend build
Sprint 64 (12/29 - 1/11) | Research - PM: ? - Design: Conduct research; Synthesize test results - FE: Continue FE Build - BE: Start BE build
Sprint 65 (1/12 - 1/25) | Finish research; determine next steps with build based on VA Profile's direction - Summarize research - Any FE tasks? - Start BE build if possible
Sprint 66 (1/26 - 2/8) | Design: Changes from research FE: Work on changes from research, if changes are mocked up before the end of the sprint BE: Still on hold
Sprint 67 (2/9 - 2/22) | PM: When will we be ready for QA? Design: Finish all design updates FE: Implement design updates BE: Start BE build if possible; VA Profile is targeting 2/14 for being ready for us
Sprint 68 (2/23 - 3/8) | Continue build; Finish design; Finish FE PM: If content isn't done, assess when we think that will be done based on Danielle's availability; If time, work on contact center guide Design: Finish all design updates; If time, work on contact center guide FE: Finish FE if possible BE: Provide estimate of how long BE build will take; Continue BE build
Sprint 69 (3/9 - 3/22) | Design: Finish design if it's not done; If done, contact center guide FE: Finish any updates if they are not already done; If done, project is on pause for Adam until backend is ready to connect to frontend BE: Continue BE (Tom out 3/10, 11, 14)
Sprint 70 (3/23 - 4/5) | Continue BE PM: Call center guide; Determine when we can do QA based on new BE timeline Design: Change gender identity BACK to single select; Create a couple mockups showing preferred name/gender identity without the other fields; Call center guide FE: Change gender identity BACK to single select; Implement final design updates; Gate separating preferred name/gender identity from pronouns/sexual orientation; Hide pronouns/sexual orientation on the frontend as part of the gate BE: Continue BE integration; Determine how our approach changes given separate launch of pronouns and sexual orientation
Sprint 71 (4/6 - 4/19) | Finish BE - PM: Request QA for 5/4 - 5/17 sprint; Finish all QA prep; Finish call center guide - Design: Finish call center guide; UAT planning if time - FE: Start connecting frontent to backend; Finish this if possible - BE: Finish BE
Sprint 72 (4/20 - 5/3) | Anything outstanding from last sprint, plus... PM: Submit call center guide for review Design: Complete UAT planning FE: Connect FE to BE if that still needs to happen Everyone: Once the feature is fully complete in staging, everyone on the project should go into staging and review the feature to make sure it's ready for QA
Sprint 73 (5/4 - 5/17) | QA PM: QA go/no-go; Analytics request; Release plan QA: QA Fixes on QA, if applicable and if QA results are available before the end of the sprint
Sprint 74 (5/18 - 5/31) | Fixes from QA, if applicable; Pre-launch prep; Staging review; privacy review; FE to implement analytics tracking
Sprint 75 (6/1 - 6/14) | UAT go/no-go; UAT recruiting; UAT
Sprint 76 (6/15 - 6/28) | Launch to 25% & 50% & 100%
Sprint 77 (6/29 - 7/12) | FE:Updated URLs that point to the contact info section of the profile (audit Adam did a few sprints ago)
Sprint 78 (7/13 - 7/26) | Submit for 508 review
Sprint 79 (7/27 - 8/9) | Documentation sprint
Sprint 80 (8/10 - 8/23)
Sprint 81 (8/24 - 9/6)
Sprint 82 (9/7 - 9/20)

## Profile_Military service info
Military service info
Sprints | Planned tasks | Notes
Sprint 70 (3/23 - 4/5) | Samara to prep product outline
Sprint 71 (4/6 - 4/19) | N/A
Sprint 72 (4/20 - 5/3) | N/A
Sprint 73 (5/4 - 5/17) | Have Tom start this work; Collab kickoff; Begin backend integration
Sprint 74 (5/18 - 5/31) | Finish backend; Talk QA strategy -- do we need something beyond internal QA?; UAT planning (may be an internal UAT); Analytics planning -- do we need to make any updates?
Sprint 75 (6/1 - 6/14) | Is there more backend work?
Sprint 76 (6/15 - 6/28) | On hold while Tom is out; Samara QA'd staging
Sprint 77 (6/29 - 7/12) | On hold due to VA Profile needing to update ICD and access permissions
Sprint 78 (7/13 - 7/26) | Once VA Profile has completed the ICD and access permissions (after July 18), coordinate internal UAT (ask people on the team to make sure their military info looks correct); Potentially start launch, if time.
Sprint 79 (7/27 - 8/9) | Assuming VA Profile is ready to go, Run internal UAT. We will launch the following sprint when I'm back from vacation.
Sprint 80 (8/10 - 8/23) | Launch to 25%; Launch to 50%; Launch to 100%; Documentation sprint (Tom)
Sprint 81 (8/24 - 9/6)
Sprint 82 (9/7 - 9/20)
Once this work is done, take 1 sprint to create master doc of Military info

## Profile_Direct deposit
Direct deposit improvements
Sprints | Planned tasks | Notes
Sprint 68 (2/23 - 3/8) | Samara: Try to figure out what error codes mean so we can look into them
Sprint 69 (3/9 - 3/22) | N/A -- Waiting for availability
Sprint 70 (3/23 - 4/5) | N/A -- Waiting for availability
Sprint 71 (4/6 - 4/19) | N/A -- Waiting for availability
Sprint 72 (4/20 - 5/3) | Design: Update direct deposit mockups in Sketch (apparently outdated); Mock up screens to for direct deposit being persistently available; Clarify edu feedback that if they receive checks, they need to call to start direct deposit
Sprint 73 (5/4 - 5/17) | FE: Implement always showing direct deposit
Sprint 74 (5/18 - 5/31) | Finish FE updates if they are not already done; Continue documentation as needed; Review build; determine launch strategy; Maybe launch updates?
Sprint 75 (6/1 - 6/14) | Launch
Sprint 76 (6/15 - 6/28) | PM: Observe analytics
Sprint 77 (6/29 - 7/12) | PM: Observe analytic
Sprint 78 (7/13 - 7/26) | On hold
Sprint 79 (7/27 - 8/9) | On hold
Sprint 80 (8/10 - 8/23) | On hold
Sprint 81 (8/24 - 9/6) | PM: Get Jason to send us Medallia data; Assess how direct deposit feedback has changed. Are people saying they should see DD info that are not seeing it? Determine next steps.
Sprint 82 (9/7 - 9/20)

## Profile_Notification Preference
Notification preferences updates
Sprints | Planned tasks | Notes
Add comp & pen payment notification: Start date TBD; Originally mentioned in VA Profile meeting on 3/10
Sprint 69 (3/9 - 3/22) | VA Profile let us know about new comp & pen payment notification
Sprint 70 (3/23 - 4/5) | Get update on comp & pen notification and do planning; Update prescriptions notification to accommodate additional facilities
Sprint 71 (4/6 - 4/19) | Get Christina to update mocks with the new claims deposit notification info, then get feedback from IA and content
Sprint 72 (4/20 - 5/3) | Start talking above massive notification migration from eBenefits; Mark to do some notification prefs discovery
Sprint 73 (5/4 - 5/17) | Nothing for now
Sprint 74 (5/18 - 5/31) | Nothing for now
Sprint 75 (6/1 - 6/14) | On hold in favor of other work
Sprint 76 (6/15 - 6/28) | On hold in favor of other work
Sprint 77 (6/29 - 7/12) | Bev says the UI does NOT have to differentiate between default opt-in and explicit opt-in. So, for this sprint, we should: - Discuss work with design to determine if UI changes are needed - Do BE and FE discovery to determine what changes need to happen
Sprint 78 (7/13 - 7/26) | Determine whether we are moving forward with default opt-in Maybe start MHV notification prefs working group? Determine if anything needs to happen re: 1095
Sprint 79 (7/27 - 8/9) | TBD, but there may be 1095B work
Sprint 80 (8/10 - 8/23) | TBD, but there may be 1095B work
Sprint 81 (8/24 - 9/6)
Sprint 82 (9/7 - 9/20)

## Profile_Bad address
Bad address indicator
Sprints | Planned tasks | Notes
Sprint 65 (1/12 - 1/25) | PM/PO prediscovery; BE to review swagger docs
Sprint 66 (1/26 - 2/8) | Continue PM discovery; product outline
Sprint 67 (2/9 - 2/22) | Collab cycle kickoff; If time allows with personal info work, start design brainstorming
Sprint 68 (2/23 - 3/8) | Design: Tickets for design in profile and email
Sprint 69 (3/9 - 3/22) | Design intent PM: Intro work to VANotify; determine what they need to do, if anything. Probably something given that we want to send an initial email blast and then emails for users when the bad address indicator gets added. Design: Design if not done the previous sprint; Design intent; Work with content on profile/email copy; start FE documentation on when the alert shows in the profile and when the email will be sent out (initial blast; whenever a new bad address is added)
Sprint 70 (3/23 - 4/5) | PM: Start on QA use cases (this will not be completed yet); Figure out how we can get a staging user with the bad address indicator for testing (might require working with VA Profile) Design: Design intent if it didn't happen; Finalize designs; FE documentation
Sprint 71 (4/6 - 4/19) | On Hold (Sharon onboarding; Team focused on other work)
Sprint 72 (4/20 - 5/3) | PM and Design on hold BE: BE work on email blast/individual emails
Sprint 73 (5/4 - 5/17) | Design: Create high fidelity mockups
Sprint 74 (5/18 - 5/31) | Design: research plan and convo guide FE: Can we start FE build?
Sprint 75 (6/1 - 6/14) | PM: Midpoint review prep; Midpoint review by the end of the sprint | PM: Midpoint review prep Design: Put together research plan; Put together convo guide FE: Assuming Design work is done for profile, start FE build if time (personal info work takes priority)
Sprint 76 (6/15 - 6/28) | Design: Research recruiting; Research | PM: Hold midpoint review Design: Recruit for research
Sprint 77 (6/29 - 7/12) | Research; Christina out the rest of the sprint
Sprint 78 (7/13 - 7/26) | PM: QA Prep; Request QA for sprint 80 (8/10-23) Design: Summarize research; Updates from research (if applicable)
Sprint 79 (7/27 - 8/9) | PM: Analytics request (this is already done, right?); Release plan Design: Design updates; Document and ticket for frontend
Sprint 80 (8/10 - 8/23) | PM: Request QA Design: Contact center guide FE: Updates from research, if applicable
Sprint 81 (8/24 - 9/6) | QA QA: Hold QA Design: UAT prep and planning; PM: Prep for staging & privacy reviews | UAT is likely not possible since we can't control who sees the BAI
Sprint 82 (9/7 - 9/20) | Updates from QA if applicable; Staging review; Privacy review; UAT recruiting
Sprint 83 (9/21 - 10/4) | UAT; Launch to 25% & 50%
Sprint 84 (10/5 - 10/18) | Launch to 100%; DOCUMENTATION SPRINT
Sprint 85 (10/19 - 11/1) | Once this work is done, take 2 sprints to create master doc of contact info
Sprint 86 (11/2 - 11/15)

## Profile_Accessibility updates
Accessibility updates
Sprints | Planned tasks | Notes
Sprint 77 (6/29 - 7/12) | On hold in favor of other work
Sprint 78 (7/13 - 7/26) | On hold in favor of documentation
Sprint 79 (7/27 - 8/9) | On hold in favor of documentation
Sprint 80 (8/10 - 8/23) | On hold in favor of documentation
Sprint 81 (8/24 - 9/6) | Discovery -- review accessibility notes on what needs to be fixed, and talk about process (especially around how we want to test this work with users throughout)
Sprint 82 (9/7 - 9/20) | Scope effort/LTP; Maybe Collab cycle kickoff; Begin design

## Profile_Forms system updates
Forms system updates
Sprints | Planned tasks | Notes
Sprint 78 (7/13 - 7/26) | Scope work/Planning
Sprint 79 (7/27 - 8/9) | Continued work
Sprint 80 (8/10 - 8/23) | Continued work
Sprint 81 (8/24 - 9/6) | Continued work
Sprint 82 (9/7 - 9/20) | Continued work
Sprint 83 (9/21 - 10/4) | Continued work
Sprint 84 (10/5 - 10/18)
Sprint 85 (10/19 - 11/1)
Sprint 86 (11/2 - 11/15)

## Profile_Update documentation
Profile: Create better documentation
Sprints | Planned tasks | Notes
Sprint 72 (4/20 - 5/3) | N/A
Sprint 73 (5/4 - 5/17) | N/A
Sprint 74 (5/18 - 5/31) | Document Direct Deposit
Sprint 75 (6/1 - 6/14) | Document Direct Deposit
Sprint 76 (6/15 - 6/28) | Document Direct Deposit
Sprint 77 (6/29 - 7/12) | Document contact info (Liz)
Sprint 78 (7/13 - 7/26) | Document Military Info (Tom); Contact info continues
Sprint 79 (7/27 - 8/9) | Document Personal info (Christina, Adam, Tom)
Sprint 80 (8/10 - 8/23) | Continue Personal info
Sprint 81 (8/24 - 9/6) | Document Notification Preferences (Liz); Document Account Settings (Christina, if Personal info is complete)
Sprint 82 (9/7 - 9/20) | Document Connected Apps
Sprint 83 (9/21 - 10/4)

## LT profile planning
Long term planning until end of contract
Project | Sprint 78 (7/13 - 7/26) | Sprint 79 (7/27 - 8/9) | Sprint 80 (8/10 - 8/23) | Sprint 81 (8/24 - 9/6) | Sprint 82 (9/7 - 9/20) | Sprint 83 (9/21 - 10/4) | Sprint 84 (10/5 - 10/18) | Sprint 85 (10/19 - 11/1) | Sprint 86 (11/2 - 11/15)
Profile
Personal information revisions | N/A | Documentation sprint
Military reintegration with VA Profile | Documentation | UAT | Launch
Notification preferences | MHV working group; 1095B conversations/work; MHV notification prefs migration
Bad address indicator | Research write up | Launch planning; research updates | Launch planning; research updates | QA; launch planning | Staging and privacy and security reviews; UAT recruiting | UAT | Launch; Documentation
Documentation updates | Military info (Tom); Contact info (Liz) | Personal info (team) | Personal info (team) | Updates ongoing | Updates ongoing | Updates ongoing
Accessibility audit/updates | On hold for documentation | On hold for documentation | On hold for documentation | Discovery | Scoping/kickoff | Updates ongoing | Updates ongoing | Updates ongoing | Updates ongoing
Forms system updates | Scope | Ongoing work
Direct deposit | Ask Jason Woodman for Medallia data

## Task list for projects
General project tasks (updated April 2021)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings