## Dual-State_&_Go_Live
Task # | Owner/Responsible | Consulted/Support | Status | Area | Parent Milestone | Milestone/Task Required | Time Frame (est.) | Artifact required | Dependency | Estimates | Target Date | Actual Date | In Progress Tracker | Notes:
1 | Team | Stakeholder |  | Process | Prep-Dual Launch | Run Book review
1.1 | VAMC |  |  | Validation checks | Prep-Dual-State | Confirm colaboration checklist is complete and all parties are updated on Dual-stage date |  | Colaboration matrix | -
1.2 | VAMC | Platform |  | Validation checks | Prep-Dual-State | Clean-up broken links and any unresolved (508 issues) |  | Devshop rebuild | -
1.4 | Stakeholder | VAMC/CMS |  | Training | Prep-Dual-State | Training Introduction Started (Minimum: Session 1 and Session 2) |  | Self serve Library/Instructor lead | -
1.5 | VHA | VAMC |  | Communications | Prep-Dual-State | Review Banner for "Current" site (Teams) and return Banner at Draft site (CMS) for COVID & Return |  | Banner draft | -
1.6 | VHA |  |  | Communications | Prep-Dual-State | Approval to deploy CMS Banner (Dual-State return banner) |  | VHA - Drafts of banner / e-mail | 1.5
1.7 | VAMC | Analytics |  | Initialized request | Prep-Dual-State | Submit issue to Analytics team to add analytics to Site/URL pages |  |  | 1.2
1.8 | CMS / Stakeholder |  |  | Training | Prep-Dual-State | Self Service training session 1-5 have been provided to PAO web maintainers |  | Learning Center, Schedule | 1.4
1.9 | Analytics | VAMC |  | Reporting/add-on | Prep-Dual-State | Analytics Deployed (Coordinated with Platform & Facilities) |  | Devshop | 1.6
1.10 | VAMC | Platform |  | Initialized request | Prep-Dual-State | Submit issue to IA to confirm - VSP team has ownership over System URL (va.gov/system) (GO LIVE) |  | Zenhub issue | -
1.11 | VAMC | CMS |  | Communications | Prep-Dual-State | (Comms only) Updated technical debt nodes have been resolved and confirmed updated. (Comm to Stakeholders) |  | Devshop | -
1.12 | VAMC | CMS |  | COVID-19 Vaccine | Prep-Dual-State | COVID-19 Vacination Health Services Detail Page (MOST recent Update) has been cloned and updated and System and Facility Health services HyperLink have been associated with page |  | .csv file for automation | -
1.13 | VAMC | CMS |  | COVID-19 Vaccine | Prep-Dual-State | COVID-19 Vacination System Health Service and Facility Specific Health Service have been migrated into System |  |  | 1.12
1.14 | VAMC | VHA/Stakeholder |  | Communications | Prep-DS/Day of Publication | Full review and comms on date of cut over from Dual-state to live-dual-state |  |  | 1.7
1.15 | VAMC | VHA/Stakeholder |  | Recommendation | Prep-DS/Day of Publication | Recommendation to add Approved Banner to Site through Teamsite (NIGHT OF Dual-State pub - COVID-19 Banner/ This can be added at a later time during Dual-State, but must be tested and active before GoLIVE) |  |  | 1.7, 1.14
1.16 | Platform | VAMC |  | Platform | Prep-DS/Day of Publication | Confirm blacklist/robots.txt files are added- (confirm where it lives and who owns)
1.17 | Platform | VAMC |  | Platform | Prep-DS/Day of Publication | Remove [System] root url (e.g. /[system]-health-care/) from robots.txt (for url link from banner) |  |  | 1.16
2 | VAMC | (Platform, CMS, 508) |  | Communications | Dual-State | COMMS: CMS (Support launch), Call Center (update), 508 for deep dive test |  | (New URL)?
2.1 | VAMC | VAMC |  | CMS | Dual-State | Publish Content from Production (All System nodes) |  |  | 1.14-1.17
2.2 | VAMC | Accessibility, VAMC |  | Testing | Dual-State | Full review and test of production pages (List issues)(Initiate stories for priority fix) |  |  | 2.1
2.3 | VAMC | CMS, VHA, DEPO, Platform |  | Review - Validation | Dual-State | **Launch Colaboration meeting** Full review summary (Good to Go or Roll back decision) |  |  | 2.1, 2.2
2.4 | VAMC | CMS (VAMC) |  | Removal of Devshop | Dual-State | If there are no roll-back items - REMOVE - DevShop instance is removed (Eliminate URL confusion)
2.4.1 | VAMC | CMS |  | Roll back? | Dual-State | **If there are issues - Institute Rollback, Remove from Dual State, Create stories to correct issues.
2.5 | Stakeholder | VHA |  | Communications | Dual-State | E-mail invitation sent out (internal) Expect: Traffic Spike |  |  | 2.3
2.6 | Stakeholder | CMS |  | Training | Dual-State | Training Session 5: (Ops/Alert Status) Muste be complete
2.7 | Stakeholder | VAMC |  | Prep for Site to Go-live | Dual-State | Alerts in Queue (review and match Legacy Site of record to match) |  |  | 2.6
2.8 | Stakeholder | CMS |  | Training | Dual-State | Feed back loop from stakeholders regarding training (Was this helpful?, suggestions, Adoption)
2.9 | Stakeholder | VAMC |  | Hand off to Stakeholder | Dual-State | Stakeholder takes ownership of Site (Test Analytics (Review Analytics views and reports) |  |  | 1.9, 2.4
2.10 | Stakeholder | VAMC |  | Configuration | Required before Prep | Confirm all Testing and revisions - Complete (No 508/accessibility)
2.11 | Stakeholder |  |  | Alerts/Op-Status | Prep for Go Live | Update Alerts: and Operating Status (COVID-19 and Closed locations, hour changes) (Running/Published) |  |  | 2.4
2.12 | CMS |  |  | Configuration | Prep for Go Live | Validate Pull/Scraping of Operating status (Make CMS primary, Teams site secondary) |  |  | 2.5
2.13 | CMS |  |  | Training | Final Training Complete | CMS - Confirm through tracking and present for sign off on Webmaintainer training |  |  | 2.4
2.14 | Platform | VAMC |  | Platform | Final Cut action | Confirm Platform has hand on switch for URL (Redirect of old url at root) |  |  | 1.11
2.15 | All Teams |  |  | Go - No Go | GO - NO GO Meeting | Meeting Colaboration - PAO Sign off on all revisions - Agree to Go live Date |  |  | -