## Slide 1: Show me, don’t tell me: Sprint 6 Demo 14 December 2021

## Slide 2: Sprint 6 Approval (1 of 2)
CLIN 0001AB
Sprint Dates: 12/1/2021-12/14/2021
Sprint Goal: The goal of this sprint is to narrow in on final design for the POC. Through rapid test-and-iteration cycles, coupled with collaboration sessions between MO and our VA partners, we'll be able to down-select from our three designs into 1-2 designs to be tested and refined in following sprint. Develop agenda and evolve presentation for January AWG. Refine product roadmap to include tactical and lifecycle elements, tollgates, and delivery estimates.
Priority | Epic: User Story | Acceptance Criteria
High | Testing and iterating: Implement VA feedback | Iterated homepage designs based on feedback from VA PO, VA Design Lead and VA Executive Sponsor Documented iteration in Mural Deliverable: Research plan and report
High | Testing and iterating: Write research plan | Developed research plan for guerilla user testing, including questions and methods Developed research plan for formal testing using VA methods and contract for Sprint 7 Uploaded research plans to GitHub repo Deliverable: Research plans and report
High | Testing and iterating: Recruit research participants | Recruited a diverse set of research participants (n=10-50) Gorilla recruiting until VA contract for research executed Recorded participant demographics in research plan Deliverable: Research plan and report
High | Testing and iterating: Testing | Tested users according to research plan Conducted multiple rounds of user research / testing based on evolved design iterations Deliverable: Research plan and report
High | Testing and iterating: Synthesize research findings | Shared research findings with VA-PO and VA Design lead at design meetings Reported summary of findings in research report in GitHub repo Deliverable: Research plan and report
High | Testing and iterate: Iterate homepage designs | Iterate designs multiple times based on research findings and feedback from stakeholders Documented iteration in Mural Deliverable: Evolved design mural

## Slide 3: Sprint 6 Approval (2 of 2)
CLIN 0001AB
Priority | Epic: User Story | Acceptance Criteria
High | Testing and iterate: Downselect design elements | Held consensus-gathering meetings with VA-PO to decide on final homepage design and sitemap Deliverable: Evolved design mural
High | Apartment Working Group: AWG meeting prep | Evolved deck and mural to reflect relevant work leading up to design decision Created agenda for distribution to VA executives and stakeholders (by VA PO) Deliverable: Evolved AWG deck Deliverable: AWG agenda
High | PMO: ZenHub migration | Migrated stories, epics and initiatives migrate to ZenHub ZenHub read and write access granted to all MO team members Deliverable: N/A
High | POC Design: Project roadmap | Project Roadmap revised with tactical (COR requirements: meetings, deliverables) and product lifecycle ( working group meetings, checkpoints, collaboration cycles, VA playbook nomenclature) Multiple meetings with VA-PO to project roadmap deliverable dates and expectations Deliverable: Revised Product Roadmap