## My VA
My VA: Payment info updates
Sprints | Planned tasks
Sprint 58 (10/6 - 10/19) | Meet with edu team
Sprint 59 (10/20 - 11/2) | Scope project PM: Schedule discussion on discovery findings for end of sprint Design: Discovery -- determine the direction of work
Sprint 60 (11/3- 11/16) | Determine next steps PM: Nothing Design: Present findings; work with team to determine next steps; FE: Technical discovery, if needed
Sprint 61 (11/17 - 11/30) | Project pivot to payment information PM: Collab kickoff Design: Additional payment info discovery; Meet with debt team to understand feature; preliminary designs; Define scope FE: Do we need any technical discovery now? I don't think so.
Sprint 62 (12/1 - 12/14) | Design intent - Design - Technical discovery
Sprint 63 (12/15 - 12/28) | Research - Midpoint review - Finish design if not already done - Research planning/convo guide - Start build?
Sprint 64 (12/29 - 1/11) | Research - Conduc research/summarize research - Continue build - QA prep
Sprint 65 (1/12 - 1/25) | Finish build - Contact center guides - Finish build
Sprint 66 (1/26 - 2/8) | QA
Sprint 67 (2/9 - 2/22) | Pre-launch prep
Sprint 68 (2/23 - 3/8) | Pre-launch prep
Sprint 69 (3/9 - 3/22) | Launch to 25% & 50%
Sprint 70 (3/23 - 4/5) | Launch to 100%

## Alerts
On-site notifications MVP
Sprints | Planned tasks
Sprint 58 (10/6 - 10/19) | PM: Meet with VANotify Design: Finalize MVP design; meet with VANotify; meet with IA; finalize MVP notification list. FE: Support as needed. BE: Talk to platform; Technical diagram;
Sprint 59 (10/20 - 11/2) | Kickoff collab cycle; start build PM: Collab cycle kickoff; Collab cycle design intent; meet with VANotify Design: Design intent; content; meet with VANotify FE: Meet with VANotify BE: Start build ; meet with VANotify
Sprint 60 (11/3- 11/16) | Finalize designs, if possible; Determine next steps and timeline for VANotify; Continue build PM: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates Design: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates; Finalize designs, if not already done; Work with content, if not already done FE: Work with team to define requirements for VANotify updates; Support team as necessary BE: Work with team to define requirements for VANotify updates; Continue build
Sprint 61 (11/17 - 11/30) | Revisit this work - Talk to Chris and make sure that pivoting is OK - Redefine MVP (elevate all appointments, messages, debt?; Maybe just elevate appointments?) - PM: Given this pivot, do we need to redo any of the collab cycle? - Tressa: Mockup/explorations
Sprint 62 (12/1 - 12/14) | Resume project - Figure out what we need from VANotify at this point, if anything. Maybe just some way to indicate/show in their system that a notification should go to VA.gov. - Figure out what design needs to be updated; Update design; determine if we need additional user testing or not based on updates; follow-up with collab cycle design intent issues/tickets and let them know about our pivot. - Continue backend build. When will this be done?
Sprint 63 (12/15 - 12/28) | Research - Midpoint review - Finish design if not already done - Research planning/convo guide - Start FE build? Finish backend build.
Sprint 64 (12/29 - 1/11) | Research - Conduc research/summarize research if needed - Continue/finish FE build - QA prep
Sprint 65 (1/12 - 1/25) | Finish build - Contact center guides - Finish build
Sprint 66 (1/26 - 2/8) | QA
Sprint 67 (2/9 - 2/22) | Pre-launch prep
Sprint 68 (2/23 - 3/8) | Pre-launch prep
Sprint 69 (3/9 - 3/22) | Launch to 25% & 50%
Sprint 70 (3/23 - 4/5) | Launch to 100%

## Comms_Notification prefs
Communications permissions/notification preferences
Sprints | Planned tasks | Notes
Sprint 57 (9/22 - 10/5) | QA PM: QA go/no-go; Submit ticket for analytics review; Submit for contact center review Design: Complete call center guide updates --> You can update the existing profile call center guide and just add a section to it for notification preferences QA: Hold QA and create tickets FE: Attend QA go/no-go BE: Attend QA go/no-go
Sprint 58 (10/6 - 10/19) | PM: Start prep for staging and privacy reviews; Hold reviews Design: UAT planning; Accessibility tests for staging review FE: Fixes from QA; Accessibiility tests for staging review BE: Fixes from QA, if needed
Sprint 59 (10/20 - 11/2) | PM: UAT go/no-go; Hold UAT; Launch go/no-go Design: Recruit for UAT; Hold UAT FE: Fixes from staging and privacy reviews, if necessary; Fxes from UAT if necessary BE: Fixes from staging and privacy reviews, if necessary; Fixes from UAT if necessary
Sprint 60 (11/3- 11/16) | PM: Monitor launch to 25%/50% FE: Flip switch to 25%/50%
Sprint 61 (11/17 - 11/30) | PM: Monitor launch to 100% FE: Flip switch to 100%
Sprint 62 (12/1 - 12/14) | Full 508 accessibility review
Sprint 63 (12/15 - 12/28) | Full 508 accessibility review
Sprint 64 (12/29 - 1/11)
Sprint 65 (1/12 - 1/25)
Sprint 66 (1/26 - 2/8)
Sprint 67 (2/9 - 2/22)
Sprint 68 (2/23 - 3/8)
Sprint 69 (3/9 - 3/22)
Sprint 70 (3/23 - 4/5)
Additional notes
Things to consider for this project/planning: - After meeting with Terry and coming up with internal plan, we should regroup with FE to discuss. - Should we do InVision testing? This seems pointless if we don't have real data. We may want to start frontend build and wait until we have real content in live code to do usability testing (and then QA and the rest of the VSP checks). - How are we going to handle staging users? — We'll need to know exactly what notifications need to go out so we can find users that will see those.

## User roles research
User roles research
Sprints | Planned tasks
Sprint 58 (10/6 - 10/19) | Design: Scope research; previous research review; review eBenefits/MHV; Identify SMEs
Sprint 59 (10/20 - 11/2) | Talk to Liz about where she think she'll be by the end of last sprint. If she's in good shape… Design: Research plan, convo guide, and reach out to SMEs to set up interviews
Sprint 60 (11/3- 11/16) | Design: Schedule Interviews; Hold as many interviews as possible
Sprint 61 (11/17 - 11/30) | Design: Finish interviews if needed; Research write-up and read-out
Sprint 62 (12/1 - 12/14)
Sprint 63 (12/15 - 12/28)
Sprint 64 (12/29 - 1/11)
Sprint 65 (1/12 - 1/25)
Sprint 66 (1/26 - 2/8)
Sprint 67 (2/9 - 2/22)
Sprint 68 (2/23 - 3/8)
Sprint 69 (3/9 - 3/22)
Sprint 70 (3/23 - 4/5)

## Profile_LGBTQ data
Personal information updates (LGBTQ data)
Sprints | Planned tasks | Notes
Sprint 58 (10/6 - 10/19) | Team onboards - Meet with team - Collab cycle kickoff - Collab cycle design intent - Create tickets for design, content, and frontend - Get relevant data points (ie What is populating dropdown menus?) - Complete initial mockups
Sprint 59 (10/20 - 11/2) | Continue design and FE build PM: Collab cycle IA review; Create frontend documentation as designs are finalized Design: Meet with content and update designs accordingly FE: Continue frontend build
Sprint 60 (11/3- 11/16) | PM: Continue to work behind the scenes to collab with MPI to get work ready for backend development Design: Transition call with Kevin; Update designs, if needed; Usability research plan FE: Continue build BE: Sit in on MPI calls
Sprint 61 (11/17 - 11/30) | PM: Start putting together list of test cases; Prep for midpoint review Design: Usability research plan & convo guide FE: Continue build (how much longer is this going to take?) BE: Start backend integration if MPI is ready
Sprint 62 (12/1 - 12/14) | Midpoint review, Recruit for user testing, Start testing (?) continue FE build; BE build | Unclear when we'll be able to start backend build
Sprint 63 (12/15 - 12/28) | Synthesize test results; Continue FE Build; BE build
Sprint 64 (12/29 - 1/11) | Finish build
Sprint 65 (1/12 - 1/25) | QA
Sprint 66 (1/26 - 2/8) | Pre-launch prep
Sprint 67 (2/9 - 2/22) | Pre-launch prep
Sprint 68 (2/23 - 3/8) | Launch to 25% & 50%
Sprint 69 (3/9 - 3/22) | Launch to 100%
Sprint 70 (3/23 - 4/5)
Additional notes

## Bad address indicator
Bad address indicator
Sprints | Planned tasks | Notes
Sprint 62 (12/1 - 12/14) | Team discovery - Meet with VA Profile to ask about this - If Lihan has time with other work, look into what we have - Product (Samara)/Design discovery to find out what this indicator can tell us - MVP definition
Sprint 63 (12/15 - 12/28) | TBD
Sprint 64 (12/29 - 1/11)
Sprint 65 (1/12 - 1/25)
Sprint 66 (1/26 - 2/8)
Sprint 67 (2/9 - 2/22)
Sprint 68 (2/23 - 3/8)
Sprint 69 (3/9 - 3/22)
Sprint 70 (3/23 - 4/5)
Additional notes

## LT project planning
Long term planning until end of contract
Project | Sprint 61 (11/17 - 11/30) | Sprint 62 (12/1 - 12/14) | Sprint 63 (12/15 - 12/28) | Sprint 64 (12/29 - 1/11) | Sprint 65 (1/12 - 1/25) | Sprint 66 (1/26 - 2/8) | Sprint 67 (2/9 - 2/22) | Sprint 68 (2/23 - 3/8) | Sprint 69 (3/9 - 3/22) | Sprint 70 (3/23 - 4/5)
My VA
Payment updates | Discovery | Design | Design/Research prep/Build | Research/Build | Finish build | QA | Pre-launch | Pre-launch | Launch 25 - 50% | Launch 100%
User roles & permissions research | Synthesis & read-out
Single on-site notification MVP (Debt notification) | Samara to do background research | Re-define project/Design/BE Build | Design/Research prep/Build | Research/Build | Finish build | QA | Pre-launch | Pre-launch | Launch 25 - 50% | Launch 100%
Potential: Unauth homepage updates |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Potential: Health apartment updates |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Potential: Updates if new user role is added
Profile
Personal information updates | Research prep/FE build | Research/FE build/Start BE build | BE/FE build | BE/FE build | Finish build/QA | Pre-launch | Pre-launch | Launch 25 - 50% | Launch 100%
Bad address indicator | Samara to do background research | Team discovery; BE discovery | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Notification preferences | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD

## Planning by person
Planning by person
Sprints | Tressa | Liz | Christina | Erik | Taylor | Zach | Lihan
Sprint 61 (11/17 - 11/30) | Add payment info to My VA; Discuss alerts pivot | User roles research; Profile backlog | Personal information updates; Profile backlog in partnership with Liz | My VA: A couple tickets in the backlog; Profile backlog | Profile backlog | Personal information updates; Profile backlog if it doesn't conflict with other projects | Hopefully get started on personal information work; If not, can support other team if we decide to not continue with VANotify integration
Sprint 62 (12/1 - 12/14)
Sprint 63 (12/15 - 12/28)
Sprint 64 (12/29 - 1/11)
Sprint 65 (1/12 - 1/25)
Sprint 66 (1/26 - 2/8)
Sprint 67 (2/9 - 2/22)
Sprint 68 (2/23 - 3/8)
Sprint 69 (3/9 - 3/22)
Sprint 70 (3/23 - 4/5)

## Task list for projects
General project tasks (updated April 2021)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings