## Sheet1
Project Name | VA.gov Modernization
Test Scenario | Alerts & Operating Status
Reference Documentation | URL of specifications or comps
Created By | Jeff Brauer
Creation Date | 2019-12-17
TEST CASE ID | TEST SCENARIO | PRE-CONDITION | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS (PASS/FAIL)
Alerts & Operating Status - 001 | Create Information Banner Alert - Global VAMC | User has drupal login | 1- Navigate to /vamc-alerts-and-statuses |  | Information Alert banner is displayed on all VAMC pages for the selected VAMC with the appropriate blue style
|  | User has section access to at least 1 VAMC | 2- Click "Add Banner Alert" |  | Operating status page includes content from Situation Information block
|  | User has permissions to create alerts and edit operating status | 3- Required fields are populated
|  | User has build and deploy content permission | 4- Default calls to action are left as-is
5- Published checkbox is checked
6- Click Save
7- Content > build and deploy content button is clicked
Alerts & Operating Status - 002 | Create Warning Banner Alert - Global VAMC | User has drupal login | 1- Navigate to /vamc-alerts-and-statuses |  | Warning Alert banner is displayed on all VAMC pages for the selected VAMC with the appropriate red style
|  | User has section access to at least 1 VAMC | 2- Click "Add Banner Alert" (or edit existing)
|  | User has permissions to create alerts and edit operating status | 3- Required fields are populated
|  | User has build and deploy content permission | 4- Default calls to action are left as-is
5- Published checkbox is checked
6- Click Save
7- Content > build and deploy content button is clicked
Alerts & Operating Status - 003 | Create Banner Alert - Limit to VAMC Landing and Operating Status Pages | User has drupal login | 1- Navigate to /vamc-alerts-and-statuses |  | Alert banner is displayed on VAMC landing page and operating status page only for the selected VAMC
|  | User has section access to at least 1 VAMC | 2- Click "Add Banner Alert" (or edit existing)
|  | User has permissions to create alerts and edit operating status | 3- Required fields are populated
|  | User has build and deploy content permission | 4- Checkbox is selected to restrict display of banner to vamc landing page and operating status page only
5- Default calls to action are left as-is
6- Published checkbox is checked
7- Click Save
8- Content > build and deploy content button is clicked
Alerts & Operating Status - 004 | Create Banner Alert - Dismissable | User has drupal login | 1- Navigate to /vamc-alerts-and-statuses |  | Alert banner has an X at the top right.
|  | User has section access to at least 1 VAMC | 2- Click "Add Banner Alert" (or edit existing) |  | Clicking the X will no longer display the alert banner to the user until he/she clears cookies
|  | User has permissions to create alerts and edit operating status | 3- Required fields are populated
|  | User has build and deploy content permission | 4- "Alert Dismissable?" Checkbox is selected
5- Default calls to action are left as-is
6- Published checkbox is checked
7- Click Save
8- Content > build and deploy content button is clicked
Alerts & Operating Status - 005 | Create Banner Alert - Change Calls to Action | User has drupal login | 1- Navigate to /vamc-alerts-and-statuses |  | Alert banner has two calls to action: 1- Subscribe to email updates 2- Find other VA facilities near you
|  | User has section access to at least 1 VAMC | 2- Click "Add Banner Alert" (or edit existing) |  | Alert banner does NOT include the CTA "Get updates on affected services and facilities"
|  | User has permissions to create alerts and edit operating status | 3- Required fields are populated
|  | User has build and deploy content permission | 4- Check call to action "Display 'Find other VA facilities near you' link" and deselect "Display 'Get updates on affected services and facilities' link"
5- Published checkbox is checked
6- Click Save
7- Content > build and deploy content button is clicked
Alerts & Operating Status - 006 | Create situation update | User has drupal login | 1- Navigate to /vamc-alerts-and-statuses |  | Situation updates are displayed on the operating status page for the VAMC with the most recent situation update on top
|  | User has section access to at least 1 VAMC | 2- Edit an existing banner alert
|  | User has permissions to create alerts and edit operating status | 3- Click "Add Situation Update" button
|  | User has build and deploy content permission | 4- Populate current date and time
5- Add content to "update" field
6- Add second situation update
7- Populate more recent date and time
8- Save the node
9- Content > build and deploy content button is clicked
Alerts & Operating Status - 007 | Create Banner Alert - Send Gov-Delivery Email | User has drupal login | 1- Navigate to /vamc-alerts-and-statuses |  | After alert is published on the site, user receives an email with the alert information and a link back to the respective VAMC operating status page.
|  | User has section access to at least 1 VAMC | 2- Click "Add Banner Alert" (or edit existing)
|  | User has permissions to create alerts and edit operating status | 3- Required fields are populated
|  | User has build and deploy content permission | 4- Checkbox is selected tosend email to subscribers via GovDelivery
|  | User has subscribed to emergency alerts for the VAMC. For Pittsburgh, this may be done here: https://public.govdelivery.com/accounts/USVHA/subscriber/new?topic_id=396 | 5- Default calls to action are left as-is
6- Published checkbox is checked
7- Click Save
8- Content > build and deploy content button is clicked
Alerts & Operating Status - 008 | Situation update - Send Gov-Delivery Email | User has drupal login | 1- Navigate to /vamc-alerts-and-statuses |  | After situation updates is displayed on the operating status page, user receives an email with the situation update information and a link back to the respective VAMC operating status page.
|  | User has section access to at least 1 VAMC | 2- Edit an existing banner alert
|  | User has permissions to create alerts and edit operating status | 3- Click "Add Situation Update" button
|  | User has build and deploy content permission | 4- Populate current date and time
|  | User has subscribed to emergency alerts for the VAMC. For Pittsburgh, this may be done here: https://public.govdelivery.com/accounts/USVHA/subscriber/new?topic_id=396 | 5- Add content to "update" field
6- Checkbox is selected to send email to subscribers via GovDelivery
7- Save the node
8- Content > build and deploy content button is clicked