## Triage Retro (1)
Went well | To improve | Action items
we are good at coming up with bodies of work based on issues we see through the platform (4 votes) | we do have some stale tickets that are lacking in clear AC/tasks (6 votes) | Adjust standup schedule to Mon, Tue, Thur - AP (0 votes)
Sprint Planning has become easier with everyone creating and moving tickets with free will. (3 votes) | Mon/Wed/Fri standups has some pitfalls, for example friday standup doesnt feel all that valuable to me since my week is nearly done already (3 votes) | Update the triage docs https://github.com/department-of-veterans-affairs/va.gov-team/blob/master/teams/vsp/teams/triage/On-point%20Rotation.md (0 votes)
we've reduced overall sentry noise --- Sentry noise is at a minimum (2 votes) | Incorporating call center into triage items. This will come over time. (3 votes) | Brainstorm more encompassing bodies of future works - "big tasks", projects or initiatives (0 votes)
we are good at grooming as we go/tidying our board. or at least approach it --- overall we do well to document our tickets as thoroughly as possible (2 votes) | Epics/Super Epics are hard to visualize and understand --- Too many Epic Categories --- the multiple epics boards are frustrating when trying to understand current/future work, (2 votes)
pair programming :) (1 votes) | We stopped following our sentry alerts rotation, probably because it was never formalized anywhere in writing (2 votes)
we seem to have a good team rapport and no jerks --- Everyone on the team is very helpful and always available within a reasonable amount of time (0 votes) | PR Reviews. They continue to overflow my inbox and I have difficulty managing them (1 votes)
Supporting the VFS teams has been much more manageable lately. (0 votes) | Not sure if there's anything to _improve_ here, but we have three or four separate areas of concern in wrapped up in one team: FE, BE, DevOps, Call Center. The goals / responsibilities of each don't often overlap. (1 votes)
Generated by FunRetro.io