## VA checklist
Page or item | Area | Task (links go to VA pages on Github) | Approach | Status (if specific task)
All | All | Understand the VA Collaboration process |  | done
All | All | Understand how to build a form at the VA (with design) |  | in progress
All | Content | Fit general form standards (chapters etc.) |  | in progress
All | Content | Ensure spelling and grammar etc. and right word choices (working with Peggy on this) | VA Design page on word-list | to do
All | Metrics | Tie everything back to user research and metrics |  | in progress
All | All | Tackle the UX Debt log | Github | in progress
All | Usability | Look at previously identified usability challenges and make sure we address these | see usability tab | to do
Accessibility (from the VA) |  | See notes from initial call with Trevor
All | accessibility | Test with screenreaders | (see VoiceOver guide and see cross-platform guide and ask for a demo if this is new to you) | to do
All | accessibility | Seek a wide variety of users for research and testing, including people with disabilities, other impairments, and those with limited digital experience | (To understand the problems to address ahead of time outside of Trevor's work) | to do
All | accessibility | Reuse components from design system | Already been tested for Section 508 - going to mark this as closed because dev team is doing this and we know to minimize custom component creation | done
All | accessibility | Use Formation’s color palette and typography | Going to mark this as closed because design is doing this, but will also check https://whocanuse.com/ | closed
All | accessibility | Test using simplified process for VA Section 508 compliance | (automated tools for testing plus manual) | to do
All | accessibility | Accessibility Dev Review Step-by-Step using Axe etc. | WCAG best practices on coding | done
All | accessibility | Full accessibility process |  | to do
All | accessibility | Usability testing for accessibility checklist
All | accessibility | Accessibility Staging Review | This is extremely detailed but valuable to go through. Let's look at Content resize as we go | to do
All | accessibility | Another list of links to go through including dev tools | https://docs.google.com/document/d/1Mw3aJGm-AbLlWMmVUjybI7aQsjtnXR8nZ_ioEBQfYVA/edit | to do
Usability (from VA)
All | usability | New design patterns have been vetted by DSVA and documented |  | to do
All | usability | Mobile, tablet, and desktop breakpoints have been accounted for | Can we confirm if we need to accomodate for tablet? If we do the Content Resize check and it's readable, is that ok? | to do
All | usability | Correct use of design patterns in context |  | in progress
All | usability | Form chapters in place |  | in progress
All | usability | Privacy policy is present |  | to do
All | usability | Address form follows pattern if applicable |  | in progress
All | usability | Name form follows pattern if applicable | Form Labels | in progress
All | usability | Correct use of typography |  | ongoing
All | usability | Padding and spacing applied appropriately |  | in progress
All | usability | Form components used correctly in context |  | in progress
All | usability | Consistent use of iconography |  | in progress
All | usability | Colors use are consistent with color palette |  | in progress
All | usability | Primary and secondary CTA buttons used correctly in context |  | in progress
All | usability | :hover and :focus states have been accounted for and are consistent with design patterns | Have separate story and create these? | to do
All | usability | Alert messages have been used appropriately | See card on board for alert messages | to do
All | usability | Error states have been accounted for and used appropriately | (https://design.va.gov/patterns/form-feedback) Have separate story and create these? | to do
All | usability | Loading indicators have been used where appropriate | Have separate story and create these? | to do
All | usability | Empty states have been accounted for (if applicable) | Have separate story and create these? | to do
All | usability | Full/complete states have been accounted for (if applicable) | How are they defininig full states? Non empty? | to do
Product development (from the VA)
is my product... | ...usable (for ALL users)?
|  | Usability testing indicates new changes improve / don't worsen back-of-house VA employee experience |  | to do
|  | Usability testing indicates new changes enable users to do what they need to do * |  | to do
|  | Everything is 508 Accessible and there are no Sev 1 accessibility bugs * |  | to do
|  | Everything is written in plain language * | Ensure writing conforms to content strategy guidelines (also great list here). Ensure Veteran is capitalized. | to do
|  | Everything is consistent with VA's Design System * |  | to do
|  | Downtime notifications and error messages are documented |  | to do
|  | End-to-end manual QA is complete and no Sev1 bugs * |  | to do
|  | End-to-end UAT(with real users) complete and no Sev1 bugs |  | to do
|  | Availability and latency targets are defined * |  | to do
...findable?
|  | URL, nav, bread crumbs, and cross-links are consistent with VA's style guide and map to the user's mental model * |  | to do
|  | SEO is baked into everything |  | to do
|  | Static entrance/intro content is in place * |  | to do
|  | Redirects (if necessary) from legacy tools/pages are in place |  | to do
|  | Changes adhere to DEPO's 7 Digital Modernization Principles |  | to do
|  | Changes have appropriate ATO |  | to do
...measurable?
|  | KPIs are defined and tracked |  | to do
|  | Feature is included in the weekly Product Health Report |  | to do
|  | Google Analytics / Google Tag Manager setup is complete * |  | to do
|  | Phased, data-informed release plan is complete * |  | to do
|  | Monitoring is setup correctly and working * |  | to do
...secure and reliable?
|  | Users' private data is safe, including not logging PII * |  | to do
|  | Feature doesn't introduce new vulnerabilities * |  | to do
|  | Playbook exists on most likely failure modes and how to respond quickly to issues * |  | to do
|  | The feature has 90% unit test coverage, running in CI/CD |  | to do
|  | Feature can handle anticipated load and traffic spikes, with a completed load test |  | to do
|  | Rate limits are set |  | to do
... supportable?
|  | Dashboards and alerts are set up for finding and investigating issues |  | to do
|  | Point of contact are documented for the app itself and any new backend dependencies * |  | to do
|  | There's a Product Outline |  | done
|  | Contact centers know how to help users who call in about the feature * |  | to do
|  | ...marketable? |  | to do
|  | Product brief (with visuals), outlining the value and functionality of your product is in github |  | to do
|  | You've done a Go/No Go meeting |  | to do
All | General | Incorporated feedback from Showcases and Stakeholders | See next tab
All | General | Incorporated feedback individual tickets | Trevor on accessibility etc., any design community comments | to do
All | General | Accessiblity Post Launch Audit | manual testing with mobile and assistive technology | to do

## feedback from VA SMEs
Story | Source (TW, VA) | Type and link to Github | Item | Description what needs to be changed, severity (must vs. nice to have) if it's a new story etc. etc. | Severity (must vs. nice to have according to VA SMEs) | Status (open = to do, in progress = actively being worked on, closed = done) | Update: Added to backlog, link to story etc. | Comments
First round of feedback early (August to Nov.)
45 | TW | Feedback | Think about A/B testing | VA doesn't have any infrastructure - usability testing? instead? |  | Open |  | Qaysar posted on Slack about that recently
45 | TW | Feedback | Mail | Is US Mail still supported response type, per The Paperwork Reduction Act? |  | Open
45 | VA - Content | Feedback | Landing page | Will there be a landing or intro page that takes users into the IRIS form? |  | Open
45 | VA - IA | Feedback | Scrubbing of comments | Do the current forms do any scrubbing of comments prior to submit (i.e. language, PII, etc) and displaying on the review and confirmation screen? |  | Open
45 | VA - IA | Feedback | Service complaint | What does "service complaint" mean? is that a complaint against a VA service? Can users use this form to file a complaint as well as ask questions? |  | Open |  | yes they can do both - I changed it to be 'complaint' but we can also update the help tooltip
45 | VA - IA | Feedback | Country | Is "country" where they are or where they are from? |  | Open |  | It's where they are currently - do we need the change this
45 | VA - IA | Feedback | Type of inquiry | Why do we need type of inquiry? If it’s a complaint does it just get shuffled to the bottom? Isn't "status" more of a topic than a type? |  | Open
45 | VA - IA | Feedback | Relationships | Simplify Relationship to Veteran - i.e. is "Child/Dependent" specific enough rather than separate options for daugher, dependent child, son, helpless child, etc? should there be an "other"? |  | Open
n/a | n/a | n/a | Required vs. required | https://design.va.gov/patterns/form-templates says (*required) but Sketch says (*Required) - which should we use? I've seen both in forms |  | Open
Feedback pre usability testing (Nov. 2020 with VA design SMEs as part of collab cycle) - see cards in backlog which are tracking these
| VA - Design | Feedback | Labels | Update the form labels to follow plain-language guidelines. Eg. “Date of Birth” should be “Your date of birth” | Must | Open | 212 | To do
| VA - IA | Feedback | Form and Public Web sites team | Must determine how this form relates to the "Contact us" page being worked on by the Public Websites page in order to determine H1, breadcrumb and navigation path for this form. | Must | Open |  | Pending discussion with Public Web sites team
| VA - IA | Feedback | H1 | Your H1 is duplicative to the PW (Public Web site) page being created - they should each have distinctive H1s as to the purpose/intent of the page | Must | Open |  | Pending discussion with Public Web sites team
| VA - IA | Feedback | Breadcrumb and Public Web site | The breadcrumb should very closely match the H1 and accurately show where this page lives within the structure of the site - does it live as a child of the PW page or at the same level? | Must | Open |  | Pending discussion with Public Web sites team
| VA - IA | Feedback | URL | The URL is currently different than the H1/breadcrumb and should be similar. Also need to determine if this page is a child of the PW page. | Must | Open |  | Pending discussion with Public Web sites team
| VA - IA | Feedback | Page within navigation | Should this page stand on its own and be accessible from areas of the site/navigational paths that the Contact us Drupal page is not? In other words, can/should it live independently of that | Must | Open |  | Pending discussion with Public Web sites team
| VA - QA | Feedback (in comments) | Integrating QA | I noticed that you marked your Quality Assurance related artifacts as N/A. While it is obviously still early in the SDLC for your product, I encourage teams to begin stubbing out test cases as early as possible. A quick perusal of TestRail reveals a decent amount of activity in your project -- which is great! I see a collection of test cases here. These test cases appear to be a11y focused, and you've already begun collecting results based on your prototypes (I assume). Awesome! I would encourage you to consider expanding your test cases with manual test cases recorded in TestRail, automated tests in Cypress(which you can automatically report to TestRail), and potentially load tests given the parameters of your product. | Must | Open | TBD
RESOLVED
45 | TW | Other | Name of product and labels | Can they answer "prefer not to answer" to any of the inputs? |  | Closed | Working with IA team and will update there | Working with IA team and will update there
45 | TW | Feedback | Font sizes | Any concerns on mobile fonts sizes |  | Closed | N/a - Sketch file has mobile standards | N/a - Sketch file has mobile standards
45 | TW | Feedback | Field lengths | Should they only provide email/phone/mail based on their contact preference? |  | Closed | n/a | I updated the widths to be shorter; the Sketch file I was using didn't have them but now will use the VA Design Pattern library as first point of reference
45 | TW | Feedback | Country dro pdown | Can some of the form fields and number of fields be simplified - get minimum info for purposes of routing/triaging - but keep it easy for the user to fill out - examples: |  | Closed | Added to story | Added to story
45 | VA - Accessibility | Feedback | Email field | Email must be validated with a second input to confirm user is entering their own email, and it's well-formed (looks like an email address). One of the other teams has recently had this issue, which is captured in #12585 |  | Closed |  | added to wireframes
45 | VA - Accessibility | Feedback | Country drop down | Country <select> should be pre-selected to "United States of America" |  | Closed |  | added note to story
45 | VA - IA | Feedback | Forms |  | VA - Design | Feedback | Step name and H2 | On each form page, it seems like the Step name and the h2 underneath are saying the same thing, and they are different sizes on the different pages (“Your message,” “Veteran service information,” “Contact information,” Normally on forms, we don’t have that 2nd h2 after the “Step 1 of 6…” (See the Health Care application as an example, screenshot below). Please remove that 2nd h2 on each of the form pages - removing it clarifies the hierarchy and keeps it consistent with other forms across VA.gov. | Must | Closed | #98
45 | VA - IA | Feedback | Users | do we want to capture biographical first and then inquiry? **I would recommend personal information first, as it seems the natural flow and sets up the form. This also follows the pattern of our other forms where we collect personal and contact information first. ** |  | Closed |  | am doing in wireframes
45 | VA - Content | Feedback | Form builder | I recommend creating a confirmation page that lets users know their question has been submitted with a general timeframe on when they will get a response |  | Closed |  | Yes, we're doing this
45 | VA - Content | Feedback | Type of questions | Are there question topics? Just wondering if we need to provide guidance to the user about what type of questions are appropriate to ask in this form? |  | Closed |  | Covered in the type of help tool tip we'll include in a future story
45 | TW | Feedback | Content mgt. | Do we need to review content and copy of the language used in the form fields and helper text? |  | Closed |  | Yes - will work with Peggy, content strategy person
45 | TW | Feedback | Single vs. mult-pate | Is there more burden for filling out single page form vs multi-page form? |  | Closed |  | Since the default in VA is multi-page, I'm going to say multi-page is fine - will close this
45 | VA - IA | Feedback | App name | This may be revised to Contact Us rather than Ask a Query - meeting with the IA team to discuss this. |  | Closed |  | This is on the radar for our meeting with IA
45 | TW | Feedback | Search field for drop downs | Are combo-boxes with search fields supported within VA Design library? These will enhance usability for Type of Inquiry/Topic dropdowns |  | Closed | yes - 68 | addressing in 68
45 | TW | Feedback | Testing Strategies | Supported browsers, devices, screen readers |  | Closed |  | We have updated list from QA session
45 | VA - IA | Feedback | " " | EXAMPLE: Does suffix need to go up to VI? |  | Closed |  | addressed in story
45 | VA - IA | Feedback | Users | What if the person completing this form is not related to or asking on behalf of a Veteran - i.e. maybe a realtor is asking about something related to va backed home loans? |  | Closed |  | There is 'a General Question (Vet Info Not Needed) ' option
45 | TW | Feedback | Form expiration date | OMB expiration date was 11/30/2019. Now that the form is expired and we are working on a new design, what's the new process of getting a new expiration date? |  | Closed |  | added to UX debt
45 | TW | Feedback | Sub sections | break down the form fields into subsections? The fields would all still be on the same page but I wonder if adding a visible header for, "General Information," "Service Information," "Contact Information," etc. to break up the vertical flow of the form a bit could help. |  | Closed |  | Working on this in story 89
82 | VA - Content | Feedback | general feedbak on forms | Peggy provided feedback in the ticket which we're incorporating |  | Closed |  | TBD
45 | VA - IA | Feedback | Form builder | Need to determine if we will have all screens of the standard form - introduction page is in question - review, confirmation are recommended |  | closed |  | Am actively tracking this as we add new screens
45 | VA - IA | Feedback | Form fields | Can some of the form fields and number of fields be simplified - get minimum info for purposes of routing/triaging - but keep it easy for the user to fill out - examples: |  | Closed |  | Marking this as closed as LOBs are simplifying
45 | VA - Accessibility | Feedback | Accessibility review | Review new screens with accessibility specialist as they are defined. This can be an async review, or a more formal meeting invite, whichever works best for your team. |  | Closed |  | Meeting with Trevor
45 | VA - Accessibility | Feedback | Wizard | Trevor mentioned on 8/26 meeting with Rachel, look at possibility of starting this out as a wizard (https://design.va.gov/patterns/wizards) BEFORE the form - so asking if this is general or GI Bill related, for example |  | Closed |  | Have this as a possible story
45 | TW | Feedback | Form estimate | How do we assess the new form's burden estimate? |  | Closed |  | we have a card to do this
45 | TW | Feedback | Grouping content | Dropping a note for grouping together certain elements such as First Name & Last Name, possibly Salutation, etc. <-- yes, we'll revisit the grouping of items and see the standard |  | Closed |  | asking users in usability testing re: grouping
45 | TW | Feedback | UX | How do we start designing user experience of having a seamless experience from entering one entry point? |  | Closed |  | Part of Get Help work we'll do Dec. onward
45 | VA - IA | Feedback | Additional help content | Will there be additional content either on the page or in a separate page for more indepth information about the form, introduction to the form, etc. Would also like to discuss this in the context of an overall site "Contact us" page/experience. |  | Closed |  | Yes, in future stories - can add note in card.
45 | TW | Feedback | Form validation | Are there too many eager form-validations triggered by default in existing IRIS form (Preferred response type as phone number, and validating phone number is filled)? |  | Closed |  | Marking this as closed as Lines of Business are simplifying the fields
45 | VA - IA | Feedback | Forms | If they are 3 independent forms, what is the focus/scope/purpose of each one compared to the other? |  | Closed |  | Addressed in discussion with lines of business
45 | VA - IA | Feedback | Contact preferences | Should they only provide email/phone/mail based on their contact preference? |  | Closed |  | Yes, this is solified with lines of business
45 | VA - Content | Feedback | FAQs | Will the legacy FAQs be migrated over with this form? If so, I recommend the FAQ going on this landing/intro page. |  | Closed |  | We're addressing how to integrate the FAQs as part of the triaging story and working with the Resources and Support team
45 | VA - IA | Feedback | Users | This implies that this form is just about asking about benefits -another option for this label could be= What is your relationship to the Veteran? |  | Closed |  | Added to wireframes - will confirm with team
| VA - IA | Feedback | Research question | I would recommend asking users where they would go to find a tool that would allow them to submit a question or comment to VA, so you can gather insights on what they might call the form, or where they might look for it. In addition, you could also have them elaborate on what they expect to see behind a "Contact us" option before they click on the link - this could give us insight on the relationship of this form and other methods of contacting VA. | Must | Closed |  | added to conversation guide
| VA - Design | Feedback | Step name and H2 | On each form page, it seems like the Step name and the h2 underneath are saying the same thing, and they are different sizes on the different pages (“Your message,” “Veteran service information,” “Contact information,” Normally on forms, we don’t have that 2nd h2 after the “Step 1 of 6…” (See the Health Care application as an example, screenshot below). Please remove that 2nd h2 on each of the form pages - removing it clarifies the hierarchy and keeps it consistent with other forms across VA.gov. | Must | Closed | #98
| VA - IA | Feedback | Multiple forms | Will there be multiple forms like this as there is today (general vs GI Bill)? | Must | Closed |  | Yes, combining GI Bill and IRIS
| VA - IA | Feedback | Get help' footer | Add the 'Get help’ footer so can click if they are having trouble filling out the form | Must | Closed | 212

## issues
Page | Problem | Solutions | Metrics | Severity (i.e. must vs. nice to have) May not need this - revisit) | Added to backlog? | Goal | Example | Status (open = to do; closed = addressed) | Comments
This document was created during onboarding where the TW team looked at areas to improve, and started to incorporate these into the backlog
Content | spelling errors in content | content refresh; links in content that throw 404 (Need a report of how many 404s - curious how many there are and if people report this) |  |  |  |  | https://iris.custhelp.va.gov/app/answers/detail/a_id/915/kw/eligiblity https://iris.custhelp.va.gov/app/answers/detail/a_id/181/kw/cremation/related/1
Ask a question | Paragraphs. Do users need to hear ‘Since we have more than one million records in the IRIS system, it looks for an EXACT match of all identifying information, including your first name, last name, suffix, and email address’ | Can we use bullets for some of the help? Need to dive into content strategy here as well.
Ask a question | input validation | date formatting to be automated rather than just showing a tooltip
Ask a question | Dropdown menu - geographical distribution can be confusing | how does a user know they fall into a regional area, and if they don't?
Ask a question | Address | address validation against USPS mail service
Ask a question | Input validation errors shown at the top of a long form, and the user may not see it | highlight fields
Ask a question | duplicate submissions | transparency; faster load time
Ask a question |  |  |  |  | #89 |  |  |  | Do users know what to do if they are still in active duty? Is the service end date field needed always/correct verbiage? Or if they have served in more than one branch, which do they input in the IRIS form?
Landing page | Visual style | Inconsistent sizes and styles of buttons. |  | TBD if doing
Landing page | Content usefulness and wordiness | We should see what legally needs to be on this page (Paperwork reduction act) vs. perceived friendliness. Streamline wherever possible | TBD | TBD if doing
Landing page | No hierarchy of content | If some content like locations is necessary, group locations and phone numbers together in an area |  | TBD if doing
Landing page | Clicking on the Ask a Question on https://iris.custhelp.va.gov/ in the nav just takes you to the landing page again |  |  | TBD if doing
Search results | Too many search results | 1. Show ways to refine/filter content and sort by direction by default instead of having to click the Advanced Search 2. Deprecate old content (What's the definition of old content?) 3. Show timestamps of the articles and category 4. Show blurb text (100 characters) of the matching search results in highlight/bold |  |  |  |  | (Change of Address returns 196 results, eligibility returns 527 results
Search results | Reduce human error when searching | typeahead autocompletion suggestions
Search results | Suggestions | synonyms, spelling errors are caught automatically
Search results | old timestamps could confuse or add doubt to user experience | content refresh and reviewed
Search results | difficult readability of suggested search terms because the free text are in one line; only show underline when hovered over
Search results | Loading icon
Search results | zebra stripes
Search results | visual alignment | inconsistent content page margins left and right, inconsistent font sizes
Search results | Answers others found helpful | how is this calculated?
Share by email | gmail immediately flags as spam, report phishing
Share by email | message only has a title and a link to redirect user
FAQ | Two search bars might cause confusion for the user about where to input their query
FAQ | FAQs depend on search so you have to know what you’re looking for | Could we have tagging or FAQs by area? Where do others indicate that content is help (‘Answers others found helpful’) - I don’t see a place to mark as helpful (may have missed it).
FAQ | Content formatting inconsistent | On this page (https://iris.custhelp.va.gov/app/answers/detail/a_id/423) we have a different font style - some of these are showing inconsistently, not sure if stylesheet or poor formatting In general the styling lacks visual hierarchy (using font styles etc.)
All | blog post on IRIS with customer complaints

## usability testing
Story | Hypothesis to validate | Details | Metrics we aim to improve (how to validate our assumptions) | Status (to test or not to test) | Comments
For usability testing, consider what we know, what we don't know, if any of the above are assumptions we need to validate for MVP, and what data would validate our assumptions. As we conduct usability testing update the results on Github
89 | Are we missing any fields from the Veterans' service history about their dates? I.e. Most recent entry date |  |  | added to usability testing doc | Validate with which stakeholder - can address in Showcase? For testing, ask users if anything's missing.
| Are people comfortable navigating with a chatbot or wizard step by step rather than the form? |  |  | added to usability testing doc | https://www.smashingmagazine.com/2019/05/chatbots-forms-mobile/ See also: VA wizards
| Is the order of content correct (i.e. are order of fields from IRIS, GI Bill and MHV intuitive if they're combined)? |  |  | added to usability testing doc | May not need actual test, but put in exit survey after test to validate order of content
302 | rearranging the form flow seems more intuitive rather than replicating current state |  |  |  | I think we revisit the flow as we develop and validate with users