## Sequencing
Sprint Dates | Oct | Nov |  | Dec |  |  | Jan |  | Feb |  | March |  | April |  | May |  | June
| 10/16-11/3 | 11/4-11/17 | 11/18-12/1 | 12/2-12/15 | 12/16-1/5 | HOLIDAYS | 1/6-1/19 | 1/20-2/2 | 2/3-2/16 | 2/17-3/2 | 3/3-3/16 | 3/17-3/30 | 3/31-4/13 | 4/14-4/27 | 4/28-5/11 | 5/12-5/25 | 5/26-6/8 | 6/9-6/22 | 6/23-7/6
Capacity (velocity in pts) | 17 | 20 | 14 | 19 | 12 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
External Deadlines or Restrictions |  | 11/11: VA.gov Deployment freeze | 11/25-11/27: VA.gov Deployment freeze |  | 12/13-1/1: VA.gov Deployment freeze
|  |  | Nov/Dec: Requirements complete (PIRIS) | 12/1: Decision on MVP Scope | [8 empty] | Early April: Another Oracle extension?
Go-Live/Prod Readiness | [8 empty] | Bug Bash #1 |  |  | Figure out URL redirects with Mikki | Bug Bash #2
[5 empty] | Security Review for Document Upload with S3 |  |  | [Placeholder] Browser testing outcomes | [Placeholder] Device testing outcomes | [Placeholder] Security testing outcomes | [Placeholder] Performance testing outcomes | [Placeholder] Create Product Guide and overview video for CCs |  | Performance/Load testing (e2e)? | Fill out External Service template about PATS-R (devops repo)
VSP Collab Cycle and Design |  | Analytics: KPIs Dashboard set up | [5 empty] | IA Request | A11y & 508 Audit | Privacy and Security Review |  | Contact Center Review | Staging Review | [5 empty] | Post-Launch Check-in
|  |  |  | 1st Round of Usability Testing: IRIS Form |  |  | Finalize User Journey mapping with external teams |  | 2nd Round of Usability Testing: Flow from Landing Page to Form (tentative on ALL drop downs integrated) |  |  | GTM (+ set up dashboard with Analytics team and revisit KPIs) |  | UAT
IRIS AAQ Form | NCA topics |  |  | GI Bill topics | Document Upload |  | Document Upload | [5 empty] | Code freeze?
| LGY topics |  |  | User journey mapping | Usability Testing Synthesis |  | Landing Page?
|  |  | Usability tweaks | Topic-wise auth |  |  | Topic-wise auth |  |  | Error Handling/Notifications
Secure Messaging |  | Understand SM API dependencies on PATS-R | Review old VA.gov SM codebase |  |  |  |  | Secure Messaging capabilities
PATS-R Integration | [6 empty] | PATS-R Integration

## Backlog
Milestone
IRIS Form (feature parity) | NCA values | LGY values | document upload | email notifications | UX debt
GI Bill Form (feature parity)
MHV Form (feature parity)
Contact Us Landing Page
IA Request | URL redirection | bookmarks | deep links
Analytics KPI Dashboard
Usability testing
Contact Center Review
Staging Review
Privacy and Security Review
Full Accessibility and 508 Office Audit
Post-launch Checkin
Integration with PATS-R
VA.gov auth
Go-Live Strategy/Prod Readiness
Reporting | GTM
User Acceptance Testing (March)
Incorporate business approved values for Inquiry category dropdowns
Bug Bash (Early December)
Bug Bash (Early February)
Secure messaging (omnichannel?)
Deprecation (Iterative Go live)
Data migration

## Scope by Priority
TW Scope (as of Dec 15 2020) | Out of Scope (handled by other teams) | Out of Scope (deprioritized, not for MVP/June 2021)
Forms: Topic-wise authentication | Chatbot (Luciana, SRA team, __?) | RPA (TW implementation of happy path flow exists)
Forms: Document upload | Secure messaging (Portal capability?)
Go-Live Strategy
Landing Page (in coordination with PW team?)
If Oracle is extended beyond June 2021, it would make sense to pick RPA back up. When we began working on RPA originally, it was meant to be a short-term solution. Now, we still have many unknowns about error handling and addressing anything beyond the happy path flow and even if we completed it all by March (the date we gave Chante), it would only be in place for the phased rollout for maybe 3 months before all LOBs need to be integrated with PATS-R in June anyways.
RPA = short term solution, help get some LOBs to see the new experience sooner (phased rollout)