## Sheet1
Task | Responsible Party | PI8 S1 (6/20-7/3) | PI8 S2 (7/4-7/17) | PI8 S3 (7/18-7/31) | PI9 S1 (8/1-8/14) | PI9 S2 (8/15-8/28) | PI9 S3 (8/29-9/11) | PI10 S1 (9/12-9/25) | PI10 S2 (9/26-10/9) | PI10 S3 (10/10-10/23) | PI11 S1 (10/24-11/6) | PI11 S2 (11/7-) | LAUNCH (11/11)
Stand Up preview.va.gov
Obtain ESCCB clearance for va.gov domain | Wyatt | 10496
v1 of Jenkins build process for preview.va.gov
DNS set-up of preview.va.gov
Get in VAEC
Load testing new va.gov
Set up CDN on preview.va.gov
Single Sign-on (SSO)
Teamsite/Existing VA.gov Pages
Determine final solution for skinning VA.gov pages
Update Teamsite templates with skinning solution
Stand up a staging environment in Teamsite
Homepage
Hi-Fidelity designs | Mel/Andy
Build front-end in vets-website repo | Sophia
Build front-end on preview.va.gov
Link list for zone 1 | Mikki
Teaser text for zone 2 | Danielle
Header and Footer
Link list for global footer | Mikki
Build header components | Sophia
Build footer components | Sophia
Incorporate header and footer into VA.gov pages
Incorporate header and footer into vets.gov pages
Megamenu Navigation
Link list for each benefit menu | Mikki
Featured content for each benefit menu
Link list for 'About VA' menu | Mikki
Build megamenu components | Bill | 10551
Import megamenu components into Formation | Bill |  |  | 10344
Benefit Hubs
v1 of hub page design | Mel/Andy
Hub page design iterations | Mel/Andy
Build scaffolding of benefits hub pages | Sophia | 11109-11117
v1 of hub pages complete | Sophia |  |  | X
v1 of final hub pages live on preview.va.gov | Wyatt |  |  | X
Health Care Hub
VA.gov content audit & IA work | Danielle & Mikki
Link list (Get, Manage, More) | Mikki | 10352
Related resources and social media
Page content | Danielle | 11123
Help links/content
Disability Hub
VA.gov content audit & IA work | Danielle & Mikki
Link list (Get, Manage, More) | Mikki | 10539
Related resources and social media
Page content | Danielle | 11124
Help links/content
Education & Training Hub
VA.gov content audit & IA work | Danielle & Mikki
Link list (Get, Manage, More) | Mikki | 10540
Related resources and social media
Page content | Danielle
Help links/content
Careers & Employment Hub
VA.gov content audit & IA work | Danielle & Mikki
Link list (Get, Manage, More) | Mikki | 10541
Related resources and social media
Page content | Danielle
Help links/content
Burials & Memorials Hub
VA.gov content audit & IA work | Danielle & Mikki
Link list (Get, Manage, More) | Mikki | 10545
Related resources and social media
Page content | Danielle
Help links/content
Life Insurance Hub
VA.gov content audit & IA work | Danielle & Mikki
Link list (Get, Manage, More) | Mikki | 10542
Related resources and social media
Page content | Danielle
Help links/content
Records Hub
VA.gov content audit & IA work | Danielle & Mikki
Link list (Get, Manage, More) | Mikki | 10546
Related resources and social media
Page content | Danielle
Help links/content
Housing Assitance Hub
VA.gov content audit & IA work | Danielle & Mikki
Link list (Get, Manage, More) | Mikki | 10544
Related resources and social media
Page content | Danielle
Help links/content
Pension Hub
VA.gov content audit & IA work | Danielle & Mikki
Link list (Get, Manage, More) | Mikki | 10543
Related resources and social media
Page content | Danielle
Help links/content
Content
Design static page for authenticated tools | Andy |  |  | X
Content on static page for authenticated tools | Danielle |  |  |  | X | X
Build static page for authenticated tools | Bill |  |  |  |  | X | X
Rewrite benefits content | Danielle |  |  |  | X
Retire duplicative benefits content on VA.gov
Determine how 2nd, 3rd, and 4th level content maps to each benefit hub | Mikki
v1 of updated benefit IA to stakeholders | Mikki | [6 empty] | X
Final benefit IA schema | Mikki | [9 empty] | X
Move existing VA.gov pages into new IA schema
Analytics
Implement GA tracking for eBenefits |  | X
Implement GA tracking for MHV |  | X
Implement GA tracking for va.gov |  | X
Identify KPIs for for va.gov
Search
Set up search.gov on preview.va.gov |  |  |  | X
User Feedback & Help | [7 empty] | X
Secure Medallia instance
Incorporate Medallia script into new va.gov
v1 of Medallia questionnaire complete in Medallia portal
Send Medallia questionnaire for PRA approval
Vets.gov Branding Cleanup
Identify all references to 'vets.gov' in vets.gov content |  |  |  | 11018
Identify all references to sign-on in vets.gov content
Update vets.gov content with new sign-on language |  |  |  |  | X
Update vets.gov content with new VA.gov-centric language |  |  |  |  | X
Governance Decisions
Identify options for web editors to update content |  |  |  | X
Finalize solution for web editors to update content |  |  |  | X |  |  | X
URL Redirects
v1 of URL schema recommendations | Mikki |  |  | X
Implement new URL schema | Wyatt
Finalize solution for redirects on va.gov that go to vets.gov
Implement URL redirect solution
Training
Call Center Training | [9 empty] | X
Web Editors Training
In-Facility Training
VSOs Training
508/Accessibility
Launch
Identify technical contacts at NSOC
Identify technical contacts at EWIS
Testing
Team testing |  |  |  | X
Internal VA preview |  |  |  |  | X | X
User research with small groups of external users | [5 empty] | X
Launch beta on preview.va.gov for user testing | [6 empty] | X | X
Load & latency testing on preview.va.gov | [9 empty] | X | X