## IPP Roadmap
In-Person Proofing Roadmap | [6 empty] | Pilot 1 (5/20-5/23) - Fayetteville, AR | [10 empty] | Pilot 2 - Long Beach, CA
Resource |  | Sprint 44 |  | Sprint 45 |  | Sprint 46 |  | Sprint 47 |  | Sprint 48 |  | Sprint 49 |  | Sprint 50 |  | Sprint 51 |  | Sprint 52 |  | Sprint 53
|  | 2024-04-10 | 2024-04-17 | 2024-04-24 | 2024-05-01 | 2024-05-08 | 2024-05-15 | 2024-05-22 | 2024-05-29 | 2024-06-05 | 2024-06-12 | 2024-06-19 | 2024-06-26 | 2024-07-03 | 2024-07-10 | 2024-07-17 | 2024-07-24 | 2024-07-31 | 2024-08-07 | 2024-08-14 | 2024-08-21
Engineering | bar: 2024-04-24 to 2024-05-01; 2024-05-29 to 2024-07-03; 2024-07-17; 2024-08-07 to 2024-08-21
| LHDI | 2024-04-10: LHDI Onboarding (done) Deploy Application to LHDI Dev environment; 2024-07-10: Deploy to LHDI
|  | Development Countermeasures - Priority 9-10 and Priority 8 | [13 empty] | UAT
Design and Architecture Countermeasures - Priority 7 and Priority 8-9
| Accessibility | 2024-07-17: A11y Testing
| Data Dog | 2024-05-29: Data Dog Onboarding (Dev, Sophia P, Sofia K); 2024-06-12: Configure IPP App with Datadog; 2024-07-03: QA Testing for Datadog
| Data Model | 2024-04-10: Update Data model for Pilot 1 Application with data fields: validated_person : boolean - set to true when they login with IAL2 and AAL2 ial : string - would look something like "http://idmanagement.gov/ns/assurance/ial/2" aal : string - would look something like "http://idmanagement.gov/ns/assurance/aal/2?phishing_resistant=true" Other 5: email sub (Login.gov UUID) x509_subject x509_issuer x509_presented Two more that are obvious are: "given_name" "family_name" proofing_transaction_started_at and proofing_transaction_completed_at attributes as timestamps to the Case data object.; 2024-05-29: Update data model to include: post pilot for PA data. IAL AAL email UUID and x509 data fields are essential. mateo will update existing issue with data fields. Case data object can come after pilot. Collect PII; 2024-06-19: Tech Documentation for Data model
| Proofing Agent App Front End | 2024-04-24: Deploy design and content updates to PA screens; 2024-07-03: Deploy design updates to IPP application
| Veteran App Front End | 2024-04-24: Deploy design and content updates; 2024-07-03: Deploy design updates to IPP application
| Site Updates | 2024-04-24: Hardcode map content for participating site; 2024-07-03: Hardcode map content for participating site
| Feature Updates | 2024-05-29: Resolve continue button functionality
| Doc Checker | 2024-05-29: Discovery on data output of doc checker Update charter to clarify need for doc checker and value add Identify UI elements to design for doc checker; 2024-06-12: Deploy doc checker fields
| VA Notify | 2024-05-29: Identify VA Notify POC; 2024-06-05: Discovery on VA Notify integration to enable automated messaging to Veteran; 2024-07-03: Integrate VA Notify
| Form Validation for Errors | 2024-05-29: Identify data fields that require validation Review accessibility standards for error fields; 2024-06-12: Write code for error validation Deploy
| MPI | 2024-04-24: Get in touch with Identity Core to set up a meeting for VA verified accounts post Pilot 1; 2024-05-29: Test marking an account as VA verified Meet with Identity Core to discuss flagging users; identify alternative solution if not flaggin for manual verification Update IPP Charter on MPI as an authoritative source
| Authorizing VA Staff Access | 2024-05-29: Discovery on verifying approved VA staff
Design | bar: 2024-04-24 to 2024-05-01; 2024-05-29 to 2024-07-03; 2024-07-17; 2024-08-07 to 2024-08-21
|  | Design updates to PA facing screens | [8 empty] | Design updates for IPP application
|  | Content refinement for Pilot app | [7 empty] | Design Doc Checker fields |  | Create VA Notify Content | Deploy to VA Notify and Test
|  | Design landing page for proofing agent facing application | [7 empty] | Design error state UI (some mockups already exist)
Design pop up page between sign-in page for Veteran facing application and start of IPP flow
| Post Pilot-2 Design | 2024-04-10: Update service blueprint for walk-in flow; 2024-04-24: Search for Veteran on MPI flow/MPI data flow; 2024-05-08: Create reschedule/cancellation flow; 2024-05-29: Update service blueprint for walk-in flow
Research | bar: 2024-04-24 to 2024-05-01; 2024-05-29 to 2024-07-03; 2024-07-17; 2024-08-07 to 2024-08-21
| Finalize pilot one site and materials | 2024-04-10: Follow up with Jeanette on contacts from Susan; schedule one for pilot 1 and hold one for pilot 2; 2024-04-17: Sign executive leadership letter Identify authorized staff and set up training calls; 2024-04-24: Create signage for participating site; 2024-05-01: Finalize signage Print pilot material; 2024-05-29: Discovery on verifying approved VA staff; 2024-06-19: Sign executive leadership letter Identify authorized staff and set up training calls; 2024-06-26: Create signage for participating site; 2024-07-03: Finalize signage Print pilot material
| Test research sessions | 2024-04-17: Pilot session test run with team; 2024-05-01: Mock research session; 2024-06-19: Pilot session test run with team; 2024-07-03: Receive roster with participant info and dummy data; 2024-07-17: Pilot session test run with mock participant
| Coordinate with Perigean to set up study participants | 2024-04-17: Initiate KO call with Perigean; 2024-04-24: KO Call Receive roster with participant info and dummy data; 2024-05-01: Train and onboard authorized staff on Proofing Agent flow; 2024-05-22: Coordinate with Perigean on attendance of scheduled participants, gain consent from intercept participants, refer to notetaking tool when observing; 2024-06-19: Initiate KO call with Perigean; 2024-07-03: Train and onboard authorized staff on Proofing Agent flow
[5 empty] | Confirmation email prepped with participants | [8 empty] | Confirmation email prepped with participants
| Determine travel logisitics | 2024-04-17: Team discusses availability for the pilot and identifies onsite researchers; 2024-04-24: Researchers submit travel expenses, accessibility accomodations, and hotel bookings; 2024-05-22: Submit expenses for reimbursement; 2024-06-19: Team discusses availability for the pilot and identifies onsite researchers; 2024-06-26: Researchers submit travel expenses, accessibility accomodations, and hotel bookings; 2024-07-10: Coordinate with Perigean on attendance of scheduled participants, gain consent from intercept participants, refer to notetaking tool when observing; 2024-07-17: Submit expenses for reimbursement if needed
[9 empty] | Return to team with notes and start synthesis | Finalize synthesis; Identify recommendations | Report write up | [7 empty] | Return to team with notes and start synthesis Report write up Identify recommendations
| ID.me Shadowing | 2024-06-05: Shadow IPP Process; 2024-06-12: Synthesize findings
| Login.gov Shadowing | 2024-05-29: Research member completes IPP Records and reports experience; 2024-06-05: Shadow IPP Process; 2024-06-12: Synthesize findings
Post-Pilot Updates to IPP
Allow a Veteran to select a language
Design and develop form validation
Integration with State ID Validation App
Resolve map functionality for scaled launch
GIS site data integration for map
Allow Veteran to select a Puerto Rico address
Develop IAM/MPI lookup through IPP application, identify alternatives
Allow Veteran to cancel or reschedule
Lookup an existing Case Number
Send reminder email during 10 day window
Enable walk in without appointment
Identify fraud letter mechanism
IPP Governance and Authorization
| MPI as Authoritative Source | 2024-05-01: Phil walkthrough with Gus
| IPP Charter | 2024-05-01: Kirk walkthrough with Gus
ATO Discovery and Requirements Documentation on security countermeasures and how we satisfy them.
DIRA Statement Acceptance
Draft IPP Platform AoA
Login.gov Integration
Login.gov Integration with Veteran App (IDP)
Login.gov Integration with Proofing Agent App (IDP) - data exchancge, Discovery on exchanging case numbers, emails, and flagging once verified
Proofing Agent Application stores PII bundle on VA system; out of scope until we got Login's consent for enabling validated PII
Enable Validated PII on Login.gov Dependency on Login.gov consenting to allow flagged PII to move and be verified"
IPP Opt-in through Login.gov Beyond scope, requires offering IPP on Login.gov site
Develop integration with Login.gov via API
ID.me Integration
IPP Opt-in through ID.me Initiate digital ID integration Discovery research
Enable Validated PII on ID.me
Full Scale MVP Rollout
Identify 5 MVP Sites for rollout
VA Facility Onboarding
Launch MVP at Selected Sites
Develop Administrative System for Proofing Agents
Build an IPP Support Team/Process
Enable Power of Attorney pathway for Veterans unable to complete in person independently POA pathway beyond pilot 2 but can create design for process and research
Onboarding ALL VA Facilities
Onboarding non-VA Facilities
Support for VA Community
Enable a larger VA support community as Proofing Agents
Enable access to additional sources of data for remote verification
Expand IPP for Trusted Referees
Enabling Veteran caregivers to verify
Enable IPP to call directly from MPI to verify information
Expand IPP into Another Agency

## Original IPP Roadmap
In-Person Proofing Roadmap
Resource
|  | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01
IPP Platform Decision and Development
Discovery on VA.gov deployment
Draft IPP Platform AoA
LHDI Onboarding
Deploy Applications to LHDI
LHDI SecRel Remediations
IPP Application Development
Build Veteran Intake Application (front-end)
Build Proofing Agent Application (front-end)
Deploy Applications to LHDI
Login.gov Integration with Veteran App (IDP)
Login.gov Integration with Proofing Agent App (IDP)
Veteran Intake: Authentication request to Login.gov
Proofing Agent Application stores PII bundle on VA system
Integrate with VA Notify to send Veteran confirmation email
Update Veteran App after Usability Tests
Update Proofing Agent App after Usability Tests
IPP Usability Tests
Coordinate Research Recruitment with Perigean
Conduct SME Interviews with VA Staff
Synthesize Results from SME Interviews
Conduct Usability Tests with Veterans
Synthesize Results from Veteran Usability Tests
Conduct Usability Tests in QA with Proofing Agents
Synthesize Results from Proofing Agent Usability Tests
Launch IPP On-Site Pilot
Confirm Pilot Site(s)
Coordinate Pilot Recruitment with Perigean
Confirm Proofing Agent Volunteers
Schedule Pilot with Sites and Volunteers
Pilot Site Logistics and Team Travel Arrangements
Run IPP Pilot 1
Synthesize Results from IPP Pilot 1
Run IPP Pilot 2
Synthesize Results from IPP Pilot 2
Post-Pilot Updates to IPP
Complete LHDI counter-measures
Make Accessibility Improvements to Applications
Allow a Veteran to select a language
Resolve Continue Button functionality
Design and develop form validation
VA Notify - Send Confirmation Email
Integration with State ID Validation App
Resolve map functionality for scaled launch
GIS site data integration for map
Allow Veteran to select a Puerto Rico address
Make front-end design improvements based on research
Develop IAM/MPI lookup through IPP application
IPP Governance and Authorization
MPI as Authoritative Source
IPP Charter
ATO Discovery and Requirements
DIRA Statement Acceptance
Scale IPP for MVP Launch
Allow Veteran to cancel or reschedule
Lookup an existing Case Number
Send reminder email during 10 day window
Create option for showing a Passport
Identify 5 MVP Sites for rollout
Enable Validated PII on Login.gov
IPP Opt-in through Login.gov
VA Facility Onboarding
Proofing Agent Training and Onboarding
Launch MVP at Selected Sites
Full Scale Rollout for VA Identity Verifiers
Enable walk in without appointment
Build an IPP Support Team/Process
Develop integration with Login.gov via API
Transmit PII bundle to Login.gov
Onboarding ALL VA Facilities
Onboarding non-VA Facilities
Transmit PII bundle to Login.gov (IAL2)
Support for VA Community
Enable a larger VA support community as Proofing Agents
Enable access to additional sources of data for remote verification
Expand IPP into Another Agency
Expand IPP to include ID.me
IPP Opt-in through ID.me
Enable Validated PII on ID.me
Expand IPP for Trusted Referees

## Epics and Features
Epic | Story | Description | Team | Priority | Status
IPP - Prepare LHDI environments for application deployment |  | LHDI = Lighthouse Development Infrastructure. We're interested in using LHDI as a platform for IPP because it's scalable and approved and in use by some other internal Veteran departments. | Engineering | 1
| Research Access to LHDI | Discovery to learn what is needed to get team access to LHDI |  |  | Done
| Get Team Access to LHDI | Team will be able to access LHDI environments
| Deploy Hello world to QA environment on LHDI | Hello World application pushed to QA on LHDI platform
| Migrate Intake App to LHDI repo | Code for intake app moved to LHDI repository
| Create Repo for Proofing Application | Code repository created in LHDI environments
| Deploy Intake app to LHDA QA Environment | Intake app pushed to QA on LHDI platform
IPP - Proofing Agent flow through ID validation (front-end) |  | Build front-end screens on local machines through ID validation | Engineering | 2
| Proofing agent : Ask for ID evidence | Proofing agent is to ask the Veteran for their ID |  |  | Done
| Proofing Agent: Case ID Search | Proofing agent is to look up the Veteran's Case ID |  |  | Done
| Proofing agent: Confirm applicant email | Proofing agent sees the Veteran's email, confirms it's correct |  |  | Done
| Proofing agent : Authenticate ID (mock up between 2 types of ID) |  |  |  | In-Progress
| Proofing agent : Assert authentication of ID | Proofing agent confirms the ID is valid by reading through criteria
IPP - Proofing Agent Flow through Complete Verification (front-end) |  | Build front-end screens through completion of the Proofing Agent flow | Engineering | 3
| Proofing Agent - Fill in Information Page | Proofing agent fills in Veteran info in a form
| Proofing Agent - Complete Verification Applicant Summary Page | Proofing agent views info the input and can make corrections
| Proofing Agent - Complete Verification View Instructions | Proofing agent reads instructions to continue
| Proofing Agent - Complete Verification View Verify in IAM toolkit | Proofing agent uses the IAM toolkit to find the Veteran
| Proofing Agent - Complete Verification View Confirm Email | Proofing agent confirms the Veteran's email and address are correct
| Proofing Agent - Progress Bar | Proofing agent can see their progress through the steps
IPP - Deploy IPP Applications to LHDI |  | Migrate IPP applications from local machines to the LHDI platform | Engineering | 4
| Deploy Veteran Intake Application to LHDI | Migrate the Veteran Intake app to LHDI
| Deploy Proofing Agent Application to LHDI | Migrate the Proofing Agent app to LHDI
IPP - Integrate Login.gov with Intake Application |  | We will need to get Login.gov and the IPP applications talking to each other. Login.gov will need to accept the Veteran IAL2 status after completeing IPP | Engineering | 5
Login.gov Onboarding for IPP: Review documentation and sample apps
Onboarding : Ensure developers have access to integration dashboard
Compose authentication request
Process authentication response
| Create an Intake "Sign In" page for Veterans | For the pilot, Veterans will not experience the full flow of selecting IPP from Login.gov, so we will need a page for them to sign in to their login.gov account
IPP - Integrate Login.gov with Proofing Agent Application |  | We will need to get Login.gov and the IPP applications talking to each other. Login.gov will need to accept the Veteran IAL2 status after completeing IPP | Engineering | 6
Create sign in page for proofing agent application
Update Authentication Request to Require Proofing Agent to Sign in to Application with a PIV
Extract x.509 from authentication response
IPP Usability Test Planning - Veteran |  |  | Design | 7
| Draft screener questions for IPP Pilot Usability Test Veterans |  |  |  | Done
| Define recruitment criteria for IPP Pilot Usability Testing, Veterans |  |  |  | Done
| Draft Conversation Guide for IPP Pilot Veteran Intake Screens Usability Test |  |  |  | In-Progress
IPP Usability Test Planning - Proofing Agent |  |  | Design | 8
| Draft screener questions for IPP Pilot Usability Test Proofing Agents |  |  |  | Done
| Define recruitment criteria for IPP Pilot Usability Testing, Proofing Agents |  |  |  | Done
Draft Conversation Guide for IPP Pilot Proofing Agent Usability Test
IPP - Research VA Staff Workflows (SME Interviews) |  |  | Design | 9
SME Interview Conversation Guide
IPP - Application Refinements Pre-Pilot
Make Security Counter-Measures from CaTO Assessment
IPP - VA Notify: Send Confirmation Email to Veterans
IPP - Conduct Usability Tests with Proofing Agents
IPP Language Selection/Translation
IPP - Application Refinements Post-Pilot
IPP Pilot Launch Must Haves
All front-end development working and complete
Login.gov integration IdP
Veteran flow for selecting in-person proofing
Veteran flow when Veteran has a Login.gov
QA Testing
Unit Testing
LHDI Staging Deployment
LHDI Production Deployment
Resolve ID Lookup
VA Notify Integration

## Pilot Planning
Artifact | Owner | Timeline | Link to doc | Notes | Next Steps
Charter | Lauren | ASAP | https://docs.google.com/document/d/1eeJPB0Q5H4HwzE9HfbwIjVf2EO7_MTbTuMwYh1pfaFI/edit?usp=sharing | Propose split into phases | Finish, circulate, publish to Github
Document Authentication | Lauren |  | https://docs.google.com/document/d/1qawoXQYA4KvLg2VXfLljdgBFyyC_ht4xecgW9I3IlFg/edit?usp=sharing |  | Figure out who to ask about purchasing (cost to this)
DIRA | Lauren |  | https://www.idmanagement.gov/playbooks/dira/#high-level-dira-process | Digital Identity Risk Assessment | Not started - we will need this to get approval that our process is strong enough to qualify for IAL2. Next step ask Tom. Need to get template
ATO | Lauren | ASAP |  | leverage Tom and Chris Johnson so we don't have to get a full blown ATO for the pilot | Will need this for pilot
6510 Updated | Lauren

## IPP Dev Timeline
| 2024-03-01 |  | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01
Core Functionality
Data dog integration
Sign in Page
Dockerize
Update status of tickets
Login.gov integration with production [connect to sandbox]
Fill info check* server dependency
Pilot 1 (Simulation) |  | Test workflow, ID hardcoded
Low level remediation
Core Team integration
Complete L10 and L9 remediation tasks
VA Notify integration -Content and template evaluation -Apply to use service -Cost assessment -Connect to server -Integrate API into application
Discovery ID integration plug ins
Promoting application through regions -CATO Assessment -Run and deploy application through security pipeline -Remediation if needed -a11y assurance check -
Enable map functionality at location level (not office)
Pilot 2
Full ID checker integration including image pull
Integrate VA staff authorized user API
Pilot 3
Enable multiple sites