## Health Care
Hub: Health Care
Legacy URL | Redirect URL | Current Status | Who's Responsible | Zenhub Ticket | Last Comments/Notes
Not specified | Not specified | Live on site but still in a validated status on Zenhub | Daniellesocompany but needs to be reassigned (possibly Randi) | #17005 | Last comment by Randi: @mnorthuis @Karak888 I just validated that this pages looks good on the live site!
N/A | https://www.va.gov/health-care/ | Ready to be completed | Mikki Northius | #17390 | Selina: Modify the display order of links in the More Resources section on both the hub page and in the left nav to better group options and accommodate new option from the legacy writing. Last comment by Kara: Waiting on all healthcare changes to be done in CMS.
https://www.va.gov/HEALTHBENEFITS/vtp/Beneficiary_Travel.asp | https://www.va.gov/health-care/get-reimbursed-for-travel-pay/ | Icebox; follow-up w/SMEs for feedback | Daniellesocompany but needs to be reassigned (possibly Randi or Anne) | #16955 | Last comment by Randi: @AnneHurley @Karak888 @jenniferlee-dsva It seems the SMEs already have this page but we never got their comments back. Can we follow up and then we can build the page in Drupal and get it live. I can build the page in Drupal now so that it's ready to go with changes incorporated once we have the comments back.
https://www.va.gov/healthbenefits/VADIP/ | https://www.va.gov/health-care/about-va-health-benefits/dental-care/dental-insurance/ | Page seems to be live but the ticket is "Open" | Not assigned | #2491 | Last comments on ticket: @Karak888 commented on Tue Oct 15 2019 @RLHecht is this one good to close? @RLHecht commented on Tue Oct 15 2019 @Karak888 Yep, close it!

## Disability
Hub: Disability
Legacy URL | Redirect URL | Current Status | Who's Responsible | Zenhub Ticket | Last Comments/Notes
https://www.va.gov/disability/about-disability-ratings/effective-date/ | https://www.va.gov/disability/effective-date/ | Page needs to be redirected to new URL | Mikki Northius | #2449 | Last comment by Mikki: This is not specific to this page. Drupal does not do redirects at this time. This redirect needs to be handled just like all the others as we get that approach finalized. This means that this change cannot go live until we are ready to do the redirect in parallel with it, or users risk the chance of encountering a 404 if they use an old link or bookmark.
N/A | https://www.va.gov/disability/ | Backlog/ Not started | Mikki Northius | #18407 | Selina: Make changes to the URL in the Redirect URL column and left nav per the ticket On the Disability Hub page, add a link and teaster text for "Effective Dates" (label TBD) as second option in the More Resources section. Link here: /disability//effective-date/ On the Disability Left Nav, move "Effective Dates" out from under the "About Disability Ratings" option , and place just before "Compensation Rates".
N/A | https://www.va.gov/disability/eligibility/ | Backlog/ Not started | Mikki Northius | #15831 | First and last comment by Mikki: The existing links on the page should be reviewed to ensure we have all pages properly linked either in the content or as additional/crosslinks at the bottom. Currently there are not links to the PTSD or Special Claims pages.
Disability Benefits Questionnaires (DBQs) for Veterans: Create a Veteran-facing page providing an overview of what DBQs are, how to use them, and links to the forms. Based on https://www.benefits.va.gov/compensation/dbq_disabilityexams.asp?_ga=2.213293268.1732517843.1548703993-1173244138.1525894550, https://www.benefits.va.gov/compensation/dbq_overview.asp, https://www.benefits.va.gov/compensation/dbq_veteraninstruct.asp, https://www.benefits.va.gov/compensation/dbq_FAQs.asp. DBQ Forms: Combine the current forms pages into 1 and offer plain-language descriptions of conditions/symptoms (https://www.benefits.va.gov/compensation/dbq_ListByDBQFormName.asp and https://www.benefits.va.gov/compensation/dbq_ListBySymptom.asp). | N/A? See notes | Received SME feedback; wants to move away from DBQ process and plans to retire the legacy DBQ pages | N/A? | #16973 | Last comment by Mikki: I updated the Master URL spreadsheet and the Disability redirects ticket to reflect that we will not be migrating these pages, nor will we be handling any redirects for them. VBA will be responsible for retiring the legacy pages. Task checked off in list above.
Source Pages: https://benefits.va.gov/Compensation/current_rates_dic.asp https://benefits.va.gov/COMPENSATION/resources-rates-read-dic.asp | Proposed URLs: /survivor-dic-rates/ /parent-dic-rates/ | Need SME clarification on content | Randi Hecht, Anne Hurley | #1727, #3040, #1729, #18325 | Last comment by Jen on ticket #1727: Thanks @AnneHurley - the essential points for Angie would be... everything Angie might need to know to share with her management: Page name: Current URL inside the Burials hub: New URL inside the Disability hub: With a note that we will redirect the ^ Burials URL to the new Disability location + where else we are adding links pointing to the DIC page -- if we're adding for example on the Disability hub page, etc.) Plus when all this will happen -- looks like Wednesday ETA per Nick's message above. Can you also please re-confirm here for everyone before Wednesday morning ET if for whatever reason Angie says to hold? (So we don't merge/deploy this if so.)

## Education
Hub: Education and Training
Legacy URL | Redirect URL | Current Status | Who's Responsible | Zenhub Ticket | Last Comments/Notes
www.benefits.va.gov/gibill/non_college_degree.asp | www.va.gov/education/about-gi-bill-benefits/how-to-use-benefits/non-college-degree-programs/ | Page Published | Anne Hurley | #2098
www.benefits.va.gov/gibill/licensing_certification.asp | www.va.gov/education/about-gi-bill-benefits/how-to-use-benefits/test-fees/ | SME reviewed; edits published | Anne Hurley | #2098 | @RLHecht Yes, thanks. When the pages are live I'll send them to the SMEs to close the loop. Thanks much! Randi made the changes in Drupal and published page
www.benefits.va.gov/gibill/choosing_a_school.asp | www.va.gov/education/choosing-a-school/ | Page Published | Anne Hurley | #2098
www.benefits.va.gov/gibill/reap.asp | www.va.gov/education/other-va-education-benefits/reap/ | ?? | Anne Hurley | #2098
www.benefits.va.gov/gibill/veap.asp | www.va.gov/education/other-va-education-benefits/veap/ | Page Published | Anne Hurley | #2098
www.benefits.va.gov/GIBILL/DEA.asp | www.va.gov/education/survivor-dependent-benefits/dependents-education-assistance/ | SME reviewed; edits published | Anne Hurley | #2098 | @RLHecht Yes, thanks. When the pages are live I'll send them to the SMEs to close the loop. Thanks much! Randi made the changes in Drupal and published page
https://www.benefits.va.gov/GIBILL/resources/benefits_resources/rates/ch33/ch33rates080119.asp | Source Page: https://www.va.gov/education/benefit-rates/ | GitHub page created; not published or SME reviewed | Anne Hurley | #17828 | Last comment by Anne: @jenniferlee-dsva Can we regroup when you're back on this batch of Education Parity pages - It doesn't look like they've been shared yet with SMEs. Same for the Yellow Ribbon page, issue #19039. @RLHecht and I wanted to circle back with you on status of these so we can move them forward. thanks! Selina: The URL in the Legacy URL column is actually the source page for the subpages that will be created under the URL in the Redirect URL column.
https://www.benefits.va.gov/GIBILL/resources/benefits_resources/rates/ch30/ch30rates100118.asp | Source Page: https://www.va.gov/education/benefit-rates/ | GitHub page created; not published or SME reviewed | Anne Hurley | #17828 | Last comment by Anne: @jenniferlee-dsva Can we regroup when you're back on this batch of Education Parity pages - It doesn't look like they've been shared yet with SMEs. Same for the Yellow Ribbon page, issue #19039. @RLHecht and I wanted to circle back with you on status of these so we can move them forward. thanks! Selina: The URL in the Legacy URL column is actually the source page for the subpages that will be created under the URL in the Redirect URL column.
https://www.benefits.va.gov/GIBILL/resources/benefits_resources/rates/ch1606/ch1606rates100118.asp | Source Page: https://www.va.gov/education/benefit-rates/ | GitHub page created; not published or SME reviewed | Anne Hurley | #17828 | Last comment by Anne: @jenniferlee-dsva Can we regroup when you're back on this batch of Education Parity pages - It doesn't look like they've been shared yet with SMEs. Same for the Yellow Ribbon page, issue #19039. @RLHecht and I wanted to circle back with you on status of these so we can move them forward. thanks! Selina: The URL in the Legacy URL column is actually the source page for the subpages that will be created under the URL in the Redirect URL column.
https://www.benefits.va.gov/gibill/resources/benefits_resources/rates/600_buyup.asp | Source Page: https://www.va.gov/education/benefit-rates/ | GitHub page created; not published or SME reviewed | Anne Hurley | #17828 | Last comment by Anne: @jenniferlee-dsva Can we regroup when you're back on this batch of Education Parity pages - It doesn't look like they've been shared yet with SMEs. Same for the Yellow Ribbon page, issue #19039. @RLHecht and I wanted to circle back with you on status of these so we can move them forward. thanks! Selina: The URL in the Legacy URL column is actually the source page for the subpages that will be created under the URL in the Redirect URL column.
https://www.benefits.va.gov/GIBILL/resources/benefits_resources/rates/ch35/ch35rates100118.asp | Source Page: https://www.va.gov/education/benefit-rates/ | GitHub page created; not published or SME reviewed | Anne Hurley | #17828 | Last comment by Anne: @jenniferlee-dsva Can we regroup when you're back on this batch of Education Parity pages - It doesn't look like they've been shared yet with SMEs. Same for the Yellow Ribbon page, issue #19039. @RLHecht and I wanted to circle back with you on status of these so we can move them forward. thanks! Selina: The URL in the Legacy URL column is actually the source page for the subpages that will be created under the URL in the Redirect URL column.
https://www.benefits.va.gov/GIBILL/resources/benefits_resources/rates/ch1607/ch1607rates100118.asp | Source Page: https://www.va.gov/education/benefit-rates/ | GitHub page created; not published or SME reviewed | Anne Hurley | #17828 | Last comment by Anne: @jenniferlee-dsva Can we regroup when you're back on this batch of Education Parity pages - It doesn't look like they've been shared yet with SMEs. Same for the Yellow Ribbon page, issue #19039. @RLHecht and I wanted to circle back with you on status of these so we can move them forward. thanks! Selina: The URL in the Legacy URL column is actually the source page for the subpages that will be created under the URL in the Redirect URL column.
GI Bill and other education housing benefit rates /TBD - Anne to provide | Source Page: https://www.va.gov/education/benefit-rates/ | GitHub page created; not published or SME reviewed | Anne Hurley | #17828 | Last comment by Anne: @jenniferlee-dsva Can we regroup when you're back on this batch of Education Parity pages - It doesn't look like they've been shared yet with SMEs. Same for the Yellow Ribbon page, issue #19039. @RLHecht and I wanted to circle back with you on status of these so we can move them forward. thanks! Selina: The URL in the Legacy URL column is actually the source page for the subpages that will be created under the URL in the Redirect URL column.
Yellow Ribbon Schools: https://www.benefits.va.gov/GIBILL/yellow_ribbon/yrp_list_2018.asp | Main Page: https://www.va.gov/education/about-gi-bill-benefits/post-9-11/yellow-ribbon-program/ Proposed URLs: https://www.va.gov/education/about-gi-bill/post-9-11/yellow-ribbon-program/participating-schools/ https://www.va.gov//education/about-gi-bill/post-9-11/yellow-ribbon-program/participating-schools-alabama/ | Need to share Heroku links w/stakeholders and SMEs | Anne Hurley | #2612 | Last comment by Anne: ....For now here is what I recommend for the revised current Yellow Ribbon page. Yellow Ribbon page revise to include accordion/section of schools @jenniferlee-dsva for your review and @RLHecht for copyedit
www.benefits.va.gov/gibill/apply.asp | www.va.gov/education/how-to-apply/ | ?? | Anne Hurley | #2098 | [Education.parity-for SME review - v1] (https://github.com/department-of-veterans-affairs/va.gov-team/files/3794905/Education.parity-for.SME.review.-.v1.docx) @jenniferlee-dsva This is ready for you to review. These are three outstanding Education parity edits we need to run by the SMEs. The third one is a confusing user flow (the map link that doesn't go to a map page but instead to that confusing "loads" page) so instead of trying to capture screen shots which I thought could be even more confusing I tried to walk them through the flows. And I can demonstrate via shared screen with them on a call if desired.
https://www.benefits.va.gov/GIBILL/comparison_chart.asp | TBD | GitHub page created; not published or SME reviewed | Randi Hecht | #17818 | Last comment by DanielleSoCompany: Hi @RLHecht. This is ready for you! File: https://github.com/department-of-veterans-affairs/vagov-content/blob/content-WIP-rewriting-education/pages/education/compare-education-benefits.md Heroku: https://vagov-content-pr-375.herokuapp.com/education/compare-education-benefits/
https://www.benefits.va.gov/GIBILL/FGIB/Restoration.asp | TBD | GitHub page created; not published or SME reviewed | Randi Hecht | #17696 | Last comment by Randi: @Karak888 @AnneHurley @peggygannon @jenniferlee-dsva This page is probably ready to send to SMES as a next step. (Danielle had me do a final read on it, but there's no note that she moved it past that stage). Not sure who follows up and sends to SMES now.
https://benefits.va.gov/gibill/fgib/stem.asp | TBD | Not started | Not assigned | #19263 | Last comment by Mikki: @jenniferlee-dsva This page is not assigned to anyone as of yet, not sure if anyone had done this work?
N/A | https://www.va.gov/education/ | Not started | Mikki Northius | #18190 | Selina: It seems that no rewriting is needed; just reorganization of links on hub page noted in the Redirect URL column.
N/A | https://www.va.gov/education/about-gi-bill-benefits/ | Not started | Mikki Northius | #18319 | Last comment by Mikki: FYI, while this change would bring the page content and the nav/links into sync, I think there needs to be a bigger review of this page and how it is organized. Will need to determine if it is worthwhile to do this change first or hold off for a bigger review of the page. Selina: It seems that no rewriting is needed; just adding a link to page noted in the Redirect URL column.

## Careers
Hub: Careers
Legacy URL | Redirect URL | Current Status | Who's Responsible | Zenhub Ticket | Last Comments/Notes
https://www.benefits.va.gov/VOCREHAB/docs/BenefitsFollowingNaturalDisaster.pdf | NA / TBD?? | Not started/Icebox | Not assigned | #18324 | Selina: Based on the attached file in ticket, it seems that this needs SME feedback
https://www.benefits.va.gov/vocrehab/jobs_for_veterans.asp | NA / TBD?? | Not started/Icebox | Not assigned | #18324 | Selina: Based on the attached file in ticket, it seems that this needs SME feedback
https://www.benefits.va.gov/vow/ https://www.benefits.va.gov/VOW/tap.asp https://www.benefits.va.gov/VOW/vocational-rehabilitation.asp https://www.benefits.va.gov/VOW/for-employers.asp | NA / TBD?? | Not started/Icebox | Not assigned | #18324 | Selina: Based on the attached file in ticket, it seems that this needs SME feedback
https://www.benefits.va.gov/vocrehab/subsistence_allowance_rates.asp | NA / TBD?? | Not started/Icebox | Not assigned | #18324 | Selina: Based on the attached file in ticket, it seems that this needs SME feedback

## Pension
Hub: Pension
Legacy URL | Redirect URL | Current Status | Who's Responsible | Zenhub Ticket | Last Comments/Notes
https://www.benefits.va.gov/PENSION/current_protected_pension_rate_tables.asp | https://www.va.gov/pension/protected-pension-rates/ | In "Ready" status; Feedback received from SMEs but paused work due to contract transition | Danielle and Beth Potts/ Needs to be reassigned | #18514 | Last comment by Danielle: @bethpotts Could you please review this page? Thank you very much! https://github.com/department-of-veterans-affairs/vagov-content/blob/content-WIP-rewriting-pension/pages/pension/protected-pension-rates.md Also, to capture final notes: Added alert to new "improved" pension program Going to ask SMEs if we/they can provide PDFs with just the 1978 rates where needed so that we can offer as reference without providing 30-page Word docs. Went with the tentative assumption that "10 years or age 65" means a pension for a Veteran with 10 years of service or who is 65 years or older, but am going to ask SMEs to confirm this. Added a brief explanation for hospital reduction rates, and also going to run this by SMEs specifically for accuracy. Added old-law SBP info and links to historic rates. Simplified tables further and restructured eligibility info to provide that first and keep rates sections more focused.

## Life Insurance
Hub: Life Insurance
Legacy URL | Redirect URL | Current Status | Who's Responsible | Zenhub Ticket | Last Comments/Notes
N/A | https://www.va.gov/life-insurance/options-eligibility/ | Backlog/ Not started | Mikki Northius | #18323 | Last comment by Mikki: FYI, as part of the legacy content rewriting effort, the "Other Programs" page will be rewritten and this link will need to reflect correct link and labeling. Selina: It seems that no rewriting is needed for this page; just adding a link to page noted in the Redirect URL column.
N/A | https://www.va.gov/life-insurance/ | Backlog/ Not started | Mikki Northius | #18188 | Selina: It seems that no rewriting is needed; just reorganization of links on hub page noted in the Redirect URL column.
Not specified | TBD. Open question out to SMEs on this. May be a page, but likely will be content added to relevant pages. | Backlog/ Not started | Mikki Northius | #17955 | Last comment by Mikki: Per our conversation, I am adding this to the Life Ins open issues doc to understand whether the content on this page is updated regularly to respond to current trends in questions/calls, or if it stay primarily static over time. We have also discussed not writing "myths" as statements in the content in an effort to minimize any SEO impacts (we don't want myths coming up as statements in search results). One other option is to break apart the content on this page and place the appropriate FAQ content on the applicable program pages.
https://benefits.va.gov/INSURANCE/forms/VAP29-9.pdf | https://www.va.gov/life-insurance/options-eligibility/s-dvi/premium-rates/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned | #19032 | Last comment by Lillian: Notes/questions: @DanielleSoCompany ready for your review! -For the 2 Modified Life insurance types, is there a link we can include with this bullet point about how to buy additional insurance?: "When you turn 70 and your policy face value decreases, you can buy additional insurance to replace what you lost. Additional insurance costs $8.64 per month per $1000.00." -The page layout is incorrect; @aubreyarcangel, would you be able to help troubleshoot this? -For any insurance type that has a bullet point like this: "- Has slightly higher premium payments than an Ordinary Life policy" --- is this bullet point necessary? -Sentence casing for insurance policy types? -I added a Related link to this new premium rates page on this page, too https://www.va.gov/life-insurance/options-eligibility/s-dvi/ -Is the way I explained the calculation correct? I'm not sure I'm quite clear on how to do the calculation correctly, ha. -All descriptions of plan types match the descriptions of plan types on this page: https://vagov-content-pr-386.herokuapp.com/life-insurance/plans/
https://www.benefits.va.gov/insurance/vgli_rates_compare_vgli.asp | https://www.va.gov/life-insurance/options-eligibility/vgli/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned | #19014 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/INSURANCE/popups/non-payPOC.htm | Taken from ticket: Make this a subpage of the SGLI page for now. Confirming final url. | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned | #19012 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/insurance/plans.asp | TBD | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned | #18999 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/insurance/dividends_options.asp | https://www.va.gov/life-insurance/dividend-payment-options/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned (likely to Anne Hurley | #18968 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/INSURANCE/introCalc.asp#what (and the calculator itself at https://insurance.va.gov/NeedsCalculator) | https://www.va.gov/life-insurance/calculate-your-needs/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned (likely to Anne Hurley | #18940 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
We're merging the following pages into this 1 new page: https://www.benefits.va.gov/INSURANCE/select.asphttps://www.benefits.va.gov/INSURANCE/usgli.asphttps://www.benefits.va.gov/insurance/vri.asphttps://www.benefits.va.gov/INSURANCE/vsli.asphttps://www.benefits.va.gov/INSURANCE/nsli.asp (include the information from this pop-up - https://www.benefits.va.gov/INSURANCE/popups/pua.htm - directly on the page)https://www.benefits.va.gov/INSURANCE/capped_term.asp (include as relevant within the context of the NSLI and VSLI information) | https://www.va.gov/life-insurance/closed-programs/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned | #18862 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/INSURANCE/uninsurable.asp | https://www.va.gov/life-insurance/uninsurable-medical-conditions/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned (likely to Anne Hurley | #18847 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/INSURANCE/vgli_auto_pay.asp | Not specified | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned (likely to Anne Hurley or Randi) | #18844 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/insurance/tsgli_schedule_Schedule.asp | Possibly https://www.va.gov/life-insurance/options-eligibility/tsgli/loss-standards/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned (likely to Randi) | #18843 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/insurance/bfcs.asp May also be info in https://www.benefits.va.gov/INSURANCE/forms/BFCSBrochure1.htm and https://www.benefits.va.gov/INSURANCE/forms/BFCSBrochure2.htm | https://www.va.gov/life-insurance/financial-counseling/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned (likely to Anne Hurley or Randi) | #18783 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/INSURANCE/SOES.asp | https://www.va.gov/life-insurance/about-soes/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned | #17958 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/INSURANCE/converting.asp | https://www.va.gov/life-insurance/convert-to-commercial-policy/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned (likely to Anne Hurley) | #17956 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/INSURANCE/sglivgli.asp | https://www.va.gov/life-insurance/file-claim/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned | #17893 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.
https://www.benefits.va.gov/INSURANCE/updatebene.asp | https://www.va.gov/life-insurance/update-beneficiaries/ | Icebox/ Started but needs to be reviewed before sending to SMEs | DanielleSoCompany / Needs to be reassigned | #17892 | Last comment by Danielle: Transition status note: This, and all life insurance pages, are rough first drafts and will need thorough reviews/edits prior to sending to SMEs. @Karak888 for awareness. This can go to Icebox.

## Housing
Hub: Housing
Legacy URL | Redirect URL | Current Status | Who's Responsible | Zenhub Ticket | Last Comments/Notes
N/A | https://www.va.gov/housing-assistance/ | Ready status; not started | Mikki Northius | #18232 | Selina: Selina: Modify the display order of links in the More Resources section on both the hub page and in the left nav to better group options and accommodate new option from the legacy writing. Last comment by Kara: PR sent to housing team - @DanielleSoCompany to update upon review if this has been done already? left nav and hub page changes
Source page: https://www.benefits.va.gov/homeloans/resources_veteran.asp and https://www.va.gov/housing-assistance/home-loans/loan-types/purchase-loan/ | Not specified | Need SME feedback | Randi Hecht | #18129 | Last comment by Danielle: @Karak888 I'm reopening this issue to keep it on the radar. We paused this work due to transition. Need to check in with SMEs to see if they have any feedback on this page.
https://www.benefits.va.gov/homeloans/purchaseco_loan_limits.asp | Not specified | Received initial feedback; work paused due to transition | Daniellesocompany/ Needs to be reasssigned | #18128 | Last comment by Danielle: @Karak888 I am re-opening this so it stays on the radar. We received initial SME feedback (see attached pdf), but then paused the work due to SME workload and our transition. https://app.zenhub.com/files/31788863/2e18523c-df8c-4588-9026-8a4f640037f1/download
https://www.benefits.va.gov/homeloans/purchaseco_loan_fee.asp | https://www.va.gov/housing-assistance-home-loans/funding-fee/ | Received initial feedback; work paused due to transition | Randi Hecht | #17865 | Last comment by Danielle: @Karak888 I am re-opening this so it stays on the radar. We received initial SME feedback (see attached pdf), but then paused the work due to SME workload and our transition. https://app.zenhub.com/files/31788863/2e18523c-df8c-4588-9026-8a4f640037f1/download
N/A | https://www.va.gov/housing-assistance/home-loans/ | Backlog; not started | Mikki Northius | #18353 | Last comment by Mikki: As part of WBC, several pages were added to the Home Loan section and the left nav, however, they were not added to the content of the parent Home Loan page. Home Loan landing page: https://www.va.gov/housing-assistance/home-loans/
Review this page to determine how it should be organized and what links should be included within the content of the page.

## Burials
Hub: Burials
Legacy URL | Redirect URL | Current Status | Who's Responsible | Zenhub Ticket | Last Comments/Notes
Not specified | Not specified | Backlog; not started | Mikki Northius | #18851 | Last comment by Mikki: Additional audiences that have been considered for this module: Educators and Students - https://www.cem.va.gov/cem/legacy/index.asp Volunteers - https://www.cem.va.gov/cem/VolunteerNCA.asp Cemetery Operations/Management - https://www.cem.va.gov/cem/design_construction/index.asp State, Territorial or Tribal Governments - https://www.cem.va.gov/cem/grants/index.asp In discussion, we did not feel that the content for these audiences is related to Veteran benefits and do not feel that users would seek this content out under a "VA Benefits and Health Care" menu. We feel it is sufficient to have access to this content under the About VA menu > National Cemetery Administration where it is today.
N/A | https://www.va.gov/burials-memorials/ | Backlog; not started | Mikki Northius | #18849 | Last comment by Mikki: Modify the display order of links in the More Resources spoke on both the hub page and in the left nav based on changes made during parity/legacy rewriting work.
N/A | https://www.va.gov/burials-memorials/ | Backlog; not started | Mikki Northius | #18848 | Last comment by Mikki: Modify the display order of links in the Plan a Burial spoke on both the hub page and in the left nav based on changes made during parity/legacy rewriting work.
Source pages: https://benefits.va.gov/Compensation/current_rates_dic.asp https://benefits.va.gov/COMPENSATION/resources-rates-read-dic.asp | See notes | Icebox | Daniellesocompany / Needs to be reassigned | #18325 | Selina: I believe these pages are being moved to the Disability hub. See Line 7 on Disability spreadsheet. Last comment by Randi: @jenniferlee-dsva I took another stab at the DIC surviving parent rates page to get rid of some of the directions that were being repeated. The only way I saw to have the directions for finding your rate based on your yearly income not repeated for each set of accordions was to put it at the top. And I bumped up the "Your payment schedule" to an H3 so it wouldn't seem like it was part of step 5 of the subway map. Let me know what you think: preview-prod.vfs.va.gov/preview?nodeID=1013

## Record
Hub: Records
Legacy URL | Redirect URL | Migrated/New Writing Live Yet? | 1:1? | Zenhub Ticket | Notes
https://www.cem.va.gov/CEM/hmm/discharge_documents.asp | https://www.va.gov/records/accepted-discharge-documents/ | No |  | #18622
https://www.benefits.va.gov/COMPENSATION/NPRC1973Fire.asp | https://www.va.gov/records/get-military-service-records/reconstruct-records/ | Yes | Yes | #18622 | Also in line 16 of the Disablility Hub spreadsheet