## P1 – Harold
VA Mobile App: Rx UAT |  | Participant 1: Harold – Android | Session Date / Time 11/10/22 – 10:30 ET | Link to UAT plan
Scenario | Expected Results | Pass or Fail? | Additional Insights
1. Listed prescriptions (ALL users) | User views the name of the prescription and correct details Prescriptions are listed alphabetically by default | PASS | Seeing lots of active as well as inactive but when the active filter was applied it was the same number of active as MHV.
2. Prescription Details (ALL users) | User can select any of these prescriptions to view details for the selected prescription The details for the selected prescription are correct | PASS | All details seemed to be accurate.
3. Refill Prescriptions | User views refillable prescriptions in Refill modal User can successfully request a refill for a refillable prescription User views Summary Confirmation page with “success icon” next to requested prescription Can they re-request a refill? | PASS | Multi select fo refill only appears after you click, "Start refill request" but it seemed unatural that it was not available from the earlier view. THis is as expected
4. Prescriptions “in process” | Prescriptions with a status of “Active: Submitted” or “Active: Refill in Process” show up in the Processing tab | PASS
5. Trackable prescriptions | Prescriptions that have an associated tracking ID show up in the Tracking tab (even if they have already been delivered) | PASS | Date shipped of 9/28/22 for one of the perscriptions (delviered 10/3/22)
6. Tracking Details | User views tracking details for trackable prescriptions, by selecting the “View tracking details” button Selecting the tracking number takes the user to the service carrier site with more detailed tracking information for that package | PASS
end UAT |  |  | Not showing Rx when logged in under ID.me (usually uses MHV creds on web). Subsequent errors logging in that we think are maybe system level not app level. tried with RxR app as well and hit error getting 2FA code back.
Participant did not immediately see Health Care as the lane to follow on Home screen

## P2 – Blake
VA Mobile App: Rx UAT |  | Participant 2: Blake – Android | Session Date / Time | Link to UAT plan
Scenario | Expected Results | Pass or Fail? | Additional Insights
1. Listed prescriptions (ALL users) | User views the name of the prescription and correct details. Prescriptions are listed alphabetically by default.
2. Prescription Details (ALL users) | User can select any of these prescriptions to view details for the selected prescription. The details for the selected prescription are correct.
3. Refill Prescriptions | User views refillable prescriptions in Refill modal. User can successfully request a refill for a refillable prescription. User views Summary Confirmation page with “success icon” next to requested prescription.
4. Prescriptions “in process” | Prescriptions with a status of “Active: Submitted” or “Active: Refill in Process” show up in the Processing tab.
5. Trackable prescriptions | Prescriptions that have an associated tracking ID show up in the Tracking tab (even if they have already been delivered).
6. Tracking Details | User views tracking details for trackable prescriptions, by selecting the “View tracking details” button. Selecting the tracking number takes the user to the service carrier site with more detailed tracking information for that package.
end UAT |  |  | Unable to get the correct build 1.33.0 (366) installed

## P3 – Keith
VA Mobile App: Rx UAT |  | Participant 3: Keith iOS | Session Date / Time | Link to UAT plan
Scenario | Expected Results | Pass or Fail? | Additional Insights
1. Listed prescriptions (ALL users) | User views the name of the prescription and correct details Prescriptions are listed alphabetically by default
2. Prescription Details (ALL users) | User can select any of these prescriptions to view details for the selected prescription The details for the selected prescription are correct
3. Refill Prescriptions | User views refillable prescriptions in Refill modal User can successfully request a refill for a refillable prescription User views Summary Confirmation page with “success icon” next to requested prescription
4. Prescriptions “in process” | Prescriptions with a status of “Active: Submitted” or “Active: Refill in Process” show up in the Processing tab
5. Trackable prescriptions | Prescriptions that have an associated tracking ID show up in the Tracking tab (even if they have already been delivered)
6. Tracking Details | User views tracking details for trackable prescriptions, by selecting the “View tracking details” button Selecting the tracking number takes the user to the service carrier site with more detailed tracking information for that package
end UAT |  |  | Sign in sticking on blue spinner screen. We think it's a system level problem.

## P4
VA Mobile App: Rx UAT |  | Participant 4: Firstname | Session Date / Time | Link to UAT plan
Scenario | Expected Results | Pass or Fail? | Additional Insights
1. Listed prescriptions (ALL users) | User views the name of the prescription and correct details Prescriptions are listed alphabetically by default
2. Prescription Details (ALL users) | User can select any of these prescriptions to view details for the selected prescription The details for the selected prescription are correct
3. Refill Prescriptions | User views refillable prescriptions in Refill modal User can successfully request a refill for a refillable prescription User views Summary Confirmation page with “success icon” next to requested prescription
4. Prescriptions “in process” | Prescriptions with a status of “Active: Submitted” or “Active: Refill in Process” show up in the Processing tab
5. Trackable prescriptions | Prescriptions that have an associated tracking ID show up in the Tracking tab (even if they have already been delivered)
6. Tracking Details | User views tracking details for trackable prescriptions, by selecting the “View tracking details” button Selecting the tracking number takes the user to the service carrier site with more detailed tracking information for that package
end UAT

## P5
VA Mobile App: Rx UAT |  | Participant 5: Firstname | Session Date / Time | Link to UAT plan
Scenario | Expected Results | Pass or Fail? | Additional Insights
1. Listed prescriptions (ALL users) | User views the name of the prescription and correct details Prescriptions are listed alphabetically by default
2. Prescription Details (ALL users) | User can select any of these prescriptions to view details for the selected prescription The details for the selected prescription are correct
3. Refill Prescriptions | User views refillable prescriptions in Refill modal User can successfully request a refill for a refillable prescription User views Summary Confirmation page with “success icon” next to requested prescription
4. Prescriptions “in process” | Prescriptions with a status of “Active: Submitted” or “Active: Refill in Process” show up in the Processing tab
5. Trackable prescriptions | Prescriptions that have an associated tracking ID show up in the Tracking tab (even if they have already been delivered)
6. Tracking Details | User views tracking details for trackable prescriptions, by selecting the “View tracking details” button Selecting the tracking number takes the user to the service carrier site with more detailed tracking information for that package
end UAT

## Summary
VA Mobile App: Rx UAT |  | Participant 5: Firstname | Session Date / Time | Link to UAT plan
Scenario | Expected Results | Pass or Fail? | Additional Insights
1. Listed prescriptions (ALL users) | User views the name of the prescription and correct details Prescriptions are listed alphabetically by default
2. Prescription Details (ALL users) | User can select any 2 prescriptions (not Transferred) to view details for two prescriptions The details for the selected prescription are correct
3. Refill Prescriptions | User views refillable prescriptions in Refill modal User can successfully request a refill for a refillable prescription User views Summary Confirmation page with “success icon” next to requested prescription
4. Prescriptions “in process” | Prescriptions with a status of “Active: Submitted” or “Active: Refill in Process” show up in the Processing tab. If they have none, they should see an empty state
5. Trackable prescriptions | Prescriptions in-transit that have an associated tracking ID show up in the Tracking tab (even if they were delivered in last 15 days)
6. Tracking Details | User views tracking details for trackable prescriptions, by selecting the “View tracking details” button Selecting the tracking number takes the user to the service carrier site with more detailed tracking information for that package
end UAT